## BoQ
|  |  |  | CONTRACTED G.T.TRADE |  | Increase of works by VO1 |  | Decrease of works by VO1 |  | ADDENDUM NO. 1 |  | 1. SITUACIJA |  |  | 2. SITUACIJA |  |  | 3 .SITUACIJA |  |  | 4 .SITUACIJA |  |  | 5. SITUACIJA |  |  | 6. SITUACIJA |  |  | 7. SITUACIJA |  |  |  | 8. SITUACIJA |  |  | 9. SITUACIJA |  |  | 10. SITUACIJA |  |  | 11. SITUACIJA |  |  | 12. SITUACIJA |  | OKONČANA SITUACIJA |  |  | TOTAL |  |  | SVEUKUPNO
A | ARCHITECTURAL WORKS | [49 empty] | Quantity | Amount
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount | Quantity IPS 1 | Unit price | Amount | Quantity IPS 2 | Unit price | Amount | Quantity IPS 3 | Unit price | Amount | Quantity IPS 4 | Unit price | Amount | Quantity IPS 5 | Unit price | Amount | Quantity IPS 6 | Unit price | Amount | Quantity IPS 7 | Unit price | Amount | Quantity IPS 7 | Unit price | Amount | Quantity IPS 7 | Unit price | Amount | Quantity IPS 7 | Unit price | Amount |  | Unit price | Amount |  | Unit price | Amount
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  | 0 | [36 empty] | 0
[14 empty] | 0 | [36 empty] | 0
A.1 | Building for personnel | [12 empty] | 0 | [36 empty] | 0
[14 empty] | 0 | [36 empty] | 0 | 0
A.1.1 | Installation works | [12 empty] | 0 | [36 empty] | 0 | 0
| Supply, delivery and installation of prefabricated containers (type: residential and office containers) dimensions according to drawings 605 x 245 x 280 cm. The item includes a complete set of equipment and furniture for the office, small kitchen, closet, bathroom, table, shelves, chairs, air conditioning, doors, windows, flooring, installation, etc., all according to the drawings and designer's selection. | [12 empty] | 0 | [36 empty] | 0 | 0
| The container has a supporting structure of welded cold formed profiles. Containers are placed on previously prepared concrete slab | [12 empty] | 0 | [36 empty] | 0 | 0
| Color of containers: RAL 9002 | [12 empty] | 0 | [36 empty] | 0 | 0
| Calculation per piece. | [12 empty] | 0 | [36 empty] | 0 | 0
| List of furniture and equipment | [12 empty] | 0 | [36 empty] | 0 | 0
| -4 wardrobe cabinets | [12 empty] | 0 | [36 empty] | 0 | 0
| -1 desk with two cabinets with drawers 580 x 75 cm | [12 empty] | 0 | [36 empty] | 0 | 0
| -2 chairs (office) | [12 empty] | 0 | [36 empty] | 0 | 0
| -office shelves (h = 220 cm, l = 450 cm) | [12 empty] | 0 | [36 empty] | 0 | 0
| -kitchen, lower and upper elements (including a sink, smal stove, refrigerator, etc.) | [12 empty] | 0 | [36 empty] | 0 | 0
| -1 dinning table (180 x 40 cm - counter table) and 2 chairs | [12 empty] | 0 | [36 empty] | 0 | 0
| -Floor mat, clothes hanger, container for umbrellas etc | [12 empty] | 0 | [36 empty] | 0 | 0
| -complete sanitary facilities (sink, toilet, toilet tank, mirror, etc.) | [12 empty] | 0 | [36 empty] | 0 | 0
| Item includes all the work, supply and the necessary materials to complete certainty | set | 1 | 65000 | 65000 | 0 | 0 | 0 | 0 | 1 | 65000 |  |  | 0 | [21 empty] | 1 | 65000 | 65000 | [12 empty] | 1 | 65000 |  | 1 | 65000 | 65000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.1.2 | Complete cleaning and washing of all spaces before handing over the building. Including cleaning and washing of floor, wall and ceiling panels as well as carpentry and locksmithing with corresponding glazing | set | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 1 | 500 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 500 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.1 | Building for personnel TOTAL |  |  |  | 65500 |  | 0 |  | 0 |  | 65500 |  |  | 0 | [23 empty] | 65000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 65000 |  | 0 | 0 | 65000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.2 | Fence | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.2.1 | Fence | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, delivery and installation of wired fence. Height of completed fence, from finished terrain elevation is 2.0 m. It is made of steel columns and wired fence. Columns are treated with zinc on the outside and the inside and are plasticised (min. 60 micron). Fence foundation is a single foundation. Total dimensions of the cross section are 50/80 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Columns are steel, galvanized with additional plastic protection as a final layer. They are placed at a maximum distance of 2,0 m, in the foundations. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| All these elements are included in the price, along with all the necessary fittings and works. All other details of the fence are to be carried out according to the design. All metal parts of the fence have to be grounded. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Item includes all works, supply and necessary materials to complete certainty. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Color of the complete fence is dark green: RAL 6005. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation per m' of the installed fence. | m´ | 200 | 250 | 50000 | 0 | 0 | 0 | 0 | 200 | 50000 |  |  | 0 | [24 empty] | 250 | 250 | 62500 |  | 0 | 0 |  | 200 | 0 |  |  |  | 250 | 62500 |  | 250 | 250 | 62500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.2.2 | Double turnaround enterance doors | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| 5,70 x 1,75 m | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply and installazion of double hinged entrance doors (driveway) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Width: 570 cm, Height: 157 cm, filling made of rectangular pipes 20x30 mm in the framework of square pipes 130x130 mm. The doors are equipped with the lock and the latch. Item includes installation of remote control (control of entry and exit in the building for personnel). It includes all the works, supply with the necessary materials to complete safety. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Color of the doors is darg green: RAL 6005 (and the fence). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calaculation per piece. | pcs | 1 | 19000 | 19000 | 0 | 0 | 0 | 0 | 1 | 19000 |  |  | 0 | [24 empty] | 1 | 19000 | 19000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 19000 |  | 1 | 19000 | 19000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.2.3 | Single hinged doors, dimensions 100 x 200 cm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply and installazion of single hinged entrance doors (pedestrian entrance) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Width: 100 cm, Height: 157 cm, filling made of rectangular pipes 20x30 mm in the framework of square pipes 130x130 mm. The doors are equipped with the lock and the latch. Item includes installation of remote control (control of entry and exit in the building for personnel). It includes all the works, supply with the necessary materials to complete certainty. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Color of the doors is darg green: RAL 6005 (and the fence). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calaculation per piece. | pcs | 1 | 5000 | 5000 | 0 | 0 |  | 0 | 1 | 5000 |  |  | 0 | [24 empty] | 1 | 5000 | 5000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 5000 |  | 1 | 5000 | 5000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.2 | Fence TOTAL |  |  |  | 74000 |  | 0 |  | 0 |  | 74000 |  |  | 0 | [23 empty] | 0 |  |  | 86500 |  |  | 0 |  |  | 0 |  |  |  | 0 | 86500 |  | 0 | 0 | 86500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.3 | Landscaping | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.3.1 | Landscaping | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Item includes complete exectuion of landscaping. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For better integration of the complex into the environment, protective green buffer zone will be formed, which will, together with the fence, create hight-quality visual barrier. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Item includes greening. It includes all the necessary actions adjusted to the terrain and the existing situation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Finishing works on green areas include milling to a depth of 20 cm, straightening and raking (fine planning) of disturbed earth with fragmentation, fertilization with organic manure 5 l/m2, and supply and installation of grass mixture in an amount of 4 dkg/m2 that consists of drizzle grass and true grass. After sowing the seeds of grass mixture, manual rolling with a roller should be carried out, and a one-time watering in an amount of 10 l/m2. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| grassing | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Conducted surfaces maintain up to completion of all planned works. Include the following works: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Mowing lawns during the implementation of the contract with the collection and disposal of cuttings, cleaning green areas, watering of green areas, if necessary, complete Phytosanitary protection, if necessary, in warranty, repair all the possible damages caused to the green. Calculation: 15% of the works procurement and planting shrubs and trees. | set | 1 | 80000 | 80000 | 0 | 0 |  | 0 | 1 | 80000 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 80000 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.3 | Landscaping TOTAL |  |  |  | 80000 |  | 0 |  | 0 |  | 80000 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4 | Equipment | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4.1 | Equipment | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Item includes supply and all necessary work for installation of containers and equipment (all according to the design) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| weigh 40 t | set | 1 | 200000 | 200000 | 0 | 0 |  | 0 | 1 | 200000 |  |  | 0 | [21 empty] | 0.9 | 200000 | 180000 | 0.1 | 200000 | 20000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 200000 |  | 1 | 200000 | 200000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4.2 | Fire extinguishers and handy tool | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4.2.1 | They are used to localize fires that would eventually appear. They are placed in visible end easy accessible places at a height of 1.5 m, according to the plan given in Fire protection study. Envisaged extinguishers are dust type ˝S˝. Item includes supply, delivery and installation of fire extinguishers. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| S 6 kg | pcs | 3 | 1000 | 3000 | 0 | 0 |  | 0 | 3 | 3000 |  |  | 0 | [24 empty] | 3 | 1000 | 3000 |  | 0 | 0 |  | 3 | 0 |  |  |  | 3 | 3000 |  | 3 | 1000 | 3000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4.2.2 | A handy tool consists of shovel, pick, hoes, metal broom for fire extinguishing, 2 birch brooms for cleaning asphalt surfaces. | set | 1 | 1500 | 1500 | 0 | 0 |  | 0 | 1 | 1500 |  |  | 0 | [24 empty] | 1 | 1500 | 1500 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 1500 |  | 1 | 1500 | 1500
| Item includes supply and delivery of the specified set of handy tool. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4.3. | Permanent Board | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Graphic preparation and design of permanent board for the purpose of informing and visibility of the project according. The frame dimensions are 100x60 cm. | pcs | 1 | 4000 | 4000 | 0 | 0 |  | 0 | 1 | 4000 |  |  | 0 | [21 empty] | 1 | 4000 | 4000 | [12 empty] | 1 | 4000 |  | 1 | 4000 | 4000
| Board will be of PVC with the text “Adriatic Sea Environmental Pollution Control Project (I), Remediation works of landfill Sitnica with closed leachate system” with specified year of ending of construction, with logos of World Bank, Global Environmental Facility (GEF), Environmental Protection and Energy Efficiency Fund. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Board shall be in Croatian Language. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
A.4 | Equipment TOTAL |  |  |  | 208500 |  | 0 |  | 0 |  | 208500 |  |  | 0 | [23 empty] | 184000 |  |  | 24500 |  |  | 0 |  |  | 0 |  |  |  | 0 | 208500 |  | 0 | 0 | 208500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A | ARCHITECTURAL WORKS | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A.1 | BUILDING FOR PERSONNEL |  |  |  | 65500 |  | 0 |  | 0 |  | 65500 |  |  | 0 | [23 empty] | 65000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 65000 |  | 0 | 0 | 65000
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A.2 | FENCE |  |  |  | 74000 |  | 0 |  | 0 |  | 74000 |  |  | 0 | [23 empty] | 0 |  |  | 86500 |  |  | 0 |  |  | 0 |  |  |  | 0 | 86500 |  | 0 | 0 | 86500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A.3 | LANDSCAPING |  |  |  | 80000 |  | 0 |  | 0 |  | 80000 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A.4 | EQUIPMENT |  |  |  | 208500 |  | 0 |  | 0 |  | 208500 |  |  | 0 | [23 empty] | 184000 |  |  | 24500 |  |  | 0 |  |  | 0 |  |  |  | 0 | 208500 |  | 0 | 0 | 208500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
A | ARHITECTURAL WORKS SUMMARY |  |  |  | 428000 |  | 0 |  | 0 |  | 428000 |  |  | 0 | [23 empty] | 249000 |  |  | 111000 |  |  | 0 |  |  | 0 |  |  |  | 0 | 360000 |  | 0 | 0 | 360000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B | CIVIL WORKS - TRAFFIC AND MANIPULATIVE AREA | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.1 | Preparation works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.1.1 | Staking out of route and objects. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| All geodetic surveys where data from design are transferred to the field and vice versa, during entire building works period, i.e. until presentation of works to the investor, are measured and charged by m2. | set | 1 | 3000 | 3000 | 0 | 0 |  | 0 | 1 | 3000 |  |  | 0 | [21 empty] | 1 | 3000 | 3000 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 3000 |  | 1 | 3000 | 3000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.1.2 | Survey of the "as built" condition of the roadways after final completion of all works. Survey shall be performed by the authorized company. Calculation shall be based on surveyed area. | set | 1 | 4500 | 4500 | 0 | 0 |  | 0 | 1 | 4500 |  |  | 0 | [27 empty] | 1 | 4500 | 4500 |  | 0 | 0 |  |  |  | 1 | 4500 |  | 1 | 4500 | 4500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.1.3 | Traffic regulation where necessary during works period. Safeguard of construction site, including all necessary signs, light signals and similar. | set | 1 | 2000 | 2000 | 0 | 0 |  | 0 | 1 | 2000 |  |  | 0 | [21 empty] | 1 | 2000 | 2000 |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 2000 |  | 1 | 2000 | 2000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.1 | Preparation works TOTAL |  |  |  | 9500 |  | 0 |  | 0 |  | 9500 |  |  | 0 | [23 empty] | 5000 |  |  | 0 |  |  | 4500 |  |  | 0 |  |  |  | 0 | 9500 |  | 0 | 0 | 9500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2 | Excavation works and sub base of roadway | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2.1 | Excavation on existing ground of category B for construction of plateau and roads. ( HRN U.E1.010) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Works include wide excavation for construction of the calculated roadway layer thickness. Safety precautions and required safeguard of existing objects, installations and communications shall be undertaken during excavation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Adequate machines shall be engaged in wide excavation, while manual excavation should be limited to required minimum. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Extreme precautions shall be applied during excavation, while excavation adjacent to installation shall be performed manually. Manual excavation volume is assumed to be 20%. All excavations shall be arranged in line with foreseen elevations and slope as per design and in accordance to the supervisory engineer requirements. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation shall be based on the m3 of excavated material in crammed condition. | m3 | 685 | 40 | 27400 | 0 | 0 |  | 0 | 685 | 27400 |  |  | 0 | [27 empty] | 53 | 40 | 2120 |  | 0 | 0 |  |  |  | 53 | 2120 |  | 53 | 40 | 2120
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2.2 | Making the embankment of gravel or stone (dolomite): | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| This work includes: - delivery of the filling material of gravel or stone (dolomite) from site-reclamation and siltation layers of 30 cm - possibly wetting or drying, and compaction and planning materials in the embankment by the dimensions and grades given in the project. Mound under gates surface running of gravel or stone (dolomite) in the layer whose thickness is determined depending on the type of material and the compactor. Tamping should be done so that every layer reaches ME = 40 N/mm2. The calculation is done per m3 made ​​embankments in packed condition. | m3 | 360 | 27 | 9720 | 0 | 0 |  | 0 | 360 | 9720 |  |  | 0 | [27 empty] | 284 | 27 | 7668 |  | 0 | 0 |  |  |  | 284 | 7668 |  | 284 | 27 | 7668
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2.3 | Construction of roadway bed. Mechanical compaction of roadway base layer. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price includes previous cleaning and leveling as well as work necessary to obtain optimal soil moisture either by damping or drying and crushing. For stony ground, the price includes leveling with up to 20 cm layer of small stones and compaction. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Performance, quality control and calculation of charges according to the General technical conditions for roadworks. | m2 | 515 | 15 | 7725 | 0 | 0 |  | 0 | 515 | 7725 |  |  | 0 | [27 empty] | 537 | 15 | 8055 |  | 0 | 0 |  |  |  | 537 | 8055 |  | 537 | 15 | 8055
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2.4 | Construction of roadway buffer layer (40 cm thick). Procurement and supply of gravel or crushed stones, construction of roadway buffer layer of total thickness equal to 40 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Gravel of adequate size class and required purity, previously examined, shall be used. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Compaction with adequate compactors in order to obtain bulk density of Me = 60 MN/m . | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The calculation shall be based on m3 of required and used gravel. | m3 | 220 | 75 | 16500 | 0 | 0 |  | 0 | 220 | 16500 |  |  | 0 | [27 empty] | 214.8 | 75 | 16110 |  | 0 | 0 |  |  |  | 214.8 | 16110 |  | 214.8 | 75 | 16110
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.2 | Excavation works and sub base of roadway TOTAL |  |  |  | 61345 |  | 0 |  | 0 |  | 61345 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 33953 |  |  | 0 |  |  |  | 0 | 33953 |  | 0 | 0 | 33953
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.3 | Pavement structure | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.3.1 | Machine paving of bitumen support layer, mixed and laid using hot mixed technology with bitumen and mixture of approved working composition. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For a medium traffic load, type AC 22 base 50/70, layer thickness 8,0 cm for roads and handling areas | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price shall include supply of machine made mixture of stone dust, gravel and bitumen as binder, of largest granule nominal size, stone type and granularity as per directives stated in design, as well as loading, transport and machine paving (scattering and compaction). | m2 | 480 | 145 | 69600 | 0 | 0 |  | 0 | 480 | 69600 |  |  | 0 | [27 empty] | 537 | 145 | 77865 |  | 0 | 0 |  |  |  | 537 | 77865 |  | 537 | 145 | 77865
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.3.2 | Machine paving of top layer in hot mix asphalt concrete (HS-AB), bitumen type and mixture of approved working composition. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For a medium traffic load, type AC 11 surf 50/70, layer thickness 4,0 cm for road and handling areas. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price shall include supply of machine made mixture of stone dust, gravel and bitumen as binder (road paving bitumen or polymer modified bitumen), stone type and granularity based on the thickest mixture rule, loading, transport, machine paving (scattering and compaction). | m2 | 480 | 91 | 43680 | 0 | 0 |  | 0 | 480 | 43680 |  |  | 0 | [27 empty] | 537 | 91 | 48867 |  | 0 | 0 |  |  |  | 537 | 48867 |  | 537 | 91 | 48867
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.3.3 | Installation of concrete curb 15x25x100 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Concrete curbs supplied as a precast concrete elements which must meet the following requirements; | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Concrete curbs must be made of concrete compressive strength C40 / 45, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Precast concrete elements must have straight edges and surfaces without cracks, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Incorporation of damaged pieces cannot allow, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Curbs are installed along the line and finished grade on concrete C16 / 20 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| This item includes the following; | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Supply of prefabricated concrete elements curb C40 / 45 with all drive the curb at the construction site. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Preparation of the substrate with the necessary excavation or filling and compaction, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Design and installation of concrete pads compressive strength C16 / 20 to the processing and plating, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Laying concrete curbs in the direction and leveling, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - All transports and transfers concrete and auxiliary materials, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Watering joints with cement mortar 1: 4, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - It concrete and quality testing curbs and pads with obtaining certificates, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Dimensions curbs are 15 x 25 x 100 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation per m 'built a concrete curb. | m | 140 | 135 | 18900 | 0 | 0 |  | 0 | 140 | 18900 |  |  | 0 | [27 empty] | 160 | 135 | 21600 |  | 0 | 0 |  |  |  | 160 | 21600 |  | 160 | 135 | 21600
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.3 | Pavement structure TOTAL |  |  |  | 132180 |  | 0 |  | 0 |  | 132180 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 148332 |  |  | 0 |  |  |  | 0 | 148332 |  | 0 | 0 | 148332
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.4 | Walkaway | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.4.1 | Machine paving of bitumen support layer, mixed and laid using hot mixed technology with bitumen and mixture of approved working composition. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For a medium traffic load, type AC 22 base 50/70, layer thickness 4,0 cm for roads and handling areas. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price shall include supply of machine made mixture of stone dust, gravel and bitumen as binder, of largest granule nominal size, stone type and granularity as per directives stated in design, as well as loading, transport and machine paving (scattering and compaction). | m2 | 31 | 90 | 2790 | 0 | 0 |  | 0 | 31 | 2790 |  |  | 0 | [27 empty] | 31 | 90 | 2790 |  | 0 | 0 |  |  |  | 31 | 2790 |  | 31 | 90 | 2790
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.4.2 | Machine paving of top layer in hot mix asphalt concrete (HS-AB), bitumen type and mixture of approved working composition. For a medium traffic load, type AC 11 surf 50/70, layer thickness 5,0 cm for road and handling areas. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price shall include supply of machine made mixture of stone dust, gravel and bitumen as binder (road paving bitumen or polymer modified bitumen), stone type and granularity based on the thickest mixture rule, loading, transport, machine paving (scattering and compaction). | m2 | 31 | 105 | 3255 | 0 | 0 |  | 0 | 31 | 3255 |  |  | 0 | [27 empty] | 31 | 105 | 3255 |  | 0 | 0 |  |  |  | 31 | 3255 |  | 31 | 105 | 3255
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.4.3 | Installation of concrete curbs 8x20x50 cm around the sidewalk near the building for staff. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Concrete curbs supplied as a precast concrete elements which must meet the following requirements; | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Concrete curbs must be made of concrete compressive strength C40 / 45, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Precast concrete elements must have straight edges and surfaces without cracks, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Incorporation of damaged pieces cannot allow, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Curbs are installed along the line and finished grade on concrete C16 / 20 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| This item includes the following; | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Supply of prefabricated concrete elements curb C40 / 45 with all drive the curb at the construction site. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Preparation of the substrate with the necessary excavation or filling and compaction, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Design and installation of concrete pads compressive strength C16 / 20 to the processing and plating, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Laying concrete curbs in the direction and leveling, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - All transports and transfers concrete and auxiliary materials, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Watering joints with cement mortar 1: 4, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - It concrete and quality testing curbs and pads with obtaining certificates, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Dimensions curbs are 8 x 20 x 50 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation per m 'built a concrete curb. | m | 28 | 100 | 2800 | 0 | 0 |  | 0 | 28 | 2800 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 100 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.4 | Walkaway TOTAL |  |  |  | 8845 |  | 0 |  | 0 |  | 8845 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 6045 |  |  | 0 |  |  |  | 0 | 6045 |  | 0 | 0 | 6045
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5 | Roadway infrastructure | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5.1 | Excavation of foundations, fabrication of concrete foundations (truncated pyramid like, with base and top edge length of 30 and 20 cm respectively) made of class C 20/25 concrete, including supply, installation and treatment and backfilling and removal of excess material after completion. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price includes supply of material, form board for foundation, installation of anchoring and support pads for fixing the pole. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation shall be based on number of completed foundations. | pcs | 2 | 300 | 600 | 0 | 0 |  | 0 | 2 | 600 |  |  | 0 | [27 empty] | 2 | 300 | 600 |  | 0 | 0 |  |  |  | 2 | 600 |  | 2 | 300 | 600
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5.2 | Setting traffic sign posts (supports), one post per sign, made of Fe pipe, dia 63,5 mm, hot galvanized 85 μm layer or double system of the same protection, dimensions and type in accordance to the traffic infrastructure and signals design and in line with Regulations on traffic signs, infrastructure and signals on road (Official Gazette No. 33/2005) and Croatian Standard HRN EN 12899-1. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price includes supply and setting of post according to design (made of aluminum or Fe pipes), including transport, shifting and storage as well as all works and materials for installation according to design requirements. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation shall be based on number of signs set. | pcs | 2 | 600 | 1200 | 0 | 0 |  | 0 | 2 | 1200 |  |  | 0 | [27 empty] | 2 | 600 | 1200 |  | 0 | 0 |  |  |  | 2 | 1200 |  | 2 | 600 | 1200
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5.3 | Setting up mandatory (traffic) signs, circle shaped, (exceptionally octagon or equilateral triangle) of 60 cm diameter according to the traffic infrastructure and signals design and in line with Regulations on traffic signs, infrastructure and signals on roads (Official Gazette No. 33/2005) and Croatian Standard HRN 1116, HRN EN 12899-1, HRN EN 1790. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price includes production and supply with painting and gluing foil (1st class retroreflexion according to HRN EN 1436:2001 en - engineer intensity), transport, shifting, storage as well as all works and material, bolting and accessories for mounting in line with design requirements. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation shall be based on number of signs set. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| B02 - mandatory stop | pcs | 1 | 700 | 700 | 0 | 0 |  | 0 | 1 | 700 |  |  | 0 | [27 empty] | 1 | 700 | 700 |  | 0 | 0 |  |  |  | 1 | 700 |  | 1 | 700 | 700
| B31 - speed limit | pcs | 1 | 700 | 700 | 0 | 0 |  | 0 | 1 | 700 |  |  | 0 | [27 empty] | 1 | 700 | 700 |  | 0 | 0 |  |  |  | 1 | 700 |  | 1 | 700 | 700
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5.4 | Making longitudinal road surface marking, of size and color in accordance to the traffic infrastructure and signals design and in line with Regulations on traffic signs, infrastructure and signals on road (Official Gazette No. 33/2005) and Croatian Standard HRN EN 1436, HRN EN 1871, HRN EN 1463-1 and 2, HRN U.S4.221, HRN U.S4.222, HRN U.S4.223. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Full line, single, (centerline, borderline, direction line in front of obstacles), 10 cm wide. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The price includes cleaning of roadway immediately before making signs, tracing, provision and supply of material (paint, thinner, reflective markers), obtaining necessary permits and quality control certificates, all works, accessories and equipment for making marking. | m | 130 | 15 | 1950 | 0 | 0 |  | 0 | 130 | 1950 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 15 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
B.5 | Roadway infrastructure TOTAL |  |  |  | 5150 |  | 0 |  | 0 |  | 5150 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3200 |  |  | 0 |  |  |  | 0 | 3200 |  | 0 | 0 | 3200
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B | CIVIL WORKS - TRAFFIC AND MANIPULATIVE AREA | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.1 | PREPARATION WORKS |  |  |  | 9500 |  | 0 |  | 0 |  | 9500 |  |  | 0 | [23 empty] | 5000 |  |  | 0 |  |  | 4500 |  |  | 0 |  |  |  | 0 | 9500 |  | 0 | 0 | 9500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.2 | EXCAVATION WORKS AND SUB BASE OF ROADWAY |  |  |  | 61345 |  | 0 |  | 0 |  | 61345 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 33953 |  |  | 0 |  |  |  | 0 | 33953 |  | 0 | 0 | 33953
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.3 | PAVEMENT STRUCTURE |  |  |  | 132180 |  | 0 |  | 0 |  | 132180 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 148332 |  |  | 0 |  |  |  | 0 | 148332 |  | 0 | 0 | 148332
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.4 | WALKWAY |  |  |  | 8845 |  | 0 |  | 0 |  | 8845 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 6045 |  |  | 0 |  |  |  | 0 | 6045 |  | 0 | 0 | 6045
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.5 | ROADWAY INFRASTRUCTURE |  |  |  | 5150 |  | 0 |  | 0 |  | 5150 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3200 |  |  | 0 |  |  |  | 0 | 3200 |  | 0 | 0 | 3200
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B.6 | PREPARATION OF DOCUMENTATION |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
B | CIVIL WORKS - TRAFFIC AND MANIPULATIVE AREA SUMMARY |  |  |  | 217020 |  | 0 |  | 0 |  | 217020 |  |  | 0 | [23 empty] | 5000 |  |  | 0 |  |  | 196030 |  |  | 0 |  |  |  | 0 | 201030 |  | 0 | 0 | 201030
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C | CIVIL WORKS - WATER SUPPLY AND DRAINAGE | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1 | Drainage | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1 | Earthworks | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.1 | Machine excavation of material in category C to a depth h [m] depending on the structure with vertical nicking. The works carried out depend on the equipment and technology of the contractor for all depths. The width of the trench is dependent on the normal profile and the size of the pipe. The excavated soil is rejected aside within the work zone, and if necessary in tight spaces is transported, deposited and again transported to the place of installation when backfilling. Excavation method determined by the Contractor, and the calculations are to be carried out according to the amounts of the ideal profile of the main design so that the excess excavation shall be calculated in the price and will not be subsequently recognized. The item includes all the necessary papers and equipment for shoring and securing the trench from collapsing, according to the technology contractor, in accordance with the prescribed conditions of safety at work, including excavation required for the installation of protective plates (which is not particularly specified). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Materials excavation (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Objects of the drainage system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Ispection shafts - 76 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Water inlets - 44 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 46,80 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| d) Absorption well - 21,15 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Oily rainfall | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Oily drainage system pipeline, trench depth 1,50 m, - 19 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary waste water pipeline, trench depth 1 m, - 1,40 m3 | m3 | 208.35 | 35 | 7292.25 | 0 | 0 |  | 0 | 208.35 | 7292.25 |  |  | 0 | [27 empty] | 44 | 35 | 1540 |  | 0 | 0 |  |  |  | 44 | 1540 |  | 44 | 35 | 1540
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.2 | Backfilling the area around the buildings carried out by selected material from excavation grit 0-32 mm to designed certain angle. The item includes leveling and compacting the material in layers of 30 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Backfilling with excavation material | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Ispection shafts - 47 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Water inlets - 40 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 23 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| d) Absorption well - 10,20m3 | m3 | 120.2 | 18 | 2163.6 | 0 | 0 |  | 0 | 120.2 | 2163.6 |  |  | 0 | [21 empty] | 27.15 | 18 | 488.7 | 42.39 | 18 | 763.02 | 40 | 18 | 720 |  | 0 | 0 |  |  |  | 109.54 | 1971.72 |  | 109.54 | 18 | 1971.72
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.3 | Preparation of filling of the space around the absorption well with stone material grit 60/120 mm. The item includes leveling and compacting the material in layers of 30 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Preparation of filling | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Absorption well filling | m3 | 25 | 100 | 2500 | 0 | 0 |  | 0 | 25 | 2500 |  |  | 0 | [23 empty] | 0 | 31.05 | 100 | 3105 |  | 0 | 0 |  | 25 | 0 |  |  |  | 31.05 | 3105 |  | 31.05 | 100 | 3105
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.4 | Supply and delivery of sand grit 0-12 mm and making sand foundation level with thickness of 10 cm for laying pipelines. The item includes compaction by manual compactor. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Preparation of sand foundation level | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) potentially oily rainfall drainage system pipeline - 1,85 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary waste water pipeline - 0,15 m3 | m3 | 2 | 160 | 320 | 0 | 0 |  | 0 | 2 | 320 |  |  | 0 | [24 empty] | 12.92 | 160 | 2067.2 |  | 0 | 0 |  | 2 | 0 |  |  |  | 12.92 | 2067.2 |  | 12.92 | 160 | 2067.2
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.5 | Supply and delivery of sand / gravel or crushed stone grit 0-32 mm and filling the pipeline with a thickness of overburden above the pipe of 30 cm. The item includes compaction manual compactor. Pay special attention to lateral compaction of material between the pipe and the wall of the trench height of 0.5 D to obtain the bigger angle seating. When filling the compound should remain visible to the implementation of the pressure test. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Backfilling with replacement material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) potentially oily rainfall pipeline - 9 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary waste water pipeline- 0,60 m3 | m3 | 9.6 | 120 | 1152 | 0 | 0 |  | 0 | 9.6 | 1152 |  |  | 0 | [24 empty] | 38.76 | 120 | 4651.2 |  | 0 | 0 |  | 9.6 | 0 |  |  |  | 38.76 | 4651.2 |  | 38.76 | 120 | 4651.2
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.6 | Backfilling space of fulfill zone of the trench above the pipeline protection zone with excavation material (max. grain size 63 mm). The item includes loading, transport, unloading, leveling and compaction of materials to the design of compression modulus in layers 30 cm thick. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Backfilling with excavation material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) potentially oily rainfall pipeline - 16,30 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary waste water pipeline - 0,60 m3 | m3 | 16.9 | 18 | 304.2 | 0 | 0 |  | 0 | 16.9 | 304.2 |  |  | 0 | [24 empty] | 155.04 | 18 | 2790.72 |  | 0 | 0 |  | 16.9 | 0 |  |  |  | 155.04 | 2790.72 |  | 155.04 | 18 | 2790.72
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.7 | Transportation of surplus material from the excavation after backfilling the space around buildings carried out on the landfill site within a distance of 500m. The item includes loading, transport and unloading and spreading material at the landfill. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Transportation of excavation material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Buildings: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Inspection shafts - 16,60m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Water inlets - 4,90 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 24 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| e) Absorption well - 15,80 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) potentially oily rainfall pipeline - 10,85 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary waste water pipeline - 0,75 m3 | m3 | 72.9 | 12 | 874.8 | 0 | 0 |  | 0 | 72.9 | 874.8 |  |  | 0 | [21 empty] | 34.11 | 12 | 409.32 | 138.84 | 12 | 1666.08 | 4.9 | 12 | 58.8 |  | 0 | 0 |  |  |  | 177.85 | 2134.2 |  | 177.85 | 12 | 2134.2
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1.8 | Supply, delivery and installation of sand grit 0-12 mm for the performance of gravel substrate below the separator with thickness of 15 cm. The item includes compaction by manual compactor. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Preparation of substrate | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Separator - 0,90 m3 | m3 | 0.9 | 160 | 144 | 0 | 0 |  | 0 | 0.9 | 144 |  |  | 0 | [21 empty] | 2.9 | 160 | 464 | 1.2 | 160 | 192 |  | 0 | 0 |  | 0.9 | 0 |  |  |  | 4.1 | 656 |  | 4.1 | 160 | 656
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.1 | Earthworks total |  |  |  | 14750.85 |  | 0 |  | 0 |  | 14750.85 |  |  | 0 | [23 empty] | 1362.02 |  |  | 15235.22 |  |  | 2318.8 |  |  | 0 |  |  |  | 0 | 18916.04 |  | 0 | 0 | 18916.04
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.2 | Concrete works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.2.1 | Supply, delivery and installation of base concrete of compressive strength C16 / 20, depending on the thickness of the building. The item includes all possibly necessary formwork, care and attestation of compressive strength. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Inspection shafts - (0,3 m3/piece) - 1,20 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Water inlets - (0,1 m3/piece) - 0,20 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Control shaft - (0,3 m3/piece) - 0,30 m3 | m3 | 1.7 | 750 | 1275 | 0 | 0 |  | 0 | 1.7 | 1275 |  |  | 0 | [21 empty] | 0.8 | 750 | 600 | 1.18 | 750 | 885 | 1.4 | 750 | 1050 |  | 0 | 0 |  |  |  | 3.38 | 2535 |  | 3.38 | 750 | 2535
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.2.2 | Supply, delivery and installation of concrete of compressive strength C25 / 30 in concrete slab and crown of inspection shafts and water inlets. The item includes all possibly necessary formwork, concrete care and attestation of compressive strength. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Inspection shafts (4 pieces): | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - (0,3m3/piece) - 1,20 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown - (0,5m3/piece) - 2,0 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Water inlets (2 pieces) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - (0,1m3/piece) - 0,20 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown - (0,15m3/piece) - 0,30 m3 | m3 | 3.7 | 1000 | 3700 | 0 | 0 |  | 0 | 3.7 | 3700 |  |  | 0 | [27 empty] | 3.7 | 1000 | 3700 |  | 0 | 0 |  |  |  | 3.7 | 3700 |  | 3.7 | 1000 | 3700
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.2 | Concrete works total |  |  |  | 4975 |  | 0 |  | 0 |  | 4975 |  |  | 0 | [23 empty] | 600 |  |  | 885 |  |  | 4750 |  |  | 0 |  |  |  | 0 | 6235 |  | 0 | 0 | 6235
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.3 | Reinforcement works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.3.1 | Supply, delivery and installation of structural reinforcement of steel B 500 B of the slab and the crown of the sanitary water collection reservoir. The strike involves cutting, shaping, transfer to the construction site, installation and connection fittings to the grounding. The item also includes approval of implemented reinforcement. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Inspection shafts (4 pieces): | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - (30kg/piece) - 120kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown - (40kg/piece) - 160kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Water inlets (2 pieces) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - (10kg/piece) - 20kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown- (15kg/piece) - 30kg | kg | 330 | 8 | 2640 | 0 | 0 |  | 0 | 330 | 2640 |  |  | 0 | [27 empty] | 330 | 8 | 2640 |  | 0 | 0 |  |  |  | 330 | 2640 |  | 330 | 8 | 2640
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.3 | Reinforcement works total |  |  |  | 2640 |  | 0 |  | 0 |  | 2640 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 2640 |  |  | 0 |  |  |  | 0 | 2640 |  | 0 | 0 | 2640
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4 | Installation works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.1 | Supply, delivery and installation of corrugated HDPE and PVC sewer pipes for drainage potentially oily storm and sanitary wastewater. It includes all required work and materials for their installation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) PEHD OD/ID 200/171 mm, SN 8 - 30,20 m' | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) PVC OD/ID 160/152 mm, SN 4 - 2,30 m' | m' | 32.5 | 75 | 2437.5 | 0 | 0 |  | 0 | 32.5 | 2437.5 |  |  | 0 | [24 empty] | 100.7 | 75 | 7552.5 |  | 0 | 0 |  | 32.5 | 0 |  |  |  | 100.7 | 7552.5 |  | 100.7 | 75 | 7552.5
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.2 | Supply, delivery and installation of corrugated HDPE sewer pipes OD / ID 1000/851 mm, SN 8, for the performance of the body of inspection shafts. The item includes the preparation of shafts with all the elements (plates bottom, pipe connections, channel ...) to full readiness, including the performance of climbers from PE sheet thickness min 2 cm, width 45 cm back protection and performance. It includes all needed works and materials for installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Potentially oily rainfall drainage system | [12 empty] | 0 | [25 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
| a) Inspection shafts- 4 pieces | pcs | 4 | 5000 | 20000 | 0 | 0 |  | 0 | 4 | 20000 |  |  | 0 | [24 empty] | 3 | 5000 | 15000 |  | 0 | 0 |  | 4 | 0 |  |  |  | 3 | 15000 |  | 3 | 5000 | 15000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.3 | Supply, delivery and installation of corrugated HDPE sewer pipes OD / ID 1000/851 mm, SN 8, for the performance of absorption well, including the performance of climbers from PE sheet thickness min 2 cm, width 45 cm, back protection and performance of the perforation of the well which is located below level of inlet pipe. It includes all needed works and materials for installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Absorption well - 1 piece | pcs | 1 | 3000 | 3000 | 0 | 0 |  | 0 | 1 | 3000 |  |  | 0 | [24 empty] | 1 | 3000 | 3000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 3000 |  | 1 | 3000 | 3000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.4 | Supply, delivery and installation of caps of HDPE sheet thickness min 2 cm. It includes all needed works and materials for installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Embedded caps of inspecting shafts - 4 pieces | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Embedded caps od control shaft - 1 piece | pcs | 5 | 2000 | 10000 | 0 | 0 |  | 0 | 5 | 10000 |  |  | 0 | [24 empty] | 4 | 2000 | 8000 |  | 0 | 0 |  | 5 | 0 |  |  |  | 4 | 8000 |  | 4 | 2000 | 8000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.5 | Supply, delivery and installation of corrugated HDPE sewer pipes OD / ID 500/431 mm, SN 8, for the performance of water inlets. The item includes making the inlet with all the elements (plates bottom, pipe connections ...) to full readiness. It includes all needed works and materials for installation to full functionality. Calculation per piece of performed inlets. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Performed water inlets | pcs | 2 | 1500 | 3000 | 0 | 0 |  | 0 | 2 | 3000 |  |  | 0 | [24 empty] | 2 | 1500 | 3000 |  | 0 | 0 |  | 2 | 0 |  |  |  | 2 | 3000 |  | 2 | 1500 | 3000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.6 | Supply, delivery and installation of cast iron grids on the water inlets capacity D 400 kN according to EN-124: 2005, measuring 400 x 400 mm. It includes all needed works and materials for their installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Embedded grids | pcs | 2 | 500 | 1000 | 0 | 0 |  | 0 | 2 | 1000 |  |  | 0 | [24 empty] | 2 | 500 | 1000 |  | 0 | 0 |  | 2 | 0 |  |  |  | 2 | 1000 |  | 2 | 500 | 1000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.7 | Supply, delivery and installation of cast iron square covers, measuring 600 x 600 mm. It includes all needed work and material for their installation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary waste water collection reservoir | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Embedded covers class B 125 kN, HRN EN-124:2005 | pcs | 1 | 600 | 600 | 0 | 0 |  | 0 | 1 | 600 |  |  | 0 | [24 empty] | 1 | 600 | 600 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 600 |  | 1 | 600 | 600
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.8 | Supply, delivery and installation of a standard separator according to EN 858-1 volume of 5000 liters and a flow rate of 20 l / s. Dimensions of the separator are LxBxH -3.0 x 1.30 x 1.35 m. It includes all the accessories that are located in the separator together with 2 cast iron covers on the openings for inspection capacity B 125 kN. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| It includes all needed works and materials for the installation of the separator to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Separator | pcs | 1 | 30000 | 30000 | 0 | 0 |  | 0 | 1 | 30000 |  |  | 0 | [21 empty] | 1 | 30000 | 30000 | 1 | 30000 | 30000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 2 | 60000 |  | 2 | 30000 | 60000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.9 | Initial charging the separator with clean water to check water resistance of compounds including assembly and dismantling of temporary water supply and other necessary equipment. Before charging, the separator must be placed on the arranged surface and joints must not be overwhelmed by the excavation material. Calculation per piece of equipment tested. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Initial charging of the built-in separator | pcs | 1 | 1000 | 1000 | 0 | 0 |  | 0 | 1 | 1000 |  |  | 0 | [27 empty] | 1 | 1000 | 1000 |  | 0 | 0 |  |  |  | 1 | 1000 |  | 1 | 1000 | 1000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.10 | Testing of the entire drainage system (the rainfall drainage system and sanitary drainage) on the waterproofing of joints and flow (including inspection shafts and water inlets) with water at the appropriate pressure. Item includes assembly and disassembly of temporary supply of water and other necessary equipment. Before filling, the pipeline must be buried except compounds. A pressure test has to be carried out according to regulations. Calculation per meter of tested sewage. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Testin of the drainage system | m' | 32.5 | 100 | 3250 | 0 | 0 |  | 0 | 32.5 | 3250 |  |  | 0 | [27 empty] | 158 | 100 | 15800 |  | 0 | 0 |  |  |  | 158 | 15800 |  | 158 | 100 | 15800
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.11 | Zero cleaning of newly drainage system (the rainfall drainage system and sanitary drainage) after the completion of all previous works. It includes all needed works and materials for the execution. Calculation per meter of cleaned sewage. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Zero cleaning of drainage system | m' | 32.5 | 50 | 1625 | 0 | 0 |  | 0 | 32.5 | 1625 |  |  | 0 | [27 empty] | 158 | 50 | 7900 |  | 0 | 0 |  |  |  | 158 | 7900 |  | 158 | 50 | 7900
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.12 | Linear drainage channel | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Linear drainage channel with capacity C400 according to EN EN 1433. Because of their specific V-section channel is characterized by a faster rate of runoff and better self-cleaning effect. The channel is made of polymer concrete, a building height of 480 mm. Fog channel width is 400 mm, width 450 mm construction, building length of 1000 mm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The edges of the channel are reinforced bracket of galvanized steel with thickness of 4 mm, which serves as a seat for taking the cover grid. The channel is carried out by laying the concrete base brand C25 / 30 thickness of 20 cm, side channel concrete pledge. The upper edge of the grid is performed at the level of 2-5 mm below the level of finished finishing the surrounding area. All the accessories for mounting to full functionality. Product as ACO Multiline V400 or equal: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.12.1 | Product as Multiline V400 or equivalent- construction height 480 mm. Channel width is 400 mm, width 450 mm construction, building length of 1000 mm | m' | 17.8 | 1600 | 28480 | 0 | 0 |  | 0 | 17.8 | 28480 |  |  | 0 | [24 empty] | 16.6 | 1600 | 26560 |  | 0 | 0 |  | 17.8 | 0 |  |  |  | 16.6 | 26560 |  | 16.6 | 1600 | 26560
C.1.4.12.2 | Product as Multiline V400 or equivalent, cover grating ACO Multiline V400 load C400 according to EN EN 1433 (medium-heavy traffic) from cast iron. | m' | 17.8 | 2000 | 35600 | 0 | 0 |  | 0 | 17.8 | 35600 |  |  | 0 | [24 empty] | 16.6 | 2000 | 33200 |  | 0 | 0 |  | 17.8 | 0 |  |  |  | 16.6 | 33200 |  | 16.6 | 2000 | 33200
C.1.4.12.3 | Collector for the product as ACO Multiline V400 or equivalent from polymer concrete, with Drainlock® strengthening the grid without screws, with the precipitation vessel made of PVC. | pcs | 3 | 5000 | 15000 | 0 | 0 |  | 0 | 3 | 15000 |  |  | 0 | [24 empty] | 3 | 5000 | 15000 |  | 0 | 0 |  | 3 | 0 |  |  |  | 3 | 15000 |  | 3 | 5000 | 15000
C.1.4.12.4 | Making the concrete foundation of quality C 20/25 according to the manufacturer of equipment, cross section and dimensions recommended by the manufacturer of equipment depending on the installation site, approximately | m3 | 1 | 1000 | 1000 | 0 | 0 |  | 0 | 1 | 1000 |  |  | 0 | [24 empty] | 5.44 | 1000 | 5440 |  | 0 | 0 |  | 1 | 0 |  |  |  | 5.44 | 5440 |  | 5.44 | 1000 | 5440
| Detailed elaboration according to the manufacturer's instructions | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4.12 | Linear drainage channel total |  |  |  | 80080 |  | 0 |  | 0 |  | 80080 |  |  | 0 | [26 empty] | 80200 |  |  | 0 |  |  | 0 |  |  |  | 0 | 80200 |  | 0 | 0 | 80200
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.1.4 | Installation works total |  |  |  | 155992.5 |  | 0 |  | 0 |  | 155992.5 |  |  | 0 | [23 empty] | 30000 |  |  | 148352.5 |  |  | 24700 |  |  | 0 |  |  |  | 0 | 203052.5 |  | 0 | 0 | 203052.5
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C.1 | Drainage TOTAL |  |  |  | 178358.35 |  | 0 |  | 0 |  | 178358.35 |  |  | 0 | [23 empty] | 31962.02 |  |  | 164472.72 |  |  | 34408.8 |  |  | 0 |  |  |  | 0 | 230843.54 |  | 0 | 0 | 230843.54
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2 | Water supply system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1 | Earthworks | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.1 | Machine excavation of material in category C to a depth h [m] depending on the structure with vertical nicking. The works carried out depend on the equipment and technology of the contractor for all depths. The width of the trench is dependent on the normal profile and the size of the pipe. The excavated soil is rejected aside within the work zone, and if necessary in tight spaces is transported, deposited and again transported to the place of installation when backfilling . Excavation method determined by the Contractor, and the calculations are to be carried out according to the amounts of the ideal profile of the main design so that the excess excavation shall be calculated in the price and will not be subsequently recognized. The item includes all the necessary papers and equipment for shoring and securing the trench from collapsing, according to the technology contractor, in accordance with the prescribed conditions of safety at work, including excavation required for the installation of protective plates (which is not particularly specified). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Materials excavation (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Objects | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary water collection reservoir - 29,60 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) sanitary network pipeline, trench depth 1,0 m - 2,00m3 | m3 | 31.6 | 45 | 1422 | 0 | 0 |  | 0 | 31.6 | 1422 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 45 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.2 | Supply, delivery and installation of sand / gravel or crushed stone grit 0-32 mm for making substrate under sanitary water collection reservoir, at a thickness of 10 cm. The item includes compaction by manual compactor. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Substrate preparation (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary water collection reservoir | m3 | 3.7 | 120 | 444 | 0 | 0 |  | 0 | 3.7 | 444 |  |  | 0 | [21 empty] | 0.67 | 120 | 80.4 |  | 0 | 0 |  | 3.7 | 0 |  | 0 | 0 |  |  |  | 0.67 | 80.4 |  | 0.67 | 120 | 80.4
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.3 | Backfilling the area around the buildings carried out by selected material from excavation grit 0-32 mm to designed certain angle. The item includes leveling and compacting the material in layers of 30 cm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Filling preparation (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary water collection reservoir | m3 | 14.8 | 18 | 266.4 | 0 | 0 |  | 0 | 14.8 | 266.4 |  |  | 0 | [21 empty] | 29.86 | 18 | 537.48 |  | 0 | 0 |  | 14.8 | 0 |  | 0 | 0 |  |  |  | 29.86 | 537.48 |  | 29.86 | 18 | 537.48
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.4 | Supply and delivery of sand grit 0-12 mm and preparation of sand formation level with thickness of 10 cm for laying pipelines. The item includes compaction by manual compactor. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Preparation of san formation level(calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary network pipeline | m3 | 0.2 | 160 | 32 | 0 | 0 |  | 0 | 0.2 | 32 |  |  | 0 | [21 empty] | 2.86 | 160 | 457.6 | 1.1 | 160 | 176 |  | 0 | 0 |  | 0.2 | 0 |  |  |  | 3.96 | 633.6 |  | 3.96 | 160 | 633.6
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.5 | Supply and delivery of sand / gravel or crushed stone grit 0-32 mm and filling the pipeline with an overlayer above the pipe of 30 cm. The item includes compaction by manual compactor. Pay special attention to lateral compaction of material between the pipe and the wall of the trench height of 0.5 D to obtain the bigger angle seating. When filling the compound should remain visible to the implementation of the pressure test. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Backfilling with replacement material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary network pipeline | m3 | 0.7 | 120 | 84 | 0 | 0 |  | 0 | 0.7 | 84 |  |  | 0 | [24 empty] | 3.3 | 120 | 396 |  | 0 | 0 |  | 0.7 | 0 |  |  |  | 3.3 | 396 |  | 3.3 | 120 | 396
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.6 | Backfilling space of fulfill zones of the trench above the pipeline protection zones pipeline with excavation material (max. grain size 63 mm) to designed level. The item includes loading, transport, unloading, leveling and compaction of materials to the designed compression modulus in layers 30 cm thick | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Backfilling with excavation material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| sanitary network pipeline | m3 | 1.1 | 18 | 19.8 | 0 | 0 |  | 0 | 1.1 | 19.8 |  |  | 0 | [24 empty] | 2.2 | 18 | 39.6 |  | 0 | 0 |  | 1.1 | 0 |  |  |  | 2.2 | 39.6 |  | 2.2 | 18 | 39.6
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1.7 | Transportation of surplus material from the excavation after backfilling the space around buildings carried out on the landfill site within a distance of 500m. The item includes loading, transport and unloading and spreading material at the landfill. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Transportation of excavation material (calculation in grown-together state) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Objects | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary water collection reservoir - 11,10 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network pipeline - 0,90 m3 | m3 | 12 | 12 | 144 | 0 | 0 |  | 0 | 12 | 144 |  |  | 0 | [21 empty] | 38 | 12 | 456 |  | 0 | 0 |  | 12 | 0 |  | 0 | 0 |  |  |  | 38 | 456 |  | 38 | 12 | 456
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.1 | Earthworks total: |  |  |  | 2412.2 |  | 0 |  | 0 |  | 2412.2 |  |  | 0 | [23 empty] | 1531.48 |  |  | 611.6 |  |  | 0 |  |  | 0 |  |  |  | 0 | 2143.08 |  | 0 | 0 | 2143.08
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.2 | Concrete works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.2.1 | Supply, delivery and installation of concrete of compressive strength C25 / 30 in concrete slab and crown of sanitary water collection reservoir. The item includes all possibly necessary formwork, concrete care and attestation of compressive strength. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - 0,20 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown- 0,10 m3 | m3 | 0.3 | 1000 | 300 | 0 | 0 |  | 0 | 0.3 | 300 |  |  | 0 | [21 empty] | 0.67 | 1000 | 670 |  | 0 | 0 |  | 0.3 | 0 |  | 0 | 0 |  |  |  | 0.67 | 670 |  | 0.67 | 1000 | 670
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.2 | Concrete works total: |  |  |  | 300 |  | 0 |  | 0 |  | 300 |  |  | 0 | [23 empty] | 670 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 670 |  | 0 | 0 | 670
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.3 | Reinforcement works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.3.1 | Supply, delivery and installation of structural reinforcement of steel B 500 B of the slab and the crown of the sanitary water collection reservoir. The strike involves cutting, shaping, transfer to the construction site, installation and connection fittings to the grounding. The item also includes approval of implemented reinforcement. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) slab - (15kg/piece) - 15kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| b) crown - (20kg/piece) - 20kg | kg | 35 | 7.5 | 262.5 | 0 | 0 |  | 0 | 35 | 262.5 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 7.5 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.3 | Reinforcement works total: |  |  |  | 262.5 |  | 0 |  | 0 |  | 262.5 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4 | Installation works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.1 | Supply, delivery and installation of smooth HDPE pressure pipes for the sanitary network. It includes all needed works and materials for their installation. Calculation per m 'of embedded pipes. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) PEHD OD 32 mm, SDR 17, PE 100, PN 10 | m' | 4 | 50 | 200 | 0 | 0 |  | 0 | 4 | 200 |  |  | 0 | [24 empty] | 11 | 50 | 550 |  | 0 | 0 |  | 4 | 0 |  |  |  | 11 | 550 |  | 11 | 50 | 550
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.2 | Supply, delivery and installation of HDPE pressure fittings for the performance of the sanitary network. It includes all needed work and material for their installation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitary network | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) electrical knee OD32/90°, PE100, SDR 11 | pcs | 4 | 280 | 1120 | 0 | 0 |  | 0 | 4 | 1120 |  |  | 0 | [24 empty] | 8 | 280 | 2240 |  | 0 | 0 |  | 4 | 0 |  |  |  | 8 | 2240 |  | 8 | 280 | 2240
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.3 | Supply, delivery and installation of standard containers (reservoir) for water systems made of hard polyethylene according to DIN EN 1898, the volume of 6000 l. The dimensions of the reservoir are LxBxH - 2,88x180x2,05 m. It includes all needed works and materials for the installation and connection to the pipeline. Calculation per unit of implanted reservoir. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Reservoir | pcs | 1 | 13500 | 13500 | 0 | 0 |  | 0 | 1 | 13500 |  |  | 0 | [21 empty] | 1 | 13500 | 13500 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 1 | 13500 |  | 1 | 13500 | 13500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.4 | Supply, delivery and installation of self-priming pump that sucks up below the pump. The pump consists of pump, motor, pressure tank, pressure sensor and flow regulator and check valve. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The controller provides automatic start of the pump during the consumption of water and automatically stops when the consumption ceases. In addition, the controller protects the pump in case of failure / malfunction. The pump must meet the flow of 3 m3 / h and lifting height 23 m. It includes all needed works and materials for the installation and connection of the sanitary water collection reservoir, up to full readiness / functionality. Calculation per piece of incorporated self-priming pump. " | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Integrated pump | pcs | 1 | 4200 | 4200 | 0 | 0 |  | 0 | 1 | 4200 |  |  | 0 | [21 empty] | 1 | 4200 | 4200 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 1 | 4200 |  | 1 | 4200 | 4200
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.5 | Supply, delivery and installation of cast iron canal cover of circular shape with a diameter of 600 mm. It includes all needed works and materials for the installation of the sanitary water collection reservoir. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Cover class B 125 kN, according to HRN EN-124:2005 | pcs | 1 | 850 | 850 | 0 | 0 |  | 0 | 1 | 850 |  |  | 0 | [24 empty] | 1 | 850 | 850 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 850 |  | 1 | 850 | 850
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.6 | Testing of the entire water system (sanitary network) on waterproofing of joints and flow with water at the appropriate pressure. Item includes assembly and disassembly of temporary supply of water and other necessary equipment. Before filling, the pipeline must be buried except for compounds. A pressure test has to be carried out according to regulations. Calculation per meter of tested the water supply system. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Testing of the water supply system | m' | 4 | 100 | 400 | 0 | 0 |  | 0 | 4 | 400 |  |  | 0 | [27 empty] | 11 | 100 | 1100 |  | 0 | 0 |  |  |  | 11 | 1100 |  | 11 | 100 | 1100
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4.7 | Zero cleaning the internal water supply system (sanitary network) after completing all the previous works. It includes all needed work and material for the execution of cleaning. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Zero cleaning of water supply system | m' | 4 | 50 | 200 | 0 | 0 |  | 0 | 4 | 200 |  |  | 0 | [27 empty] | 11 | 50 | 550 |  | 0 | 0 |  |  |  | 11 | 550 |  | 11 | 50 | 550
[14 empty] | 0 | [28 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
C.2.4.8 | Disinfection of sanitary network pipeline. It includes all needed works and materials to perform. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Disinfection of the pipeline | m' | 4 | 500 | 2000 | 0 | 0 |  | 0 | 4 | 2000 |  |  | 0 | [27 empty] | 11 | 500 | 5500 |  | 0 | 0 |  |  |  | 11 | 5500 |  | 11 | 500 | 5500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
C.2.4 | Installation works total: |  |  |  | 22470 |  | 0 |  | 0 |  | 22470 |  |  | 0 | [23 empty] | 17700 |  |  | 3640 |  |  | 7150 |  |  | 0 |  |  |  | 0 | 28490 |  | 0 | 0 | 28490
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C.2 | Water supply system TOTAL |  |  |  | 25444.7 |  | 0 |  | 0 |  | 25444.7 |  |  | 0 | [23 empty] | 19901.48 |  |  | 4251.6 |  |  | 7150 |  |  | 0 |  |  |  | 0 | 31303.08 |  | 0 | 0 | 31303.08
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C | CIVIL WORKS - WATER SUPPLY AND DRAINAGE | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C.1 | DRAINAGE |  |  |  | 178358.35 |  | 0 |  | 0 |  | 178358.35 |  |  | 0 | [23 empty] | 31962.02 |  |  | 164472.72 |  |  | 34408.8 |  |  | 0 |  |  |  | 0 | 230843.54 |  | 0 | 0 | 230843.54
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C.2 | WATER SUPPLY SYSTEM |  |  |  | 25444.7 |  | 0 |  | 0 |  | 25444.7 |  |  | 0 | [23 empty] | 19901.48 |  |  | 4251.6 |  |  | 7150 |  |  | 0 |  |  |  | 0 | 31303.08 |  | 0 | 0 | 31303.08
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
C | CIVIL WORKS - WATER SUPPLY AND DRAINAGE SUMMARY |  |  |  | 203803.05 |  | 0 |  | 0 |  | 203803.05 |  |  | 0 | [23 empty] | 51863.5 |  |  | 168724.32 |  |  | 41558.8 |  |  | 0 |  |  |  | 0 | 262146.62 |  | 0 | 0 | 262146.62
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D | CIVIL WORKS - CONSTRUCTION | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.1 | Earth works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.1.1 | Excavation of soil with dumping in vicinity of the construction pit. This item also includes compaction of base soil to the designed compaction module. Calculation is conducted per m3 of soil in its natural state. | m3 | 170 | 90 | 15300 | 0 | 0 |  | 0 | 170 | 15300 |  |  | 0 | [21 empty] | 444.11 | 90 | 39969.9 | 324.27 | 90 | 29184.3 |  | 0 | 0 |  | 170 | 0 |  |  |  | 768.38 | 69154.2 |  | 768.38 | 90 | 69154.2
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.1.2 | Backfilling of construction pit (after construction of foundations) with the material from the excavation. Backfilling of the construction pit is to be realized in 20 cm thick layers with compaction of each layer separately. Calculation is conducted per m3 of soil in its natural state. | m3 | 90 | 18 | 1620 | 0 | 0 |  | 0 | 90 | 1620 |  |  | 0 | [21 empty] | 47 | 18 | 846 | [12 empty] | 47 | 846 |  | 47 | 18 | 846
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.1.3 | Transportation of the excess material from the excavation after backfilling to the dump site up to 5 km. This item includes loading, transportation and unloading, as well as levelling of the material, at the dump site. Calculation is conducted per m3 of soil in its natural state. | m3 | 80 | 12 | 960 | 0 | 0 |  | 0 | 80 | 960 |  |  | 0 | [27 empty] | 721.38 | 12 | 8656.56 |  | 0 | 0 |  |  |  | 721.38 | 8656.56 |  | 721.38 | 12 | 8656.56
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.1 | Earth works TOTAL |  |  |  | 17880 |  | 0 |  | 0 |  | 17880 |  |  | 0 | [23 empty] | 40815.9 |  |  | 29184.3 |  |  | 8656.56 |  |  | 0 |  |  |  | 0 | 78656.76 |  | 0 | 0 | 78656.76
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.2 | Concrete works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.2.1 | Concreting of the lean concrete in C16/20 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete. Calculation is conducted per m3 of placed concrete. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Building for personnel foundation slab | m3 | 2 | 750 | 1500 | 0 | 0 |  | 0 | 2 | 1500 |  |  | 0 | [21 empty] | 2.06 | 750 | 1545 |  | 0 | 0 |  | 2 | 0 |  | 0 | 0 |  |  |  | 2.06 | 1545 |  | 2.06 | 750 | 1545
| b) Sanitary waste water collection reservoir | m3 | 1.5 | 750 | 1125 | 0 | 0 |  | 0 | 1.5 | 1125 |  |  | 0 | [21 empty] | 1.5 | 750 | 1125 |  | 0 | 0 |  | 1.5 | 0 |  | 0 | 0 |  |  |  | 1.5 | 1125 |  | 1.5 | 750 | 1125
| c) Weigh | m3 | 1 | 750 | 750 | 0 | 0 |  | 0 | 1 | 750 |  |  | 0 | [21 empty] | 2.96 | 750 | 2220 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 2.96 | 2220 |  | 2.96 | 750 | 2220
| d) Garage for compactor | m3 | 4.5 | 750 | 3375 | 0 | 0 |  | 0 | 4.5 | 3375 |  |  | 0 | [21 empty] | 10.6 | 750 | 7950 |  | 0 | 0 |  | 4.5 | 0 |  | 0 | 0 |  |  |  | 10.6 | 7950 |  | 10.6 | 750 | 7950
| e) Wheel washing facility | m3 | 5.5 | 750 | 4125 | 0 | 0 |  | 0 | 5.5 | 4125 |  |  | 0 | [21 empty] | 0 | 750 | 0 | [12 empty] | 0 | 0 |  | 0 | 750 | 0
| f) Stable electric diesel engine foundation slab | m3 | 0.5 | 750 | 375 | 0 | 0 |  | 0 | 0.5 | 375 |  |  | 0 | [21 empty] | 0.76 | 750 | 570 |  | 0 | 0 |  | 0.5 | 0 |  | 0 | 0 |  |  |  | 0.76 | 570 |  | 0.76 | 750 | 570
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.2.2 | Concreting in C30/37 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete. This item also includes the appropriate formwork, and all the materials and works related to that. Calculation is conducted per m3 of placed concrete. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Building for personnel foundation slab | m3 | 3.5 | 1350 | 4725 | 0 | 0 |  | 0 | 3.5 | 4725 |  |  | 0 | [21 empty] | 3.2 | 1350 | 4320 |  | 0 | 0 |  | 3.5 | 0 |  | 0 | 0 |  |  |  | 3.2 | 4320 |  | 3.2 | 1350 | 4320
| b) Sanitary waste water collection reservoir | m3 | 11 | 1350 | 14850 | 0 | 0 |  | 0 | 11 | 14850 |  |  | 0 | [21 empty] | 11.24 | 1350 | 15174 |  | 0 | 0 |  | 11 | 0 |  | 0 | 0 |  |  |  | 11.24 | 15174 |  | 11.24 | 1350 | 15174
| c) Weigh | m3 | 12 | 1350 | 16200 | 0 | 0 |  | 0 | 12 | 16200 |  |  | 0 | [21 empty] | 21.05 | 1350 | 28417.5 |  | 0 | 0 |  | 12 | 0 |  | 0 | 0 |  |  |  | 21.05 | 28417.5 |  | 21.05 | 1350 | 28417.5
| d) Garage for compactor | m3 | 65.6 | 1350 | 88560 | 0 | 0 |  | 0 | 65.6 | 88560 |  |  | 0 | [21 empty] | 40.17 | 1350 | 54229.5 |  | 0 | 0 |  | 65.6 | 0 |  | 0 | 0 |  |  |  | 40.17 | 54229.5 |  | 40.17 | 1350 | 54229.5
| f) Stable electric diesel engine foundation slab | m3 | 1.5 | 1350 | 2025 | 0 | 0 |  | 0 | 1.5 | 2025 |  |  | 0 | [21 empty] | 0 | 1350 | 0 | 1.2 | 1350 | 1620 |  | 0 | 0 |  | 1.5 | 0 |  |  |  | 1.2 | 1620 |  | 1.2 | 1350 | 1620
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.2.3 | Concreting in C20/25 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete. This item also includes the appropriate formwork, and all the materials and works related to that. Calculation is conducted per m3 of placed concrete. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Weigh | m3 | 2 | 1300 | 2600 | 0 | 0 |  | 0 | 2 | 2600 |  |  | 0 | [21 empty] | 2.14 | 1300 | 2782 |  | 0 | 0 |  | 2 | 0 |  | 0 | 0 |  |  |  | 2.14 | 2782 |  | 2.14 | 1300 | 2782
| b) Garage for compactor | m3 | 8.5 | 1300 | 11050 | 0 | 0 |  | 0 | 8.5 | 11050 |  |  | 0 | [21 empty] | 0 | 1300 | 0 | 8.01 | 1300 | 10413 |  | 0 | 0 |  | 8.5 | 0 |  |  |  | 8.01 | 10413 |  | 8.01 | 1300 | 10413
| c) Wheel washing facility | m3 | 35.5 | 1300 | 46150 | 0 | 0 |  | 0 | 35.5 | 46150 |  |  | 0 | [21 empty] | 0 | 1300 | 0 |  | 0 | 0 |  | 35.5 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 1300 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.2.4 | Concreting foundation blocks for the fence of 0.40 x 0.40 x 0.45 m dimensions, with concrete of compression strength C20/25. The foundations are at the axial distance of 200.0 cm. The price includes the supply and transport of concrete and mechanical placement and curing of fresh concrete, and the formwork. | pcs | 100 | 95 | 9500 | 0 | 0 |  | 0 | 100 | 9500 |  |  | 0 | [24 empty] | 151 | 95 | 14345 |  | 0 | 0 |  | 100 | 0 |  |  |  | 151 | 14345 |  | 151 | 95 | 14345
D.2 | Concrete works TOTAL |  |  |  | 206910 |  | 0 |  | 0 |  | 206910 |  |  | 0 | [23 empty] | 118333 |  |  | 26378 |  |  | 0 |  |  | 0 |  |  |  | 0 | 144711 |  | 0 | 0 | 144711
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.3 | Reinforcement works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.3.1 | Supply, cutting, bending, transportation and placing of reinforcement. This item includes all the work and material. Calculation is conducted per kg of placed reinforcement. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Building for personnel foundation slab | kg | 350 | 7.5 | 2625 | 0 | 0 |  | 0 | 350 | 2625 |  |  | 0 | [21 empty] | 455.78 | 7.5 | 3418.35 |  | 0 | 0 |  | 350 | 0 |  | 0 | 0 |  |  |  | 455.78 | 3418.35 |  | 455.78 | 7.5 | 3418.35
| b) Sanitary waste water collection reservoir | kg | 1935 | 7.5 | 14512.5 | 0 | 0 |  | 0 | 1935 | 14512.5 |  |  | 0 | [21 empty] | 1216.04 | 7.5 | 9120.3 |  | 0 | 0 |  | 1935 | 0 |  | 0 | 0 |  |  |  | 1216.04 | 9120.3 |  | 1216.04 | 7.5 | 9120.3
| c) Weigh | kg | 1100 | 7.5 | 8250 | 0 | 0 |  | 0 | 1100 | 8250 |  |  | 0 | [21 empty] | 1081.2 | 7.5 | 8109 |  | 0 | 0 |  | 1100 | 0 |  | 0 | 0 |  |  |  | 1081.2 | 8109 |  | 1081.2 | 7.5 | 8109
| d) Garage for compactor | kg | 7360 | 7.5 | 55200 | 0 | 0 |  | 0 | 7360 | 55200 |  |  | 0 | [21 empty] | 4409.49 | 7.5 | 33071.175 |  | 0 | 0 |  | 7360 | 0 |  | 0 | 0 |  |  |  | 4409.49 | 33071.175 |  | 4409.49 | 7.5 | 33071.175
| e) Wheel washing facility | kg | 3520 | 7.5 | 26400 | 0 | 0 |  | 0 | 3520 | 26400 |  |  | 0 | [21 empty] | 0 | 7.5 | 0 |  | 0 | 0 |  | 3520 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 7.5 | 0
| f) Stable electric diesel engine foundation slab | kg | 150 | 7.5 | 1125 | 0 | 0 |  | 0 | 150 | 1125 |  |  | 0 | [21 empty] | 164.58 | 7.5 | 1234.35 |  | 0 | 0 |  | 150 | 0 |  | 0 | 0 |  |  |  | 164.58 | 1234.35 |  | 164.58 | 7.5 | 1234.35
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.3 | Reinforcement works TOTAL |  |  |  | 108112.5 |  | 0 |  | 0 |  | 108112.5 |  |  | 0 | [23 empty] | 54953.175 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 54953.175 |  | 0 | 0 | 54953.175
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.4 | Metal works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.4.1 | Fabrication, transportation and installation of garage for compactor according to the executable documentation, technical description and specification of materials. The price of this item includes: supply and delivery of steel (hot cast profiles, seamless round tubes, sheets, hot tubing square and rectangular hollow profiles, screws, making workshop documentation and production of steel tower structure, supply of electrodes, welding, blackmail includes work and all necessary material with loading, unloading, transport and transfer of materials and construction, as well as the necessary machinery, and the costs of testing materials. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Provides for the protection of AK steel construction hot-dip galvanized, with previous blasting and surface preparation. According to standard EN 12944-2 - protection category C2. Complete the steel construction is cleaned to the level Sa 2 ½ (blasting, chemical equipments, brushes). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Is calculated kg steel, actually built into the design, quality control, size, and position exactly according to the project. Corrosion protection of the supporting steel structure. Complete the steel construction is cleaned (sand blasting, chemical equipment, brushes). need to be cleaned before construction hot-dip galvanizing process. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| During installing, receiving ropes must be of non-metals (tape), which do not damage the corrosion protection layers of the structure. Upon completion of construction, installation, repair damaged parts of the coating. The surfaces of the steel structure that contact with concrete, not to be painted. | kg | 1905 | 27 | 51435 | 0 | 0 |  | 0 | 1905 | 51435 |  |  | 0 | [24 empty] | 1905 | 27 | 51435 | 1010 | 27 | 27270 |  | 0 | 0 |  |  |  | 2915 | 78705 |  | 2915 | 27 | 78705
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.4.2 | Supply, delivery, assembly and anti-corrosive protection for steel structure wheel washing facility fence. Calculation is conducted per m of mounted steel structure members. | m | 11.7 | 85 | 994.5 | 0 | 0 |  | 0 | 11.7 | 994.5 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 85 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.4 | Metal works TOTAL |  |  |  | 52429.5 |  | 0 |  | 0 |  | 52429.5 |  |  | 0 | [23 empty] | 0 |  |  | 51435 |  |  | 27270 |  |  | 0 |  |  |  | 0 | 78705 |  | 0 | 0 | 78705
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.5 | Assembly works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.5.1 | Roof metalware. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Procurement and installation of roof metalware from steel galvanized plastic coated sheet metal. Including all necessary materials for attaching to the concrete building structure (hooks, clamps), sealed element joints. Construction and assembly according to a detailed blueprint and agreement with the designer. Color according to design. The item includes all materials and labor. Calculated by m1 of assembled, finalized metalware. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The gutter is made from galvanized steel 0.55mm thick, rectangular cross section 15 x 15 cm with a slope on both sides, attached by galvanized steel hooks 30/3 mm to the roof purlins in the middle of the roof spaced about 75 cm apart. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Vertical drainage pipes made from galvanized steel 0.55 mm thick, square cross section 10 x10 cm. Drainage pipes are fixed to the pillars by galvanized collars made from flat steel 30/3 mm. Collars are installed about every 1.00 m. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Color RAL 7004, gray | m | 9.7 | 185 | 1794.5 | 0 | 0 |  | 0 | 9.7 | 1794.5 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 185 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.5.2 | Covering the roof with sheet metal | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Procurement and assembly of roof covering steel sheets d=0,55. Grading of the steel sheet S250, galvanized 275 g/m2 according to EN10142 and EN10147-2000 norms, load bearing 1.50 kN/m2, final coating of polyester paint RAL 7004 (gray) 25 microns thick. The item includes the necessary substructure for fastening the covering steel sheets. The substructure is secured to the reinforced concrete sloped slab or to the steel structure (according to the design) according to the details of the manufacturer. The item includes all necessary covering and flashing profiles on surface aberrations, rustproof bolts, washers and seals. Insulating layers under the cover are calculated separately. Creation of the workshop documentation and execution details have to be submitted by the constructor to the designer for approval. The item included all necessary materials and labor. Calculated by m2 of installed cover. | m2 | 69 | 255 | 17595 | 0 | 0 |  | 0 | 69 | 17595 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 255 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
D.5 | Assembly works TOTAL |  |  |  | 19389.5 |  | 0 |  | 0 |  | 19389.5 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D | CIVIL WORKS- CONSTRUCTION | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D.1 | EARTH WORKS |  |  |  | 17880 |  | 0 |  | 0 |  | 17880 |  |  | 0 | [23 empty] | 40815.9 |  |  | 29184.3 |  |  | 8656.56 |  |  | 0 |  |  |  | 0 | 78656.76 |  | 0 | 0 | 78656.76
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D.2 | CONCRETE WORKS |  |  |  | 206910 |  | 0 |  | 0 |  | 206910 |  |  | 0 | [23 empty] | 118333 |  |  | 26378 |  |  | 0 |  |  | 0 |  |  |  | 0 | 144711 |  | 0 | 0 | 144711
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D.3 | REINFORCEMENT WORKS |  |  |  | 108112.5 |  | 0 |  | 0 |  | 108112.5 |  |  | 0 | [23 empty] | 54953.175 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 54953.175 |  | 0 | 0 | 54953.175
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D.4 | METAL WORKS |  |  |  | 52429.5 |  | 0 |  | 0 |  | 52429.5 |  |  | 0 | [23 empty] | 0 |  |  | 51435 |  |  | 27270 |  |  | 0 |  |  |  | 0 | 78705 |  | 0 | 0 | 78705
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D.5 | ASSEMBLY WORKS |  |  |  | 19389.5 |  | 0 |  | 0 |  | 19389.5 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
D | CIVIL WORKS- CONSTRUCTION SUMMARY |  |  |  | 404721.5 |  | 0 |  | 0 |  | 404721.5 |  |  | 0 | [23 empty] | 214102.075 |  |  | 106997.3 |  |  | 35926.56 |  |  | 0 |  |  |  | 0 | 357025.935 |  | 0 | 0 | 357025.935
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E | CIVIL WORKS - LANDFILL (STAGE II, PHASE 1) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1 | Excavation of landfill basins for landfill cells I, II, III and IV and construction of the clean stormwater drainage system and macadam roads. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1 | Preparation works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1.1 | Preparation work includes the preparation for undisturbed work at the construction site (disposal site), namely the elaboration of all activities which are necessary for the construction to be built in accordance with valid laws and regulations and provisions in the contracted period and respecting contracted economic-financial conditions. Preparation work starts with the elaboration of the Organization design by the Client. After the elaboration of the Construction organization design it is delivered to the Client for acceptance and approval. The Calculation according to the set of elaborated design. | set | 1 | 27000 | 27000 | 0 | 0 |  | 0 | 1 | 27000 | 27000 | 1 | 27000 | [36 empty] | 1 | 27000 |  | 1 | 27000 | 27000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1.2 | Realization of temporary construction roads and parking lots, including the road toward the dump in the area of the disposal site, placing construction facilities (barracks, containers, and similar), realization of all necessary installations for the work, and supply and delivery of all necessary equipment, everything according to the elaborated Construction organization design accepted by the Client. The item includes the maintenance of everything specified during construction and removal after the completion of works. Calculation per set. | set | 1 | 10000 | 10000 | 0 | 0 |  | 0 | 1 | 10000 | 10000 | 1 | 10000 | [36 empty] | 1 | 10000 |  | 1 | 10000 | 10000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1.3 | Cutting of bushes, brushwood and trees of all dimensions and their removal from the disposal site and protection zone (in the area where excavation and backfilling are performed). The work includes cutting and removal of brushwood, bushes and trees with roots from the entire surface of the disposal including the boundary channel and fire access road, and disposal in the area of the disposal in the place determined according to the Construction organization design. Work is measured and calculated in square meters (m2) of plan area, disregarding the density and coverage of the vegetation certified by the supervising engineer. | m2 | 9325 | 1.2 | 11190 | 0 | 0 |  | 0 | 9325 | 11190 | 9315.81 | 1.2 | 11178.972 | [36 empty] | 9315.81 | 11178.972 |  | 9315.81 | 1.2 | 11178.972
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1.4 | Surveying works include the compilation of the elaborate for the stakeout of the building, stakeout of the structure on terrain, all measurements regarding the transfer of data from the design onto the terrain and vice versa, preservation of stakeout markings on terrain during the entire period from the beginning of works until the handover of all works to the client and elaboration of the as-built survey. Calculation per m2 of plan area. | m2 | 46625 | 0.7 | 32637.5 | 0 | 0 |  | 0 | 46625 | 32637.5 | 18000 | 0.7 | 12600 | 8000 | 0.7 | 5600 | 5000 | 0.7 | 3500 |  |  |  | 7000 | 0.7 | 4900 | 4000 | 0.7 | 2800 | [6 empty] | 4625 | 0.7 | 3237.5 |  | 0 | 0 |  | 46625 | 0 |  | 0.7 | 0 |  |  |  | 46625 | 32637.5 |  | 46625 | 0.7 | 32637.5
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.1 | Preparation works TOTAL |  |  |  | 80827.5 |  | 0 |  | 0 |  | 80827.5 | [26 empty] | 3237.5 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 80816.472 |  | 0 | 0 | 80816.472
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2 | Earthworks | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.1 | Mechanical excavation of class "B" material, to the elevations specified in the design. The item includes excavation, transport and disposal at the place where backfilling shall be performed. The excavation includes also the fragmentation of large pieces into grains of maximum size of 40 cm. Calculation is conducted per m3 of actually excavated and transported material in natural condition, based on surveyed profiles and in the presence of the supervising engineer who shall also determine the class and percentage of excavated material. | m3 | 122653 | 33 | 4047549 |  | 0 | 98122.4 | 3238039.2 | 24530.6 | 809509.8 | 6243.98 | 33 | 206051.34 |  |  |  | 2520.67 | 33 | 83182.11 | 1664.2 | 33 | 54918.6 | 2044.3 | 33 | 67461.9 |  |  |  | 2692.4 | 33 | 88849.2 | 742.66 | 33 | 24507.78 | [15 empty] | 15908.21 | 524970.93 |  | 15908.21 | 33 | 524970.93
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.2 | Construction of the embankment for achieving the dimensions specified in the design with the material from the excavation (stone material). The item includes spreading, levelling and compaction to the necessary compaction level (≥ 40 MN/m2) of transported material. Backfilling is conducted in layers, and all the compaction level requirements of the previous layer have to be satisfied, which has to be shown to the supervising engineer. Maximum thickness of the spread layer of the embankment is determined by the contractor from his experience or on a trial section. All the works regarding the trial section are to be borne by the contractor. The item includes all the necessary testing regarding the construction of the embankment specified in the quality control programme. | m3 | 41346 | 13 | 537498 | 35150.23 | 456952.99 |  | 0 | 76496.23 | 994450.99 | 1234.1 | 13 | 16043.3 | 5484.18 | 13 | 71294.34 | 2790.87 | 13 | 36281.31 |  |  |  | 8398.7 | 13 | 109183.1 |  |  |  | 6964.8 | 13 | 90542.4 | 15086.5 | 13 | 196124.5 | [15 empty] | 39959.15 | 519468.95 |  | 39959.15 | 13 | 519468.95
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.3 | Supply, delivery and installation of the material for anchor trench. Material is stone, granulation 0/63 mm. The item includes loading, transport, spreading, levelling and compaction of the material until the necessary compaction level (≥20MN/m2). Calculation per m3 of placed material in compacted state. | m3 | 655 | 45 | 29475 | 0 | 0 |  | 0 | 655 | 29475 | 0 | 0 | 0 | [9 empty] | 744.95 | 45 | 33522.75 | [6 empty] | 433.96 | 45 | 19528.2 | [15 empty] | 1178.91 | 53050.95 | 19528.2 | 1178.91 | 45 | 53050.95
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| MACADAM ROAD | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.4 | Construction of the embankment for achieving the dimensions specified in the design with the material from the excavation (stone material). The item includes spreading, levelling and compaction to the necessary compaction level (≥ 40 MN/m2) of transported material. Backfilling is conducted in layers, and all the compaction level requirements of the previous layer have to be satisfied, which has to be shown to the supervising engineer. Maximum thickness of the spread layer of the embankment is determined by the contractor from his experience or on a trial section. All the works regarding the trial section are to be borne by the contractor. The item includes all the necessary testing regarding the construction of the embankment specified in the quality control programme. | m3 | 3220 | 23.5 | 75670 | 0 | 0 |  | 0 | 3220 | 75670 | 1592.3 | 23.5 | 37419.05 | [36 empty] | 1592.3 | 37419.05 |  | 1592.3 | 23.5 | 37419.05
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.5 | Supply, delivery and installation of stone materials granulation 0/63 mm for installation in the buffer layer of the fire safety roads. Thickness of the layer is 35 cm. The item includes loading, transport, spreading, levelling and compaction of the material until the necessary compaction level. The item includes all the necessary testing specified in the chapter Quality control and insurance programme. Calculation per m3 embedded material. | m3 | 285 | 65 | 18525 | 0 | 0 |  | 0 | 285 | 18525 |  |  | 0 | [27 empty] | 227.15 | 65 | 14764.75 |  | 0 | 0 |  |  |  | 227.15 | 14764.75 |  | 227.15 | 65 | 14764.75
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.6 | Supply, delivery and installation of chippings in the upper layer of fire safety road. Thickness of the layer is 10 cm. The item includes loading, transport, spreading, levelling and compaction of the material until the necessary compaction level. The item includes all the necessary testing specified in the chapter Quality control and insurance programme. Calculation per m3 embedded material. | m3 | 65 | 85 | 5525 | 0 | 0 |  | 0 | 65 | 5525 |  |  | 0 | [27 empty] | 64.9 | 85 | 5516.5 |  | 0 | 0 |  |  |  | 64.9 | 5516.5 |  | 64.9 | 85 | 5516.5
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2.7 | Transport of excess material from the excavation after backfilling the area around the building carried out at the landfill within construction site at distances up to 500m. The item includes loading, transport and unloading and spreading material at the landfill. | m3 | 78087 | 2.5 | 195217.5 | 0 | 0 |  | 0 | 78087 | 195217.5 |  |  | 0 | [9 empty] | 78404 | 2.5 | 196010 | [24 empty] | 78404 | 196010 | 792.5 | 78404 | 2.5 | 196010
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.2 | Earthworks TOTAL |  |  |  | 4909459.5 |  | 456952.99 |  | 3238039.2 |  | 2128373.29 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 20281.25 |  |  | 0 |  |  |  | 0 | 1351201.13 |  | 0 | 0 | 1351201.13
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3 | Rainfall collection system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.1 | PERIMETER CHANNEL | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.1.1 | Construction of the trapezoidal perimeter channel. The channel is of trapezoidal shape, of 60 cm width in the lower part, and 160 cm width in the upper part and of 50 cm height with the slope inclination 1:1. The channel has to be realized exactly according to dimensions specified in the design. The item includes forming the channel shape in already realized embankment, spreading and levelling and compaction to the necessary compaction level (>40 MN/m2) or by excavation in the cutting. Calculation is conducted per m of formed channel. | m | 648 | 45 | 29160 | 0 | 0 |  | 0 | 648 | 29160 |  |  | 0 | [21 empty] | 429 | 45 | 19305 | 248 | 45 | 11160 |  | 0 | 0 |  | 648 | 0 |  |  |  | 677 | 30465 |  | 677 | 45 | 30465
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.1.2 | Concreting lateral sides of the canal, after forming the canal shape, in concrete of d=12.0 cm thickness and of compressive strength C 25/30. Concrete reinforced with mesh reinforcement Q-131 with retarders flow channels on slopes greater than 7%. The item includes supply (batching) of concrete, placement and concrete curing and placement of fabric reinforcement and formwork. Calculation is conducted per m3 of embedded concrete. | m3 | 145 | 1300 | 188500 | 0 | 0 |  | 0 | 145 | 188500 |  |  | 0 | [21 empty] | 140.71 | 1300 | 182923 | 81.34 | 1300 | 105742 |  | 0 | 0 |  | 145 | 0 |  |  |  | 222.05 | 288665 |  | 222.05 | 1300 | 288665
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.2 | RC CULVERT | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Construction of RC culvert with concrete compressive strength C 25/30. Concrete reinforced with mesh reinforcement Q-131st Sentence included supply (making) concrete placing and curing of concrete and placing wire mesh and formwork. The items are covered and all necessary tests specified in section program control and quality assurance. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The calculation is performed by a built-ab failure. | psc | 1 | 7000 | 7000 | 0 | 0 |  | 0 | 1 | 7000 |  |  | 0 | [24 empty] | 2 | 7000 | 14000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 2 | 14000 |  | 2 | 7000 | 14000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.3 | SEDIMENTION TANK | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, delivery and installation of corrugated PE sewage pipes OD / ID 800/688 mm, SN 8, the performance of the body precipitator. The item includes the creation of shafts with all the elements (plates bottom, pipe connections, channel ...) to full readiness. It includes all needed work and material for installation to full functionality. | psc | 1 | 3500 | 3500 | 0 | 0 |  | 0 | 1 | 3500 |  |  | 0 | [21 empty] | 1 | 3500 | 3500 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 1 | 3500 |  | 1 | 3500 | 3500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.4 | RAINFALL COLLECTION RESERVOIR | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.4.1 | Concreting of the lean concrete in C16/20 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete. Calculation is conducted per m3 of placed concrete. | m3 | 11 | 1000 | 11000 | 0 | 0 |  | 0 | 11 | 11000 |  |  | 0 | [9 empty] | 12.06 | 1000 | 12060 | [24 empty] | 12.06 | 12060 | 1060 | 12.06 | 1000 | 12060
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.4.2 | Concreting in C30/37 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete.This item also includes the appropriate formwork, and all the materials and works related to that. Calculation is conducted per m3 of placed concrete. | m3 | 97 | 1400 | 135800 | 0 | 0 |  | 0 | 97 | 135800 |  |  | 0 | [9 empty] | 88.79 | 1400 | 124306 | [24 empty] | 88.79 | 124306 |  | 88.79 | 1400 | 124306
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.4.3 | Supply, cutting, bending, transportation and placing of reinforcement. This item includes all the work and material. Calculation is conducted per kg of placed reinforcement. | kg | 9700 | 7.5 | 72750 | 0 | 0 |  | 0 | 9700 | 72750 |  |  | 0 | [9 empty] | 12751 | 7.5 | 95632.5 | [24 empty] | 12751 | 95632.5 |  | 12751 | 7.5 | 95632.5
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.4.4 | Supply, delivery and installation of cast iron canal cover of circular shape with a dimension 60x60 cm. It includes all needed works and materials for the installation of the reservoir. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Cover class B 125 kN, according to HRN EN-124:2005 | psc | 3 | 700 | 2100 | 0 | 0 |  | 0 | 3 | 2100 |  |  | 0 | [21 empty] | 3 | 700 | 2100 |  | 0 | 0 |  | 3 | 0 |  | 0 | 0 |  |  |  | 3 | 2100 |  | 3 | 700 | 2100
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.5 | PIPELINE | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, delivery and installation of smooth PE pipes for drainage clean rainwater to drainage well. It includes all needed works and materials for their installation. Calculation per m 'of embedded pipes. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) PE OD/ID 315/277 mm | m' | 21.7 | 100 | 2170 | 0 | 0 |  | 0 | 21.7 | 2170 |  |  | 0 | [24 empty] | 17.5 | 100 | 1750 |  | 0 | 0 |  | 21.7 | 0 |  |  |  | 17.5 | 1750 |  | 17.5 | 100 | 1750
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.6 | REVISION SHAFT | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, delivery and installation of corrugated HDPE sewer pipes OD / ID 1000/851 mm, SN 8, for the performance of the body of inspection shafts. The item includes the preparation of shafts with all the elements (plates bottom, pipe connections, channel ...) to full readiness, including the performance of climbers from PE sheet thickness min 2 cm, width 45 cm back protection and performance. It includes all needed works and materials for installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Revision shaft | psc | 1 | 5000 | 5000 | 0 | 0 |  | 0 | 1 | 5000 |  |  | 0 | [24 empty] | 1 | 5000 | 5000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 5000 |  | 1 | 5000 | 5000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3.7 | FILTRATION WELL | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Supply, delivery and installation of corrugated HDPE sewer pipes OD / ID 1000/851 mm, SN 8, for the performance of absorption well, including the performance of climbers from PE sheet thickness min 2 cm, width 45 cm, back protection and performance of the perforation of the well which is located below level of inlet pipe. It includes all needed works and materials for installation to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Infiltration well - 1 piece | psc | 1 | 6500 | 6500 | 0 | 0 |  | 0 | 1 | 6500 |  |  | 0 | [24 empty] | 1 | 6500 | 6500 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 6500 |  | 1 | 6500 | 6500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.1.3 | Rainfall collection system TOTAL |  |  |  | 463480 |  | 0 |  | 0 |  | 463480 |  |  | 0 | [23 empty] | 207828 |  |  | 144152 |  |  | 0 |  |  | 0 |  |  |  | 0 | 583978.5 |  | 0 | 0 | 583978.5
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.1 | Excavation of landfill basins for landfill cells I, II, III and IV and construction of the clean stormwater drainage system and macadam roads TOTAL |  |  |  | 5453767 |  | 456952.99 |  | 3238039.2 |  | 2672680.79 |  |  | 320292.662 |  |  | 76894.34 | [5 empty] | 54918.6 | [14 empty] | 211065.5 |  |  | 144152 |  |  | 20281.25 |  |  | 0 |  |  |  | 0 | 2015996.102 |  | 0 | 0 | 2015996.102
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2 | Bottom sealing layer | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.1 | Earthworks | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.1.1 | The construction of the layer for levelling made of clay in the thickness of d=15 cm, and after realized excavation and embankment, namely after forming the area (bath) for disposing waste. The works have to be realized according to the design. The item includes loading, transport, spreading and compaction of the base to the necessary compaction level (≥40 MN/m2). The item includes all the necessary testing specified in the chapter Quality control and quality assurance programme. The calculation is conducted per m3 of embedded replacement layer. | m3 | 5100 | 45 | 229500 | 0 | 0 |  | 0 | 5100 | 229500 |  |  | 0 |  |  |  | 1403.79 | 45 | 63170.55 |  |  |  | 1019.25 | 45 | 45866.25 |  |  |  | 891.87 | 45 | 40134.15 | 1467.33 | 45 | 66029.85 | [15 empty] | 4782.24 | 215200.8 |  | 4782.24 | 45 | 215200.8
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.1.1 | Construction of the drainage layer in stone aggregate in the lower liner of thickness d=51 cm. The draining layer is made of aggregate, granulation 16/32 mm. The item includes supply, delivery, placement and testing of the draining layer, and all the works have to be realized according to the design. Calculation is conducted per m3 of placed material. | m3 | 17200 | 85 | 1462000 | 0 | 0 |  | 0 | 17200 | 1462000 |  |  | 0 |  |  |  | 4772.89 | 85 | 405695.65 |  |  |  | 3755.64 | 85 | 319229.4 |  |  |  | 3032.36 | 85 | 257750.6 | 4522.99 | 85 | 384454.15 | [15 empty] | 16083.88 | 1367129.8 |  | 16083.88 | 85 | 1367129.8
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.1 | Earthworks TOTAL |  |  |  | 1691500 |  | 0 |  | 0 |  | 1691500 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 1582330.6 |  | 0 | 0 | 1582330.6
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2 | Geosynthetic works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2.1 | Supply, delivery and placement of smooth PEHD geomembrane, thickness of d=2.0 mm as a protection from flooding of anchor trench. Geomembrane can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap, cutting and anchoring. | m2 | 1965 | 42 | 82530 | 0 | 0 |  | 0 | 1965 | 82530 |  |  | 0 | [6 empty] | 540 | 42 | 22680 | [27 empty] | 540 | 22680 |  | 540 | 42 | 22680
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| BOTTOM SEALING LAYER | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2.2 | Supply, delivery and placement of geosynthetic clay liner (GCL) in the bottom sealing layer of the disposal site. Characteristics, testing and manner of placing the geosynthetic clay liner (GCL) in the bottom liner have to be realized in the manner described in the design and according to the instructions of the producer. GCL can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surfaces, and it includes all the losses occurred due to overlap, cutting and anchoring. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 33720 | 34 | 1146480 | 0 | 0 |  | 0 | 33720 | 1146480 |  |  | 0 |  |  |  | 11318.47 | 34 | 384827.98 | 5760 | 34 | 195840 | 8187.5 | 34 | 278375 |  |  |  | 2338.46 | 34 | 79507.64 | 7969.8 | 34 | 270973.2 | [15 empty] | 35574.23 | 1209523.82 | 63043.82 | 35574.23 | 34 | 1209523.82
[14 empty] | 0 | [5 empty] | 0 | [30 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2.3 | Supply, delivery and placement of the PEHD geomembrane rough on both sides for the slopes and smooth for the bottom of landfill cells, thickness of d=2.5 mm in the lower liner of the disposal site and after the placement of GCL. Characteristics, testing and manner of placing the PEHD geomembrane rough on both sides into the lower liner has to be realized in the manner described in the design and according to the instructions of the producer. Geomembrane can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap, cutting and anchoring. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 33720 | 52 | 1753440 | 0 | 0 |  | 0 | 33720 | 1753440 |  |  | 0 |  |  |  | 11318.47 | 52 | 588560.44 | 7200 | 52 | 374400 | 8187.5 | 52 | 425750 |  |  |  | 898.46 | 52 | 46719.92 | 7969.8 | 52 | 414429.6 | [15 empty] | 35574.23 | 1849859.96 | 96419.96 | 35574.23 | 52 | 1849859.96
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2.4 | Supply, delivery and placement of the protective geotextile of 1000 g/m2 weight in the bottom liner of the disposal site, after the placement of the PEHD geomembrane. Characteristics, testing and manner of placing the protective geotextile into the lower liner have to be realized in the manner described in the design and according to the instructions of the producer. Protective geotextile can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap, cutting and anchoring. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 33720 | 24.5 | 826140 | 0 | 0 |  | 0 | 33720 | 826140 |  |  | 0 |  |  |  | 11318.47 | 24.5 | 277302.515 | 3024 | 24.5 | 74088 | 8187.5 | 24.5 | 200593.75 |  |  |  | 5074.46 | 24.5 | 124324.27 | 7969.8 | 24.5 | 195260.1 | [15 empty] | 35574.23 | 871568.635 | 45428.635 | 35574.23 | 24.5 | 871568.635
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2.5 | Supply, delivery and placement of geogrid, 30/30 kN/m in the bottom liner of the disposal site, after the placement of the drainage layer. Characteristics, testing and manner of placing the protective geotextile into the lower liner have to be realized in the manner described in the design and according to the instructions of the producer. Protective geotextile can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap, cutting and anchoring. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 33720 | 12 | 404640 | 0 | 0 |  | 0 | 33720 | 404640 |  |  | 0 |  |  |  | 11318.47 | 12 | 135821.64 | 14583.92 | 12 | 175007.04 | 3275 | 12 | 39300 | [6 empty] | 6396.84 | 12 | 76762.08 | [15 empty] | 35574.23 | 426890.76 | 22250.76 | 35574.23 | 12 | 426890.76
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.2.2 | Geosynthetic works TOTAL |  |  |  | 4213230 |  | 0 |  | 0 |  | 4213230 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 4380523.175 |  | 0 | 0 | 4380523.175
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.2 | Bottom sealing layer TOTAL |  |  |  | 5904730 |  | 0 |  | 0 |  | 5904730 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 5962853.775 |  | 0 | 0 | 5962853.775
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.3 | Leachate collection system | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1 | Leachate collection reservoir | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1.1 | Concrete-work of the foundation layer 10 cm thickness, with concrete C16/20. Calculation by m3 of the embedded material including the rim formwork. | m3 | 7 | 800 | 5600 | 0 | 0 |  | 0 | 7 | 5600 |  |  | 0 | [9 empty] | 6.83 | 800 | 5464 | [24 empty] | 6.83 | 5464 |  | 6.83 | 800 | 5464
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1.2 | Concreting in C35/45 concrete. This item includes production, i.e. supply and transportation of concrete, placement and curing of fresh concrete.This item also includes the appropriate formwork, and all the materials and works related to that. Calculation is conducted per m3 of placed concrete. | [12 empty] | 0 | [9 empty] | 34.53 | 1500 | 51795 | [24 empty] | 34.53 | 51795 |  | 0 | 0 | 0
| a) LEACHATE COLLECTION RESERVOIR | m3 | 47 | 1500 | 70500 | 0 | 0 |  | 0 | 47 | 70500 |  |  | 0 | [36 empty] | 0 | 0 |  | 34.53 | 1500 | 51795
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1.3 | Supply, cutting, bending, transportation and placing of reinforcement. This item includes all the work and material. Calculation is conducted per kg of placed reinforcement. | [12 empty] | 0 | [9 empty] | 5457.5 | 7.5 | 40931.25 | [24 empty] | 5457.5 | 40931.25 |  | 0 | 0 | 0
| a) LEACHATE COLLECTION RESERVOIR | kg | 4700 | 7.5 | 35250 | 0 | 0 |  | 0 | 4700 | 35250 |  |  | 0 | [36 empty] | 0 | 0 |  | 5457.5 | 7.5 | 40931.25
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1.4 | Supply, delivery and installation of cast iron canal cover of circular shape with a dimension 150x120 cm. It includes all needed works and materials for the installation of the reservoir. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Cover class B 125 kN, according to HRN EN-124:2005 | psc | 1 | 4500 | 4500 | 0 | 0 |  | 0 | 1 | 4500 |  |  | 0 | [21 empty] | 1 | 4500 | 4500 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 1 | 4500 |  | 1 | 4500 | 4500
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.1 | Leachate collection reservoir TOTAL |  |  |  | 115850 |  | 0 |  | 0 |  | 115850 |  |  | 0 | [23 empty] | 4500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 102690.25 |  | 0 | 0 | 102690.25
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.2 | Pipeline | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.2.1 | Procurement, placement and installation of PEHD pipes OD315mm, SDR11 with perforation on 2/3 of total surface for the collection and drainage of leachate. Item includes procurement and installation of electrofusion sockets for pipe connection. | m | 795 | 435 | 345825 | 0 | 0 |  | 0 | 795 | 345825 |  |  | 0 |  |  |  | 190.88 | 435 | 83032.8 |  |  |  | 179.28 | 435 | 77986.8 |  |  |  | 172.86 | 435 | 75194.1 | 147.62 | 435 | 64214.7 | [15 empty] | 690.64 | 300428.4 |  | 690.64 | 435 | 300428.4
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.2.2 | Procurement, placement and installation of full PEHD pipes OD315mm, SDR11 for the collection and drainage of leachate. Item includes procurement and installation of electrofusion sockets for pipe connection and the necessary flanged pieces. | m | 145 | 435 | 63075 | 0 | 0 |  | 0 | 145 | 63075 |  |  | 0 |  |  |  | 52.25 | 435 | 22728.75 |  |  |  | 34.64 | 435 | 15068.4 |  |  |  | 35.5 | 435 | 15442.5 | 25.22 | 435 | 10970.7 | [15 empty] | 147.61 | 64210.35 | 1135.35 | 147.61 | 435 | 64210.35
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.2.3 | Procurement and installation of the PEHD revision shaft Ø1600 mm, SN8 with PEHD Ø800 mm entry opening and top cover, bottom of the shaft thickness 20.0 mm, with PEHD ladders with safety cage and ventilation openings. Item includes all necessary fittings and parts for constructing the pipe line connections for the seepage water Procurement from the repository and pipe line connections for water drainage toward the pump shaft. | psc | 2 | 13000 | 26000 | 0 | 0 |  | 0 | 2 | 26000 |  |  | 0 | [15 empty] | 1 | 13000 | 13000 | 1 | 13000 | 13000 | [15 empty] | 2 | 26000 |  | 2 | 13000 | 26000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.3.2 | Pipeline TOTAL |  |  |  | 434900 |  | 0 |  | 0 |  | 434900 |  |  | 0 | [5 empty] | 105761.55 | [17 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 390638.75 |  | 0 | 0 | 390638.75
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.3 | Leachate collection system TOTAL |  |  |  | 550750 |  | 0 |  | 0 |  | 550750 |  |  | 0 | [23 empty] | 4500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 493329 |  | 0 | 0 | 493329
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4 | Cover sealing layer | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.1 | Earthworks | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| MIDDLE SEALING LAYER | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.1.1 | The construction of the layer for levelling (lining layer) made of soil in the thickness of d=25 cm. The works have to be realized according to the design. The item includes loading, transport, spreading and compaction of the base to the necessary compaction level. The item includes all the necessary testing specified in the chapter Quality control and quality assurance programme. The calculation is conducted per m3 of developed area. | m3 | 357 | 20 | 7140 | 0 | 0 |  | 0 | 357 | 7140 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 20 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| COVER SEALING LAYER | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.1.2 | The construction of the layer for levelling (lining layer) made of soil in the thickness of d=25 cm. The works have to be realized according to the design. The item includes loading, transport, spreading and compaction of the base to the necessary compaction level. The item includes all the necessary testing specified in the chapter Quality control and quality assurance programme. The calculation is conducted per m3 of developed area. | m3 | 6670 | 20 | 133400 | 0 | 0 |  | 0 | 6670 | 133400 |  |  | 0 | [12 empty] | 3080.86 | 20 | 61617.2 |  |  |  | 1500 | 20 | 30000 | 1502.75 | 20 | 30055 |  | 0 | 0 |  | 6670 | 0 |  | 0 | 0 |  |  |  | 6083.61 | 121672.2 |  | 6083.61 | 20 | 121672.2
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.1.3 | Supply, delivery and placement of recultivation layer made of soil. Thickness of layer is 0,81 m. Characteristics, testing and manner of placing reciltivation layer into the cover sealing layer have to be realized in the manner described in the design and according to the instructions of the producer. Recultivation layer can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m3 of lined surface. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m3 | 21610 | 32 | 691520 | 0 | 0 |  | 0 | 21610 | 691520 |  |  | 0 | [12 empty] | 9981.97 | 32 | 319423.04 |  |  |  | 2464.68 | 32 | 78869.76 | 12131.11 | 32 | 388195.52 |  | 0 | 0 |  | 21610 | 0 |  | 0 | 0 |  |  |  | 24577.76 | 786488.32 |  | 24577.76 | 32 | 786488.32
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.1.4 | Supply, delivery and placement of humus layer. Thickness of layer is 0,20 m. Characteristics, testing and manner of placing humus into the cover sealing layer have to be realized in the manner described in the design and according to the instructions of the producer. Recultivation layer can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 5335 | 20 | 106700 | 0 | 0 |  | 0 | 5335 | 106700 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 20 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  |  | 0 | 0
E.4.1 | Earthworks TOTAL |  |  |  | 938760 |  | 0 |  | 0 |  | 938760 |  |  | 0 | [23 empty] | 418250.52 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 908160.52 |  | 0 | 0 | 908160.52
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2 | Geosynthetic works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| INTERSEALING | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.1 | Supply, delivery and placement of the geotextile of 400 g/m2 weight in the middle sealing layer of the disposal site, before and after the placement of the HDPE geomembrane so the quantity is calculated twice. Characteristics, testing and manner of placing the geotextile into the middle sealing layer have to be realised in the manner described in the design and according to the instructions of the producer. Geotextile can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap and cutting. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 1426 | 9.5 | 13547 | 0 | 0 |  | 0 | 1426 | 13547 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 9.5 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.2 | Supply, delivery and placement of the HDPE geomembrane rough on both sides for the slopes and smooth for the bottom of landfill cells, thickness of d=1.5 mm in the middle sealing layer of the disposal site and after the placement of geotextile. Characteristics, testing and manner of placing the PEHD geomembrane rough on both sides into the middle layer has to be realized in the manner described in the design and according to the instructions of the producer. Geomembrane can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap and cutting. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 1426 | 40 | 57040 | 0 | 0 |  | 0 | 1426 | 57040 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 40 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| COVER SEALING LAYER | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.3 | Supply, delivery and placement of the geosynthetic de-gassing composite in the cover sealing layer of the disposal site, before the placement of the geogrid. Characteristics, testing and manner of placing the composite into the cover sealing layer have to be realized in the manner described in the design and according to the instructions of the producer. Composite can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap and cutting. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 26675 | 26 | 693550 | 0 | 0 |  | 0 | 26675 | 693550 |  |  | 0 | [12 empty] | 17323.42 | 26 | 450408.92 | [6 empty] | 7011 | 26 | 182286 |  | 0 | 0 |  | 26675 | 0 |  | 0 | 0 |  |  |  | 24334.42 | 632694.92 |  | 24334.42 | 26 | 632694.92
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.4 | Supply, delivery and placement of geosynthetic clay liner (GCL) in the cover sealing layer of the disposal site. Characteristics, testing and manner of placing the geosynthetic clay liner (GCL) in the cover liner have to be realized in the manner described in the design and according to the instructions of the producer. GCL can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surfaces, and it includes all the losses occurred due to overlap, cutting and anchoring. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 26675 | 34 | 906950 | 0 | 0 |  | 0 | 26675 | 906950 |  |  | 0 | [12 empty] | 17323.42 | 34 | 588996.28 | [6 empty] | 7011 | 34 | 238374 |  | 0 | 0 |  | 26675 | 0 |  | 0 | 0 |  |  |  | 24334.42 | 827370.28 |  | 24334.42 | 34 | 827370.28
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.5 | Supply, delivery and placement of the geosynthetic drainage composite in the cover sealing layer of the disposal site, before the placement of the geogrid. Characteristics, testing and manner of placing the composite into the cover sealing layer have to be realised in the manner described in the design and according to the instructions of the producer. Composite can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap and cutting. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 26675 | 26 | 693550 | 0 | 0 |  | 0 | 26675 | 693550 |  |  | 0 | [6 empty] | 2872.8 | 26 | 74692.8 |  |  |  | 14450.62 | 26 | 375716.12 | [6 empty] | 7011 | 26 | 182286 |  | 0 | 0 |  | 26675 | 0 |  | 0 | 0 |  |  |  | 24334.42 | 632694.92 |  | 24334.42 | 26 | 632694.92
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2.6. | Supply, delivery and placement of geogrid, 30/30 kN/m in the cover sealing layer of the disposal site, placed on protective geotextile. Characteristics, testing and manner of placing the geogrid into the cover sealing layer have to be realized in the manner described in the design and according to the instructions of the producer. Geogrid can be placed only after testing proves its quality and it is approved by the supervising engineer. Calculation is conducted per m2 of lined surface and it includes all the losses occurred due to overlap and cutting. The item also includes all the necessary testing specified in the chapter Quality control and insurance programme. | m2 | 26675 | 12 | 320100 | 0 | 0 |  | 0 | 26675 | 320100 |  |  | 0 | [12 empty] | 17323.42 | 12 | 207881.04 | [6 empty] | 7011 | 12 | 84132 |  | 0 | 0 |  | 26675 | 0 |  | 0 | 0 |  |  |  | 24334.42 | 292013.04 |  | 24334.42 | 12 | 292013.04
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.2 | Geosynthetic works TOTAL |  |  |  | 2684737 |  | 0 |  | 0 |  | 2684737 |  |  | 0 | [23 empty] | 687078 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 2384773.16 |  | 0 | 0 | 2384773.16
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.3 | Gas wells | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Execution of gas wells for passive-gassed, diameter 100 cm. All necessary materials, labor and machinery are included in price. Gas well is perforated tube diameter 160 mm (DN 160 HDPE), coated stone aggregate (32/64 mm), in packs of wire braiding, with biofilters diameter 300 cm. Performance according to General technical requirements and designs. Calculation per piece. | psc | 11 | 3600 | 39600 | 0 | 0 |  | 0 | 11 | 39600 |  |  | 0 | [12 empty] | 8 | 3600 | 28800 | [6 empty] | 4 | 3600 | 14400 |  | 0 | 0 |  | 11 | 0 |  | 0 | 0 |  |  |  | 12 | 43200 |  | 12 | 3600 | 43200
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.4.3 | Gas wells TOTAL |  |  |  | 39600 |  | 0 |  | 0 |  | 39600 |  |  | 0 | [23 empty] | 14400 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 43200 |  | 0 | 0 | 43200
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.4 | Cover sealing layer TOTAL |  |  |  | 3663097 |  | 0 |  | 0 |  | 3663097 |  |  | 0 | [23 empty] | 1119728.52 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 3336133.68 |  | 0 | 0 | 3336133.68
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.5 | System for collecting clean stormwater from the body of a disposal cell | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.5.1 | Construction of the trapezoidal perimeter channel. The channel is of trapezoidal shape, of 60 cm width in the lower part, and 160 cm width in the upper part and of 50 cm height with the slope inclination 1:1. The channel has to be realized exactly according to dimensions specified in the design. The item includes forming the channel shape in already realized embankment, spreading and levelling and compaction to the necessary compaction level (>40 MN/m2) or by excavation in the cutting. Calculation is conducted per m of formed channel. | m | 1996 | 10 | 19960 | 0 | 0 |  | 0 | 1996 | 19960 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 10 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.5.2 | Concreting lateral sides of the canal, after forming the canal shape, in concrete of d=12.0 cm thickness and of compressive strength C 25/30. The item includes supply (batching) of concrete, placement and concrete curing and placement of fabric reinforcement and formwork. Calculation is conducted per m3 of embedded concrete. | m3 | 86 | 1100 | 94600 | 0 | 0 |  | 0 | 86 | 94600 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 1100 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.5 | System for collecting clean stormwater from the body of a disposal cell TOTAL |  |  |  | 114560 |  | 0 |  | 0 |  | 114560 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.6 | Service road | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| EXECUTION OF SERVICE ROAD | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For the purpose of service access on top of the closed landfill, service road is carried out, as shown in the graphic part of the design. Cross inclination of this road is 4%, and the maximum longitudinal inclination is 10%. Road is carried out in levels as follows (top to bottom): | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • sand 2 cm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • stone material 20 cm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Geotextile (200 g / m2) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Stone material 35cm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| These layers are placed on a soil layer (81 cm) that is installed above geosynthetics within recultivating layer. | m2 | 1255 | 40 | 50200 | 0 | 0 |  | 0 | 1255 | 50200 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 40 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.6 | Service road TOTAL |  |  |  | 50200 |  | 0 |  | 0 |  | 50200 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.7 | Waste displacement | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The item includes: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| 1. Excavation and removal of existing waste and other materials, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| 2. Separation of certain types of waste (bulk waste, tires, metals, ...) from existing waste and handing over to the authorized concessionaire, | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| 3. Installation and planning of existing waste on newly-built fields; | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| 4. Remediation and landscaping / planning of cleaned surface. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Excavation and moving of the existing waste according to the manner defined in the Work Plan. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Before excavating waste, make sure to remove the covering material (soil) carefully. The cover material embedded (de-deposited) is over the disposed waste in a thickness of approximately 30 cm and it is necessary to extricate it carefully to prevent its mixing with waste. The excavated inert material can be used as making a leveling layer or as a daily covering. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Waste scrap to the constructed disposal cell to dimenstion defined by the project, in order to achieve the final inclination of the final caver layer and the intersealing layer of 1: 2.5. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| During works on excavation of existing waste, consider the following: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - The stability of the existing landfill to avoid the uncontrolled corrosion of existing waste and | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - There has been a fire on the landfill, which has not been fully extinguished, so it has to be secured with the fire extinguisher on the construction site. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| During work, special attention should be undertake on all available occupational safety, fire protection and environmental protection measures to avoid accidental situations during the execution of works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Calculation per m3 of compacted waste embedded in the landfill body according to the project’s dimensions. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Any additional waste transfer as per working technology will not be specifically calculated | m3 | 155000 | 23 | 3565000 | 0 | 0 |  | 0 | 155000 | 3565000 |  |  | 0 | [6 empty] | 82560 | 23 | 1898880 | 21421 | 23 | 492683 | 76036 | 23 | 1748828 |  |  |  | 24735.64 | 23 | 568919.72 | 11518 | 23 | 264914 |  | 0 | 0 |  | 155000 | 0 |  | 0 | 0 |  |  |  | 216270.64 | 4974224.72 | 1409224.72 | 216270.64 | 23 | 4974224.72
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.7 | Waste displacement TOTAL |  |  |  | 3565000 |  | 0 |  | 0 |  | 3565000 |  |  | 0 | [23 empty] | 264914 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 4974224.72 |  | 0 | 0 | 4974224.72
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.8 | Preparation of waste samples | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| For this purposes of waste samples it is required to pick waste with the adequate excavator from predefined position and depth in coordination with Investor and dispose it to the accessible handling areas (if possible, it can be constructed cell) for the Investor or his representative to be able to take representative waste sample. Number of samples is 6. After sampling the remaining waste from the handling areas must be disposed to the constructed cell. | set | 6 | 2000 | 12000 | 0 | 0 |  | 0 | 6 | 12000 |  |  | 0 | [21 empty] | 6 | 2000 | 12000 |  | 0 | 0 |  | 6 | 0 |  | 0 | 0 |  |  |  | 6 | 12000 |  | 6 | 2000 | 12000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
E.8 | Preparation of waste samples TOTAL |  |  |  | 12000 |  | 0 |  | 0 |  | 12000 |  |  | 0 | [23 empty] | 12000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 12000 |  | 0 | 0 | 12000
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E | CIVIL WORKS - LANDFILL | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.1 | EXCAVATION OF LANDFILL BASINS FOR LANDFILL CELLS I, II, III AND IV AND CONSTRUCTION OF THE CLEAN STORMWATER DRAINAGE SYSTEM AND MACADAM ROADS. |  |  |  | 5453767 |  | 456952.99 |  | 3238039.2 |  | 2672680.79 |  |  | 0 | [23 empty] | 211065.5 |  |  | 144152 |  |  | 20281.25 |  |  | 0 |  |  |  | 0 | 2015996.102 |  | 0 | 0 | 2015996.102
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.2 | BOTTOM SEALING LAYER |  |  |  | 5904730 |  | 0 |  | 0 |  | 5904730 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 5962853.775 |  | 0 | 0 | 5962853.775
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.3 | LEACHATE COLLECTION SYSTEM |  |  |  | 550750 |  | 0 |  | 0 |  | 550750 |  |  | 0 | [23 empty] | 4500 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 493329 |  | 0 | 0 | 493329
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.4 | COVER SEALING LAYER |  |  |  | 3663097 |  | 0 |  | 0 |  | 3663097 |  |  | 0 | [23 empty] | 1119728.52 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 3336133.68 |  | 0 | 0 | 3336133.68
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.5 | SYSTEM FOR COLLECTING CLEAN STORMWATER FROM THE BODY OF A DISPOSAL CELL |  |  |  | 114560 |  | 0 |  | 0 |  | 114560 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.6 | SERVICE ROAD |  |  |  | 50200 |  | 0 |  | 0 |  | 50200 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.7 | WASTE DISPLACEMENT |  |  |  | 3565000 |  | 0 |  | 0 |  | 3565000 |  |  | 0 | [23 empty] | 264914 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 4974224.72 |  | 0 | 0 | 4974224.72
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E.8 | PREPARION OF WASTE SAMPLES |  |  |  | 12000 |  | 0 |  | 0 |  | 12000 |  |  | 0 | [23 empty] | 12000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 12000 |  | 0 | 0 | 12000
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
E | CIVIL WORKS - LANDFILL SUMMARY |  |  |  | 19314104 |  | 456952.99 |  | 3238039.2 |  | 16533017.79 |  |  | 0 | [23 empty] | 1612208.02 |  |  | 144152 |  |  | 20281.25 |  |  | 0 |  |  |  | 0 | 16794537.277 |  | 0 | 0 | 16794537.277
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F. | MECHANICAL WORKS | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.1 | Procurement, supply and construction of a pumping station for recirculation of leachate | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The item includes: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The pumps for recirculation of leachate as a Grundfos SV.80.125.290.2.58H or equivalent. The body and the impeller are made of stainless steel. The pumps are explosion-proof category 1. Copies of the two pumps, according to the technical solution shown in the designs of the main mechanical design. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Pressure pipe stainless steel (Č1.4301), which includes all the connecting pieces according to the technical solution shown in the designs of the main mechanical design. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Two check valves and two valves to separate stations, all according to the technical solution shown in the drawings of mechanical design. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Switches levels in explosion-proof, for use in hazardous zone 0 (category 1). Copies of the total 4 level switches. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Control electrical cabinet with equipment suitable for the defined zone of danger of explosion (zone 0), with "soft start" running the pumps and transmission signals, according to the technical solution defined in the main electro design | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Steel holder for extraction pumps with winch and ropes, appropriate capacity for the selected pump (1 pc.). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Paragraph is covered by all the connecting material required for installation of the pump, switch level, the carrier extraction pumps and control electrical cabinets, and all work on the same assembly. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Testing of electrical installation, pressure testing, functional testing and all other necessary tests in accordance with the applicable regulations. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Technical supervision of facility by Ex Agency and obtaining Ex documents and Ex Manual forming. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Release of pumping stations in a test drive with the regulation of labor, training of personnel investors to operate and possibly eliminating the identified deficiencies. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Handing over the device and instructions for handling and inventory of spare and wear parts. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| As built documentation. | set | 1 | 230000 | 230000 | 0 | 0 |  | 0 | 1 | 230000 |  |  | 0 | [18 empty] | 0.8 | 230000 | 184000 |  |  |  | 0.2 | 230000 | 46000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 230000 |  | 1 | 230000 | 230000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.1 | Procurement, supply and construction of a pumping station for recirculation of leachate TOTAL |  |  |  | 230000 |  | 0 |  | 0 |  | 230000 |  |  | 0 | [23 empty] | 0 |  |  | 46000 |  |  | 0 |  |  | 0 |  |  |  | 0 | 230000 |  | 0 | 0 | 230000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.2 | Procurement, supply and construction of pump stations for storm water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The item includes: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Pumps for storm water as Grundfos SP 9-8 or equivalent. The body and the impeller are made of stainless steel. Copies of the two pumps, according to the technical solution shown in the designs of the main mechanical project. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Pressure pipe stainless steel (Č1.4301), which includes all the connecting pieces according to the technical solution shown in the designs of the main mechanical project. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Two check valves and two valves to separate stations, all according to the technical solution shown in the drawings of mechanical project. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Switches levels (performed a total of 4 level switches). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Control electrical cabinet with "soft start" running the pumps and transmission signals, according to the technical solution defined in the main electro project. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Steel holder for extraction pumps with winch and ropes, appropriate capacity for the selected pump (1 pc.). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Paragraph is covered by all the connecting material required for installation of the pump, switch level, the carrier extraction pumps and control electrical cabinets, and all work on the same assembly. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Testing of electrical installation, pressure testing, functional testing and all other necessary tests in accordance with the applicable regulations. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Set fire hose with a diameter of 50 mm and a total length of 100 m, including all fittings to connect the pump station, cabinet for outdoor installation size sufficient to accommodate all the hoses and two nozzles for washing the surface, hole diameter 16-24 mm. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Release of pumping stations in a test drive with the regulation of labor, training of personnel investors to operate and possibly eliminating the identified deficiencies. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Handing over the device and instructions for handling and inventory of spare and wear parts. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| As built documentation. | set | 1 | 35000 | 35000 | 0 | 0 |  | 0 | 1 | 35000 |  |  | 0 | [21 empty] | 1 | 35000 | 35000 |  | 0 | 0 |  | 1 | 0 |  | 0 | 0 |  |  |  | 1 | 35000 |  | 1 | 35000 | 35000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.2 | Procurement, supply and construction of pump stations for storm water TOTAL |  |  |  | 35000 |  | 0 |  | 0 |  | 35000 |  |  | 0 | [23 empty] | 35000 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 35000 |  | 0 | 0 | 35000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.3 | Procurement, supply and construction of wheels washing facility | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The item includes: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Wheel washing units (made up of two modules of the same length are connected at the construction site in one unit) consisting of: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Two hot galvanized elements for washing, measuring 5.60 m x 3.1 m, installed 50 cm into the ground, allowing access for vehicles to the level of the country after leaving the location, before access road and entrance and exit zone. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The central element with sloping sides constructed of robust galvanized grid | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Static nozzle system for complete flushing profile wheels, exterior and interior surface of the wheel and chassis parts | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Two galvanized wall with nozzles (left and right) with integrated, adjustable side jets. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Dimensions: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| external dimensions 6600 x 3150 x 50 mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| truck width 2800 mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| complete unit weight 6000 kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sedimentary pool (recirculation), derived from the concrete: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Dimensions: 8500 x 3000 x 3000 mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Useful volume: 55 m3 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Additional safety equipment sedimentary basin composed of: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Handrail designed for installation around the perimeter of the pool, made of square steel profile, galvanized, height 1200 mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Ladders for access to pumps, made of square steel profile, galvanized ' | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Submersible pressure pumps DN 100, special construction, intended for fixed installation in the chamber pump sedimentary basin, complete with non-return valve elements for fixing the pumps and piping and wiring Electrical cable length of 15 m, the following characteristics: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Q = 2500 l / min | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| H = 1,8 bar | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| N = 6,5 kW / 400 V / 50Hz | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Dimensions: Ø270 × 530 mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Weight: 80 kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Equipment (control -dosing) consisting of: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Flocculant dosing device, complete with electro-mechanical dosing pump lubrication oil and the diaphragm dosing head, suction tube with a suction valve, pressure pipes with dosage valves for installation in pressure pipe submersible pumps and tank for flocculant | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Control - the control cabinet, made from stainless steel, complete with built-in automation and control for fully automatic operation, in accordance with EN 60439-1, the setting options (programming) the length of time for washing, and all necessary elements | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Solid steel barrier separating sedimentary basins of the chamber pump with steel mesh for dressing in the upper part of the barrier | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Piping required for internally connecting the above elements in the functional unit, including supports, the supports, the required fittings such as for example, the float valve to replenish the pool, a flexible tube, the protective tube and the penetrating, small consumables, and tightening the fastening material, and the required corrosion other protection of pipelines and the like. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Electrical cables necessary for the internal wiring of the above electrical consumer (inside the device) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Paragraph covered all fittings and the work required for installation. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Release of pumping stations in a test drive with the regulation of labor, training of personnel investors to operate and possibly eliminating the identified deficiencies. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Handing over the device and instructions for handling and inventory of spare and wear parts. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Production of as-built documentation. | set | 1 | 500000 | 500000 | 0 | 0 |  | 0 | 1 | 500000 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 500000 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
F.3 | Procurement, supply and construction of wheels washing facility TOTAL |  |  |  | 500000 |  | 0 |  | 0 |  | 500000 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
F | MECHANICAL WORKS |  |  |  | 765000 |  | 0 |  | 0 |  | 765000 |  |  | 0 | [23 empty] | 35000 |  |  | 46000 |  |  | 0 |  |  | 0 |  |  |  | 0 | 265000 |  | 0 | 0 | 265000
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
F | MECHANICAL WORKS SUMMARY |  |  |  | 765000 |  | 0 |  | 0 |  | 765000 |  |  | 0 | [23 empty] | 35000 |  |  | 46000 |  |  | 0 |  |  | 0 |  |  |  | 0 | 265000 |  | 0 | 0 | 265000
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G | ELECTROTEHNICAL WORKS | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
Item No. | Item description | Unit | Quantity | Rate | Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  |  | 0 | [36 empty] | 0 |  |  | 0
1 | 2 | 3 | 4 | 5 | 6 | 4 | 6 | 4 | 6 | 4 | 6 |  |  | 0 | [36 empty] | 0 | 0 |  | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.1 | Generator station | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.1.1 | Supply and installation of automatic, stationary, diesel-generator plant in housing for indoor or outdoor use, stand-by / Primary power: 110 / 100kVA - 88 / 80kW, 159A 3P + N, with a minimum of the following characteristics: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The facility should be minimally equipped with: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Industrial, water-cooled, diesel engine | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Radiator with a cooling medium designed for 50 ° C max T in the air inlet | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Electric starter and charging alternator | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Mechanical speed controller | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Excitation system type AREP (Auxiliary Winding Excitation Principle, equivalent PMG) or PMG-om | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Plant should bear the short-circuit in the amount of 3xIn a period of 10s | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Standard air filter | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Alternator with a single bed - IP23 / Insulation class H / H | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Microprocessor control / Control Module | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Output breaker Compact NSX160A 4P Micrologic 2.0 SCHNEIDER ELECTRIC or equivalent | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Welded steel base frame with mounted antivibration elements | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Daily fuel tank welded inside the base frame | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Flexible fuel lines, draining lubricating oil | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Twin silencer exhaust 9dB (A) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Filled and formed the starting battery | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - The user manual (1 copy) in Croatian and English language | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Should be wrapped in protective foil | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - The necessary fluids for work (except fuels) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Actuator engine as a John Deere 4045HF120 or equvalent | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -generator as SDMO AT00911T or equivalent | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -bath for collecting liquid leak | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -prefuel filter to separate water | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -The user guide and maintenance manuals in paper form in Croatian and English language | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -main operating console should be aligned with the IEC directive | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -contact protection of high temperature working parts should be in accordance CE standard | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -a micro processor control / control module as MICS APM303 or equivalent | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -MODBus Communication interface | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -system for remote start | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - A packet of automation (charger, resistor for preheating engines relay 220 / 240V) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -measuring card (U, V, S) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Display to display analog values | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -functions for stopping due to low levels of cooling liquid | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Sound enclosure for indoor or outdoor MOUNTING WITH TANK INCREASED SIZE AND double wall: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Protection stationary and mobile plants from the effects of bad weather and theft with the function of reducing of noise | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Housing should be made of steel reinforcement with steel sides, zinc before painting (inside and outside) with a polyester powder for corrosion protection | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -In purpose of high corrosion protection, in addition to the above, anodized aluminum alloy should be used for making door hinges, a system of flexible seals should be used between elements of the housing | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -In purpose of reduce of noise should have called. "Acoustic foam" with a thickness of 20 to 50mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Hausing should be equipped with doors increased dimensions in order to facilitate access for servicing | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The window for the control should be carried out with safety glass | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -exhaust silencer as "critical silencer" (29 or 40 dB (A)) should be mounted within the housing | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -The Emergency stop should be available inside and outside the housing | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -Sound attenuation should be: 77dB (A) @ 1m, 66dB (A) @ 7m, 95LWA | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -dimension LxWxH: 2602 x 1150 x 1948mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -weight without fuel: 2012kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The capacity of the fuel tank: 825L | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -dimension LxWxH: 2602 x 1150 x 1948mm | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -weight without fuel: 2012kg | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - capacity of the fuel tank: 825L | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Diesel generator plant as a type SDMO XP-J110IV Montana Express or equivalent. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Offer: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | set | 1 | 145000 | 145000 | 0 | 0 |  | 0 | 1 | 145000 |  |  | 0 | [24 empty] | 1 | 145000 | 145000 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1 | 145000 |  | 1 | 145000 | 145000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.1.2 | Delivery, installation and commissioning of the DEA system to a prepared site (inlet and outlet cables), prepared concrete (or equivalent) base. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| The item includes: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -all necessary fluids to operate (oil, coolant, except fuels). | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| and delivery and unloading with a crane or forklift, and fixing anchor bolts. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - merger with all mutual, previously deposited, lines to the full functionality of the plant, including the connection to FeZn grounding strap. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -triali work (manual and automatic remote switching) | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -with the plant is delivered user's and maintenance manual in English and Croatian language, the factory test report and Croatian certificates. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| -making the Minutes of the handover. | set | 1 | 7000 | 7000 | 0 | 0 |  | 0 | 1 | 7000 |  |  | 0 | [33 empty] | 1 | 7000 | 7000 | 1 | 7000 |  | 1 | 7000 | 7000
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.1.3 | Supply, delivery and pouring diesel fuel for testing aggregate operation, the amount min. 30 liters. | set | 1 | 1200 | 1200 | 0 | 0 |  | 0 | 1 | 1200 |  |  | 0 | [30 empty] | 2.8 | 1200 | 3360 | 1.7 | 1200 | 2040 | 4.5 | 5400 |  | 4.5 | 1200 | 5400
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.1 | Generator station TOTAL |  |  |  | 153200 |  | 0 |  | 0 |  | 153200 |  |  | 0 | [23 empty] | 0 |  |  | 145000 |  |  | 0 |  |  | 3360 |  |  | 9040 | 0 | 157400 |  | 0 | 0 | 157400
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2 | Main power distribution | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.1 | Delivery and installation of the main stand-alone control cabinet layout tags GRO, made of polyester, with full double doors equipped with a type lock and key, mounting plate, DIN rail, canopy, sealing washer to the bottom of the closet and a standard polyester base height h = 900mm, protect min. IP54, dimensions min. 1500 × 1250 × 420mm (H x W x D), as a type of PLA Thalassa "Schneider" or equivalent. The cabinet is installed below specified equipment type "Schneider" or equivalent, as follows | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • MCCB rated current up to 160A, equipped with electronic protection unit Micrologic 5.2A, leakage module 300mA and MX voltage trigger, 4P4D as type NSX160B or equivalent | pcs | 1 | 5000 | 5000 | 0 | 0 |  | 0 | 1 | 5000 |  |  | 0 | [30 empty] | 1 | 5000 | 5000 |  |  |  | 1 | 5000 |  | 1 | 5000 | 5000
| • surge arresters type 2 + 3, 40 / 15kA, 4P, for TN-S system, complete with changing cartridges | pcs | 1 | 2500 | 2500 | 0 | 0 |  | 0 | 1 | 2500 |  |  | 0 | [30 empty] | 1 | 2500 | 2500 |  |  |  | 1 | 2500 |  | 1 | 2500 | 2500
| • Percussion mushroom push button for the door (or housing) closet, with 1xCO contact 230V, red, min. IP55 | pcs | 1 | 2000 | 2000 | 0 | 0 |  | 0 | 1 | 2000 |  |  | 0 | [30 empty] | 1 | 2000 | 2000 |  |  |  | 1 | 2000 |  | 1 | 2000 | 2000
| • MCCB rated current up to 100A, equipped with electronic protection unit Micrologic 5.2A, 3P3D as type NSX100F or equivalent | pcs | 1 | 350 | 350 | 0 | 0 |  | 0 | 1 | 350 |  |  | 0 | [30 empty] | 1 | 350 | 350 |  |  |  | 1 | 350 |  | 1 | 350 | 350
| • MCCB rated current up to 100A, equipped with thermal-magnetic protection unit TM-D 40A, 3P3D as type NSX100F or equivalent | pcs | 1 | 1600 | 1600 | 0 | 0 |  | 0 | 1 | 1600 |  |  | 0 | [30 empty] | 1 | 1600 | 1600 |  |  |  | 1 | 1600 |  | 1 | 1600 | 1600
| • circuit breaker rated current C40A / 3p as type iC60N or equivalent | pcs | 2 | 1600 | 3200 | 0 | 0 |  | 0 | 2 | 3200 |  |  | 0 | [30 empty] | 2 | 1600 | 3200 |  |  |  | 2 | 3200 |  | 2 | 1600 | 3200
| • circuit breaker rated current C32A / 3p as type iC60N or equivalent | pcs | 2 | 600 | 1200 | 0 | 0 |  | 0 | 2 | 1200 |  |  | 0 | [30 empty] | 2 | 600 | 1200 |  |  |  | 2 | 1200 |  | 2 | 600 | 1200
| • circuit breaker rated current C25A / 3p as type iC60N or equivalent | pcs | 2 | 170 | 340 | 0 | 0 |  | 0 | 2 | 340 |  |  | 0 | [30 empty] | 1 | 170 | 170 |  |  |  | 1 | 170 |  | 1 | 170 | 170
| • circuit breaker rated current C16A / 3p as type iC60N or equivalent | pcs | 6 | 700 | 4200 | 0 | 0 |  | 0 | 6 | 4200 |  |  | 0 | [30 empty] | 5 | 700 | 3500 |  |  |  | 5 | 3500 |  | 5 | 700 | 3500
| • circuit breaker rated current C16A / 4p as type iC60N or equivalent, equipped with a Vigi differential module 30mA / 4p | pcs | 2 | 140 | 280 | 0 | 0 |  | 0 | 2 | 280 |  |  | 0 | [30 empty] | 2 | 140 | 280 |  |  |  | 2 | 280 |  | 2 | 140 | 280
| • circuit breaker rated current C10A / 3p as type iC60N or equivalent | pcs | 1 | 40 | 40 | 0 | 0 |  | 0 | 1 | 40 |  |  | 0 | [30 empty] | 1 | 40 | 40 |  |  |  | 1 | 40 |  | 1 | 40 | 40
| • circuit breaker rated current C16A / 1p as type iC60N or equivalent | pcs | 2 | 40 | 80 | 0 | 0 |  | 0 | 2 | 80 |  |  | 0 | [30 empty] | 0 | 40 | 0 |  |  |  | 0 | 0 |  | 0 | 40 | 0
| • circuit breaker rated current C10A / 1p as type iC60N or equivalent | pcs | 2 | 40 | 80 | 0 | 0 |  | 0 | 2 | 80 |  |  | 0 | [30 empty] | 2 | 40 | 80 |  |  |  | 2 | 80 |  | 2 | 40 | 80
| • circuit breaker rated current B10A / 1p as type iC60N or equivalent | pcs | 2 | 40 | 80 | 0 | 0 |  | 0 | 2 | 80 |  |  | 0 | [30 empty] | 2 | 40 | 80 |  |  |  | 2 | 80 |  | 2 | 40 | 80
| • circuit breaker rated current B6A / 1p as type iC60N or equivalent | pcs | 1 | 40 | 40 | 0 | 0 |  | 0 | 1 | 40 |  |  | 0 | [30 empty] | 1 | 40 | 40 |  |  |  | 1 | 40 |  | 1 | 40 | 40
| • circuit breaker rated current B4A / 1p as type iC60N or equivalent | pcs | 1 | 40 | 40 | 0 | 0 |  | 0 | 1 | 40 |  |  | 0 | [30 empty] | 1 | 40 | 40 |  |  |  | 1 | 40 |  | 1 | 40 | 40
| • circuit breaker rated current B2A / 1p as type iC60N or equivalent | pcs | 4 | 40 | 160 | 0 | 0 |  | 0 | 4 | 160 |  |  | 0 | [30 empty] | 4 | 40 | 160 |  |  |  | 4 | 160 |  | 4 | 40 | 160
| • cam switch 40A / 3p for inner cabinet doors | pcs | 1 | 450 | 450 | 0 | 0 |  | 0 | 1 | 450 |  |  | 0 | [30 empty] | 1 | 450 | 450 |  |  |  | 1 | 450 |  | 1 | 450 | 450
| • cam switch 25A / 1p for inner cabinet doors | pcs | 6 | 400 | 2400 | 0 | 0 |  | 0 | 6 | 2400 |  |  | 0 | [30 empty] | 6 | 400 | 2400 |  |  |  | 6 | 2400 |  | 6 | 400 | 2400
| • rippled election switch 1-0-2, 12A / 1p, the inner cabinet doors | pcs | 1 | 340 | 340 | 0 | 0 |  | 0 | 1 | 340 |  |  | 0 | [30 empty] | 1 | 340 | 340 |  |  |  | 1 | 340 |  | 1 | 340 | 340
| • installation coupler 25A / 3P / 230V | pcs | 2 | 400 | 800 | 0 | 0 |  | 0 | 2 | 800 |  |  | 0 | [30 empty] | 2 | 400 | 800 |  |  |  | 2 | 800 |  | 2 | 400 | 800
| • signal light 2A / 230V green | pcs | 3 | 45 | 135 | 0 | 0 |  | 0 | 3 | 135 |  |  | 0 | [30 empty] | 3 | 45 | 135 |  |  |  | 3 | 135 |  | 3 | 45 | 135
| • light switch (luxomat) 2-2000lx, complete with outdoor sensor in the protection min. IP54 | pcs | 1 | 320 | 320 | 0 | 0 |  | 0 | 1 | 320 |  |  | 0 | [30 empty] | 1 | 320 | 320 |  |  |  | 1 | 320 |  | 1 | 320 | 320
| • thermostat temperature control TS140 or equivalent | pcs | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 0 | 400 | 0 |  |  |  | 0 | 0 |  | 0 | 400 | 0
| • higrotermostat temperature control or HS3000 or equivalent | pcs | 1 | 2200 | 2200 | 0 | 0 |  | 0 | 1 | 2200 |  |  | 0 | [30 empty] | 1 | 2200 | 2200 |  |  |  | 1 | 2200 |  | 1 | 2200 | 2200
| • resistive heater CR 90W / 230V / 50Hz | pcs | 1 | 1200 | 1200 | 0 | 0 |  | 0 | 1 | 1200 |  |  | 0 | [30 empty] | 1 | 1200 | 1200 |  |  |  | 1 | 1200 |  | 1 | 1200 | 1200
| • Light cabinet 11W / 230V, with magnet | pcs | 1 | 220 | 220 | 0 | 0 |  | 0 | 1 | 220 |  |  | 0 | [30 empty] | 1 | 220 | 220 |  |  |  | 1 | 220 |  | 1 | 220 | 220
| • terminal blocks up to 95mm2 | pcs | 4 | 110 | 440 | 0 | 0 |  | 0 | 4 | 440 |  |  | 0 | [30 empty] | 4 | 110 | 440 |  |  |  | 4 | 440 |  | 4 | 110 | 440
| • terminal blocks up to 35mm2 | pcs | 3 | 22 | 66 | 0 | 0 |  | 0 | 3 | 66 |  |  | 0 | [30 empty] | 3 | 22 | 66 |  |  |  | 3 | 66 |  | 3 | 22 | 66
| • terminal blocks to 10-16mm2 | pcs | 15 | 20 | 300 | 0 | 0 |  | 0 | 15 | 300 |  |  | 0 | [30 empty] | 15 | 20 | 300 |  |  |  | 15 | 300 |  | 15 | 20 | 300
| • terminal blocks up to 6mm2 | pcs | 15 | 10 | 150 | 0 | 0 |  | 0 | 15 | 150 |  |  | 0 | [30 empty] | 15 | 10 | 150 |  |  |  | 15 | 150 |  | 15 | 10 | 150
| • terminal blocks up to 2.5mm2 | pcs | 30 | 7 | 210 | 0 | 0 |  | 0 | 30 | 210 |  |  | 0 | [30 empty] | 30 | 7 | 210 |  |  |  | 30 | 210 |  | 30 | 7 | 210
| • sealing plate to the bottom of the closet and entry pipes and cables | pcs | 1 | 300 | 300 | 0 | 0 |  | 0 | 1 | 300 |  |  | 0 | [30 empty] | 0 | 300 | 0 |  |  |  | 0 | 0 |  | 0 | 300 | 0
| • grid ventilation for IP54 protection | pcs | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 0 | 400 | 0 |  |  |  | 0 | 0 |  | 0 | 400 | 0
| • L1, L2 and L3 insulated needle-pole bus, N and PE bus, copper bus bars, insulators, terminals, conductors for wiring, connecting material, labels, nameplates, screws and fittings, equipment carriers, cover plates, with lock mask and keys and other small materials. | [12 empty] | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Offer: | [12 empty] | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
|  | set | 1 | 720 | 720 | 0 | 0 |  | 0 | 1 | 720 |  |  | 0 | [30 empty] | 1 | 720 | 720 |  |  |  | 1 | 720 |  | 1 | 720 | 720
[14 empty] | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.2.2 | Supply and laying of 1 kV power cables with flexible HERP insulation and PVC sheath, according to the lower specification. The cables are laid in the previously passed PVC pipes in ducts. The sentence included mutually connecting cable with all necessary equipment to full functionality. | [12 empty] | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
| 5xFG70R 1×95mm2 | m' | 20 | 405 | 8100 | 0 | 0 |  | 0 | 20 | 8100 |  |  | 0 | [27 empty] | 25 | 405 | 10125 |  | 405 | 0 |  |  |  | 25 | 10125 |  | 25 | 405 | 10125
| 5xFG70R 1×35mm2 | m' | 90 | 185 | 16650 | 0 | 0 |  | 0 | 90 | 16650 |  |  | 0 | [24 empty] | 89 | 185 | 16465 |  | 0 | 0 |  | 185 | 0 |  |  |  | 89 | 16465 |  | 89 | 185 | 16465
| FG70R 5×10mm2 | m' | 240 | 55 | 13200 | 0 | 0 |  | 0 | 240 | 13200 |  |  | 0 | [24 empty] | 206 | 55 | 11330 |  | 0 | 0 |  | 55 | 0 |  |  |  | 206 | 11330 |  | 206 | 55 | 11330
| FG70R 5×6mm2 | m' | 20 | 43 | 860 | 0 | 0 |  | 0 | 20 | 860 |  |  | 0 | [31 empty] | 43 | 0 |  |  |  | 0 | 0 |  | 0 | 43 | 0
| FG70R 3×1,5mm2 | m' | 50 | 11 | 550 | 0 | 0 |  | 0 | 50 | 550 |  |  | 0 | [31 empty] | 11 | 0 |  |  |  | 0 | 0 |  | 0 | 11 | 0
| FG70R 5×2,5mm2 | m' | 50 | 22 | 1100 | 0 | 0 |  | 0 | 50 | 1100 |  |  | 0 | [31 empty] | 22 | 0 |  |  |  | 0 | 0 |  | 0 | 22 | 0
| NHXH E30 2×1,5mm2 | m' | 20 | 25 | 500 | 0 | 0 |  | 0 | 20 | 500 |  |  | 0 | [27 empty] | 20 | 25 | 500 |  | 25 | 0 |  |  |  | 20 | 500 |  | 20 | 25 | 500
| NYY 16x1,5mm2 | m' | 100 | 39 | 3900 | 0 | 0 |  | 0 | 100 | 3900 |  |  | 0 | [27 empty] | 100 | 39 | 3900 |  | 39 | 0 |  |  |  | 100 | 3900 |  | 100 | 39 | 3900
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.3 | Supply and laying of double wall corrugated PVC / HDPE pipes in pre-prepared earthen trench to the lower specification. The pipes must be made of high density polyethylene, with a corrugated outer wall and an inner smooth, suitable for direct burial in the ground and concrete. All pipe to perform a standard couplings. All segments laid pipes must be equipped with a trailer for broaching metal cable. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • 1 × PVC Ø50mm | m' | 25 | 28 | 700 | 0 | 0 |  | 0 | 25 | 700 |  |  | 0 | [27 empty] | 104 | 28 | 2912 |  | 0 | 0 |  |  |  | 104 | 2912 |  | 104 | 28 | 2912
| • 2 × PVC Ø50mm | m' | 30 | 52 | 1560 | 0 | 0 |  | 0 | 30 | 1560 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 52 | 0
| • 3 × PVC Ø50mm | m' | 30 | 80 | 2400 | 0 | 0 |  | 0 | 30 | 2400 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 80 | 0
| • 1 × PVC Ø110mm | m' | 30 | 40 | 1200 | 0 | 0 |  | 0 | 30 | 1200 |  |  | 0 | [24 empty] | 285 | 40 | 11400 | 140 | 40 | 5600 |  | 0 | 0 |  |  |  | 425 | 17000 |  | 425 | 40 | 17000
| • 2 × PVC Ø110mm | m' | 90 | 80 | 7200 | 0 | 0 |  | 0 | 90 | 7200 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 80 | 0
| • 3 × PVC Ø110mm | m' | 35 | 120 | 4200 | 0 | 0 |  | 0 | 35 | 4200 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 120 | 0
| • 4 × PVC Ø110mm | m' | 40 | 150 | 6000 | 0 | 0 |  | 0 | 40 | 6000 |  |  | 0 | [24 empty] | 15 | 150 | 2250 |  | 0 | 0 |  | 40 | 0 |  |  |  | 15 | 2250 |  | 15 | 150 | 2250
| • 1 × PVC Ø160mm | m' | 20 | 60 | 1200 | 0 | 0 |  | 0 | 20 | 1200 |  |  | 0 | [24 empty] | 10 | 60 | 600 |  | 0 | 0 |  | 20 | 0 |  |  |  | 10 | 600 |  | 10 | 60 | 600
[14 empty] | 0 | [25 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.2.4 | Preparation and connect the power cable to 5x35mm2 the distributor housings, complete with all necessary equipment and works. Calculation per piece unilaterally. | set | 25 | 195 | 4875 | 0 | 0 |  | 0 | 25 | 4875 |  |  | 0 | [27 empty] | 25 | 195 | 4875 |  | 0 | 0 |  |  |  | 25 | 4875 |  | 25 | 195 | 4875
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.5 | Delivery and installation of 1 kV underground cable connectors for power cables type Raich "TYCO" or equivalent, for the following cables: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • 5x35 Cu | pcs | 2 | 360 | 720 | 0 | 0 |  | 0 | 2 | 720 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 360 | 0
| • 5x10 Cu | pcs | 3 | 360 | 1080 | 0 | 0 |  | 0 | 3 | 1080 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 360 | 0
| • 5x6 Cu | pcs | 2 | 300 | 600 | 0 | 0 |  | 0 | 2 | 600 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 300 | 0
| Offer: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.6 | Delivery and installation of a full metal cable channel made of stainless steel, complete with cover and mounting accessories. The channel dimensions of 100 / 50mm. The channel is mounted on the front of the building for staff from the floor to the position of connection sockets and GTDI. | m' | 4 | 200 | 800 | 0 | 0 |  | 0 | 4 | 800 |  |  | 0 | [30 empty] | 3 | 200 | 600 |  |  |  | 3 | 600 |  | 3 | 200 | 600
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.7 | Supply and installation of industrial plug IEC 309 3P + N + PE 16 (32) A / 400V. The plug is installed on the power cable to the building for staff. The plug must be protection min. IP67. | pcs | 1 | 200 | 200 | 0 | 0 |  | 0 | 1 | 200 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 200 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.8 | Production of construction pits for installation pedestal cabinets GRO, RO.PK, RO.PV and RO.O.V After mounting surface to its original condition and the excess material disposed. The sentence included all the material and labor for excavation and installation of stands, to full functionality. | pcs | 4 | 750 | 3000 | 0 | 0 |  | 0 | 4 | 3000 |  |  | 0 | [33 empty] | 4 | 750 | 3000 | 4 | 3000 |  | 4 | 750 | 3000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.9 | Delivery and installation of rigid pipe installation PNT Ø19-22mm on the walls of buildings, complete with brackets and wiring accessories. | m' | 50 | 29 | 1450 | 0 | 0 |  | 0 | 50 | 1450 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 29 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2.10 | Supply, installation and connection of the intermediate disconnecting push button for emergency switching off power to protect min IP55, red color, with removable front slides. Push button must be equipped contact 1xC / O 2A / 230V. | pcs | 1 | 300 | 300 | 0 | 0 |  | 0 | 1 | 300 |  |  | 0 | [27 empty] | 1 | 300 | 300 |  | 0 | 0 |  |  |  | 1 | 300 |  | 1 | 300 | 300
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.2 | Main power distribution TOTAL |  |  |  | 114586 |  | 0 |  | 0 |  | 114586 |  |  | 0 | [23 empty] | 0 |  |  | 42045 |  |  | 28212 |  |  | 30791 |  |  | 3000 | 0 | 104048 |  | 0 | 0 | 104048
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3 | Electric installation of building for personnel | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.1 | Delivery and installation of wall the intermediate control cabinet layout tags RO.K, made of PVC, with full door equipped with a type lock and DIN rails. The cabinet is installed below specified equipment type "Schneider" or equivalent, as follows: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • current protection switch 40A / 0.03 / 4p | pcs | 1 | 1350 | 1350 | 0 | 0 |  | 0 | 1 | 1350 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 1350 | 0
| • circuit breaker rated current C16A / 1p as type iC60N or equivalent | pcs | 1 | 35 | 35 | 0 | 0 |  | 0 | 1 | 35 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 35 | 0
| • circuit breaker rated current B16A / 1p as type iC60N or equivalent | pcs | 6 | 35 | 210 | 0 | 0 |  | 0 | 6 | 210 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 35 | 0
| • circuit breaker rated current B10A / 1p as type iC60N or equivalent | pcs | 3 | 35 | 105 | 0 | 0 |  | 0 | 3 | 105 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 35 | 0
| • circuit breaker rated current B6A / 1p as type iC60N or equivalent | pcs | 1 | 35 | 35 | 0 | 0 |  | 0 | 1 | 35 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 35 | 0
| • terminal blocks up to 6mm2 | pcs | 4 | 10 | 40 | 0 | 0 |  | 0 | 4 | 40 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 10 | 0
| • terminal blocks up to 2.5mm2 | pcs | 15 | 10 | 150 | 0 | 0 |  | 0 | 15 | 150 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 10 | 0
| • L1, L2 and L3 insulated needle-pole bus, N and PE busbars, insulators, terminals, conductors for wiring, connecting material, labels, nameplates, screws and fittings, equipment carriers, cover plates, lock the mask and keys and other small materials. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Offer: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | set | 1 | 600 | 600 | 0 | 0 |  | 0 | 1 | 600 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 600 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.2 | Supply and installation of power cables with PVC insulation and PVC sheath, according to the lower specification. The cables are laid in the previously passed PVC pipes or PVC tiles. The sentence included mutually connecting cable with all necessary equipment to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| NYM 3x1,5mm2 | m' | 40 | 12 | 480 | 0 | 0 |  | 0 | 40 | 480 |  |  | 0 | [27 empty] | 32 | 12 | 384 |  | 0 | 0 |  |  |  | 32 | 384 |  | 32 | 12 | 384
| NYM 3x2,5mm2 | m' | 250 | 15 | 3750 | 0 | 0 |  | 0 | 250 | 3750 |  |  | 0 | [30 empty] | 28 | 15 | 420 |  |  |  | 28 | 420 |  | 28 | 15 | 420
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.3 | Supply and installation of PVC cable channel dim. Approx 100x60cm. The channels are placed in the building for staff in the ceiling. The sentence included fittings, covers and mounting accessories. | m' | 30 | 110 | 3300 | 0 | 0 |  | 0 | 30 | 3300 |  |  | 0 | [27 empty] | 22 | 110 | 2420 |  | 0 | 0 |  |  |  | 22 | 2420 |  | 22 | 110 | 2420
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.4 | Supply and installation of PNT pipes Ø20mm, complete with brackets and mounts. The pipes are laid in the building for staff in the vertical divorce. | m' | 25 | 30 | 750 | 0 | 0 |  | 0 | 25 | 750 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 30 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.5 | Supply and installation of PVC trunking. The channels are placed in the building for staff above the desk. The sentence included fittings, covers and mounting accessories. | m' | 4 | 100 | 400 | 0 | 0 |  | 0 | 4 | 400 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 100 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.6 | Supply, installation and connection of the double socket 16A / 230V 2P + E for installation in trunking. | pcs | 3 | 120 | 360 | 0 | 0 |  | 0 | 3 | 360 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 120 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.7 | Supply, installation and connection of plaster socket 16A / 230V 2P + E for installation in the building for personnel | pcs | 5 | 90 | 450 | 0 | 0 |  | 0 | 5 | 450 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 90 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.8 | Supply, installation and connection of plaster switches 10A / 230V 1P for installation in the building for personnel | pcs | 6 | 90 | 540 | 0 | 0 |  | 0 | 6 | 540 |  |  | 0 | [27 empty] | 1 | 90 | 90 |  | 0 | 0 |  |  |  | 1 | 90 |  | 1 | 90 | 90
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.9 | Supply, installation and connection of Vanity ceiling lamps with shiny grid and fluorescent light sources 2x35W, as type wedge "INDORA" or equivalent. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Offer: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | pcs | 1 | 540 | 540 | 0 | 0 |  | 0 | 1 | 540 |  |  | 0 | [33 empty] | 2 | 540 | 1080 | 2 | 1080 |  | 2 | 540 | 1080
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.10 | Supply, installation and connection of Vanity ceiling lamps in protecting min. IP44, insulation class II, with saving light source. | pcs | 5 | 300 | 1500 | 0 | 0 |  | 0 | 5 | 1500 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 300 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.11 | Supply, installation and connection of Vanity wall lamps in protecting min. IP55, with saving light source. | pcs | 1 | 320 | 320 | 0 | 0 |  | 0 | 1 | 320 |  |  | 0 | [27 empty] | 1 | 320 | 320 |  | 0 | 0 |  |  |  | 1 | 320 |  | 1 | 320 | 320
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.12 | Delivery and installation of emergency lighting autonomy 1 hour of work, with a fluorescent light source 1x8W and pictogram "EXIT". The lamp must be in preparatory compound. | m' | 1 | 450 | 450 | 0 | 0 |  | 0 | 1 | 450 |  |  | 0 | [27 empty] | 1 | 450 | 450 |  | 0 | 0 |  |  |  | 1 | 450 |  | 1 | 450 | 450
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.13 | Connecting the mechanical consumer to previously laid the power cable, including water heater, pump hot water, wardrobe R, S and air unit. The sentence included all papers and accessories to full functionality. | pcs | 5 | 100 | 500 | 0 | 0 |  | 0 | 5 | 500 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 100 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.3.14 | Delivery and installation of wall the intermediate control cabinet layout marking R, S, made of steel, with full door equipped with a type lock. On the closet door is installed below specified equipment for signaling the state of the basin for leachate or closet PSF, as follows: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Push-button for switching off the pump 2A / 230V, red | pcs | 1 | 600 | 600 | 0 | 0 |  | 0 | 1 | 600 |  |  | 0 | [30 empty] | 1 | 600 | 600 |  |  |  | 1 | 600 |  | 1 | 600 | 600
| • signal light 2A / 230V red | pcs | 3 | 80 | 240 | 0 | 0 |  | 0 | 3 | 240 |  |  | 0 | [30 empty] | 3 | 80 | 240 |  |  |  | 3 | 240 |  | 3 | 80 | 240
| • signal light 2A / 230V yellow | pcs | 1 | 80 | 80 | 0 | 0 |  | 0 | 1 | 80 |  |  | 0 | [30 empty] | 1 | 80 | 80 |  |  |  | 1 | 80 |  | 1 | 80 | 80
| • beeper buzzer to signal alarm | pcs | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 0 | 400 | 0 |  |  |  | 0 | 0 |  | 0 | 400 | 0
| • guides for wiring, fittings and similar | pcs | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 1 | 400 | 400 |  |  |  | 1 | 400 |  | 1 | 400 | 400
| Offer: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
|  | set | 1 | 1720 | 1720 | 0 | 0 |  | 0 | 1 | 1720 |  |  | 0 | [31 empty] | 1720 | 0 |  |  |  | 0 | 0 |  | 0 | 1720 | 0
[14 empty] | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.3 | Electric installation of building for personnel TOTAL |  |  |  | 19305 |  | 0 |  | 0 |  | 19305 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3664 |  |  | 1740 |  |  | 1080 | 0 | 6484 |  | 0 | 0 | 6484
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.4 | Electric installation of garage for compactor | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.4.1 | Delivery and installation of wall the intermediate control cabinet layout tags RO.gk, made of steel, with full door equipped with a type lock and DIN rails. Wardrobe approx. 800x600x230mm, the protection IP55. The cabinet is installed below specified equipment type "Schneider" or equivalent, as follows: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • current protection switch 63A / 0.03 / 4p | pcs | 1 | 510 | 510 | 0 | 0 |  | 0 | 1 | 510 |  |  | 0 | [30 empty] | 1 | 510 | 510 |  |  |  | 1 | 510 |  | 1 | 510 | 510
| • break switch 63A / 3p with Shunt | pcs | 1 | 2300 | 2300 | 0 | 0 |  | 0 | 1 | 2300 |  |  | 0 | [30 empty] | 1 | 2300 | 2300 |  |  |  | 1 | 2300 |  | 1 | 2300 | 2300
| • circuit breaker rated current C16A / 3p as type iC60N or equivalent | pcs | 5 | 110 | 550 | 0 | 0 |  | 0 | 5 | 550 |  |  | 0 | [30 empty] | 4 | 110 | 440 |  |  |  | 4 | 440 |  | 4 | 110 | 440
| • circuit breaker rated current C16A / 1p as type iC60N or equivalent | pcs | 3 | 32 | 96 | 0 | 0 |  | 0 | 3 | 96 |  |  | 0 | [30 empty] | 0 | 32 | 0 |  |  |  | 0 | 0 |  | 0 | 32 | 0
| • circuit breaker rated current B16A / 1p as type iC60N or equivalent | pcs | 2 | 30 | 60 | 0 | 0 |  | 0 | 2 | 60 |  |  | 0 | [30 empty] | 4 | 30 | 120 |  |  |  | 4 | 120 |  | 4 | 30 | 120
| • circuit breaker rated current B10A / 1p as type iC60N or equivalent | pcs | 4 | 30 | 120 | 0 | 0 |  | 0 | 4 | 120 |  |  | 0 | [30 empty] | 4 | 30 | 120 |  |  |  | 4 | 120 |  | 4 | 30 | 120
| • circuit breaker rated current C10A / 3p as type iC60N or equivalent | pcs | 3 | 105 | 315 | 0 | 0 |  | 0 | 3 | 315 |  |  | 0 | [30 empty] | 1 | 105 | 105 |  |  |  | 1 | 105 |  | 1 | 105 | 105
| • circuit breaker rated current B6A / 1p as type iC60N or equivalent | pcs | 2 | 30 | 60 | 0 | 0 |  | 0 | 2 | 60 |  |  | 0 | [30 empty] | 2 | 30 | 60 |  |  |  | 2 | 60 |  | 2 | 30 | 60
| • circuit breaker rated current B2A / 1p as type iC60N or equivalent | pcs | 4 | 30 | 120 | 0 | 0 |  | 0 | 4 | 120 |  |  | 0 | [30 empty] | 4 | 30 | 120 |  |  |  | 4 | 120 |  | 4 | 30 | 120
| • signal light 2A / 230V green | pcs | 3 | 40 | 120 | 0 | 0 |  | 0 | 3 | 120 |  |  | 0 | [30 empty] | 3 | 40 | 120 |  |  |  | 3 | 120 |  | 3 | 40 | 120
| • Percussion mushroom push button for the door (or housing) closet, with 1xCO contact 230V, red, min. IP55 | pcs | 1 | 330 | 330 | 0 | 0 |  | 0 | 1 | 330 |  |  | 0 | [30 empty] | 1 | 330 | 330 |  |  |  | 1 | 330 |  | 1 | 330 | 330
| • break switch 25A / 1p / 230V for cabinet doors | pcs | 3 | 430 | 1290 | 0 | 0 |  | 0 | 3 | 1290 |  |  | 0 | [30 empty] | 3 | 430 | 1290 |  |  |  | 3 | 1290 |  | 3 | 430 | 1290
| • socket 16A 230V 2P+E for cabinet IEC 309 | pcs | 1 | 200 | 200 | 0 | 0 |  | 0 | 1 | 200 |  |  | 0 | [30 empty] | 1 | 200 | 200 |  |  |  | 1 | 200 |  | 1 | 200 | 200
| • thermostat temperature control TS140 or equivalent | pcs | 1 | 380 | 380 | 0 | 0 |  | 0 | 1 | 380 |  |  | 0 | [30 empty] | 0 | 380 | 0 |  |  |  | 0 | 0 |  | 0 | 380 | 0
| • higrotermostat temperature control or HS3000 equivalent | pcs | 1 | 3000 | 3000 | 0 | 0 |  | 0 | 1 | 3000 |  |  | 0 | [30 empty] | 1 | 3000 | 3000 |  |  |  | 1 | 3000 |  | 1 | 3000 | 3000
| • resistive heater CR 90W / 230V / 50Hz | pcs | 1 | 950 | 950 | 0 | 0 |  | 0 | 1 | 950 |  |  | 0 | [30 empty] | 1 | 950 | 950 |  |  |  | 1 | 950 |  | 1 | 950 | 950
| • Light cabinet 11W / 230V, with magnet | pcs | 1 | 230 | 230 | 0 | 0 |  | 0 | 1 | 230 |  |  | 0 | [30 empty] | 1 | 230 | 230 |  |  |  | 1 | 230 |  | 1 | 230 | 230
| • terminal blocks up to 10mm2 | pcs | 4 | 15 | 60 | 0 | 0 |  | 0 | 4 | 60 |  |  | 0 | [30 empty] | 4 | 15 | 60 |  |  |  | 4 | 60 |  | 4 | 15 | 60
| • terminal blocks up to 2.5mm2 | pcs | 15 | 7 | 105 | 0 | 0 |  | 0 | 15 | 105 |  |  | 0 | [30 empty] | 15 | 7 | 105 |  |  |  | 15 | 105 |  | 15 | 7 | 105
| • L1, L2 and L3 insulated needle-pole bus, N and PE busbars, insulators, terminals, conductors for wiring, connecting material, labels, nameplates, screws and fittings, equipment carriers, cover plates, lock the mask and keys and other small materials. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Offer: | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | set | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 1 | 400 | 400 |  |  |  | 1 | 400 |  | 1 | 400 | 400
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.4.2 | Supply and laying of 1 kV power cables with flexible HERP insulation and PVC sheath, according to the lower specification. The cables are laid in the previously passed PK channels and PNT pipes in the garage for the compactor. The sentence included mutually connecting cable with all necessary equipment to full functionality. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • FG70R 3x1,5mm2 | m' | 120 | 11 | 1320 | 0 | 0 |  | 0 | 120 | 1320 |  |  | 0 | [30 empty] | 120 | 11 | 1320 |  |  |  | 120 | 1320 |  | 120 | 11 | 1320
| • FG70R 3x2,5mm2 | m' | 90 | 15 | 1350 | 0 | 0 |  | 0 | 90 | 1350 |  |  | 0 | [30 empty] | 90 | 15 | 1350 |  |  |  | 90 | 1350 |  | 90 | 15 | 1350
| • FG70R 5x2,5mm2 | m' | 90 | 20 | 1800 | 0 | 0 |  | 0 | 90 | 1800 |  |  | 0 | [30 empty] | 90 | 20 | 1800 |  |  |  | 90 | 1800 |  | 90 | 20 | 1800
| • NHXH E30 2×1,5mm2 | m' | 25 | 22 | 550 | 0 | 0 |  | 0 | 25 | 550 |  |  | 0 | [30 empty] | 25 | 22 | 550 |  |  |  | 25 | 550 |  | 25 | 22 | 550
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.4.3 | Supply and installation of perforated sheet metal cable channel (PKK) in size to a standard wall mounts. The channels are laid on the walls of the garage in the ceiling. The sentence included all the necessary mounting hardware, fittings and the like. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • PKK 100/50mm | m' | 40 | 105 | 4200 | 0 | 0 |  | 0 | 40 | 4200 |  |  | 0 | [30 empty] | 40 | 105 | 4200 |  |  |  | 40 | 4200 |  | 40 | 105 | 4200
| • PKK 50/35mm | m' | 30 | 80 | 2400 | 0 | 0 |  | 0 | 30 | 2400 |  |  | 0 | [30 empty] | 10 | 80 | 800 |  |  |  | 10 | 800 |  | 10 | 80 | 800
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.4 | Supply and installation of PNT pipes Ø20mm, complete with brackets and mounts. The pipes are laid in a garage in the vertical distribution | m' | 70 | 23 | 1610 | 0 | 0 |  | 0 | 70 | 1610 |  |  | 0 | [30 empty] | 65 | 23 | 1495 |  |  |  | 65 | 1495 |  | 65 | 23 | 1495
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.5 | Supply and installation of bus Equipotential visible variations. The bus must be able to accept the tape 30x3,5mm and 10 guide section 6-16mm2. | pcs | 1 | 310 | 310 | 0 | 0 |  | 0 | 1 | 310 |  |  | 0 | [30 empty] | 1 | 310 | 310 |  |  |  | 1 | 310 |  | 1 | 310 | 310
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.6 | Supply, installation and connection of plaster socket 16A / 230V 2P + E for installation in the garage. | pcs | 5 | 90 | 450 | 0 | 0 |  | 0 | 5 | 450 |  |  | 0 | [30 empty] | 4 | 90 | 360 |  |  |  | 4 | 360 |  | 4 | 90 | 360
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.7 | Supply, installation and connection of plaster socket 16A / 230V 3P + N + PE for installation in the garage. | pcs | 5 | 145 | 725 | 0 | 0 |  | 0 | 5 | 725 |  |  | 0 | [30 empty] | 4 | 145 | 580 |  |  |  | 4 | 580 |  | 4 | 145 | 580
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.8 | Supply, installation and connection of Vanity ceiling lamps in protecting min. IP66 and LED light sources 1x59W as type FUTURA 2.5ft PC Al 8000/840 or equivalent. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
| Offer: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
|  | pcs | 9 | 900 | 8100 | 0 | 0 |  | 0 | 9 | 8100 |  |  | 0 | [30 empty] | 9 | 900 | 8100 |  |  |  | 9 | 8100 |  | 9 | 900 | 8100
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.9 | Delivery and installation of emergency lighting autonomy 1 hour of work, with a fluorescent light source 1x11W and pictogram "EXIT". The lamp has to be in the preliminary junction, protection IP55. | m' | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 1 | 400 | 400 |  |  |  | 1 | 400 |  | 1 | 400 | 400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.10 | Connecting the mechanical consumer to previously laid the power cable. The sentence included all papers and accessories to full functionality. | pcs | 1 | 400 | 400 | 0 | 0 |  | 0 | 1 | 400 |  |  | 0 | [30 empty] | 1 | 400 | 400 |  |  |  | 1 | 400 |  | 1 | 400 | 400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.11 | Supply, installation and connection of the intermediate disconnecting push button for emergency switching off power to protect min IP55, red color, with removable front slides. Push button must be equipped contact 1xC / O 2A / 230V. | pcs | 1 | 300 | 300 | 0 | 0 |  | 0 | 1 | 300 |  |  | 0 | [30 empty] | 1 | 300 | 300 |  |  |  | 1 | 300 |  | 1 | 300 | 300
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.4.12 | Supply green-yellow guide and performance connectivity conductive parts earthed. In paragraph included all the necessary fittings and works up to full functionality. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
| • H07V-K 1x6mm2 | m' | 50 | 10 | 500 | 0 | 0 |  | 0 | 50 | 500 |  |  | 0 | [30 empty] | 50 | 10 | 500 |  |  |  | 50 | 500 |  | 50 | 10 | 500
| • H07V-K 1x16mm2 | m' | 30 | 20 | 600 | 0 | 0 |  | 0 | 30 | 600 |  |  | 0 | [30 empty] | 30 | 20 | 600 |  |  |  | 30 | 600 |  | 30 | 20 | 600
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.4 | Electric installation of garage for compactor TOTAL |  |  |  | 36211 |  | 0 |  | 0 |  | 36211 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 33525 |  |  |  | 0 | 33525 |  | 0 | 0 | 33525
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.5 | LPS of garage for compactor | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.5.1 | The supply and laying of stainless steel strips P30x3,5mm Rf in the concrete foundation of the garage. All compounds are cleaved and implement a standard cross stainless steel fittings "strip-tape '' and coated with bitumen coating. | m' | 50 | 48 | 2400 | 0 | 0 |  | 0 | 50 | 2400 |  |  | 0 | [27 empty] | 50 | 48 | 2400 | 0 | 48 | 0 |  |  |  | 50 | 2400 |  | 50 | 48 | 2400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [31 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.2 | Creating a branch (lateral lines) with a grounding in the basis, the average length l = 4m stainless steel strip P30x3,5mm by cross-coupling. The compound coated with bitumen. | pcs | 7 | 220 | 1540 | 0 | 0 |  | 0 | 7 | 1540 |  |  | 0 | [27 empty] | 4 | 220 | 880 | 0 | 220 | 0 |  |  |  | 4 | 880 |  | 4 | 220 | 880
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.3 | The implementation of ground available and foreign conductive mass connecting the grounding strap. Compound perform screw, the type coupler or welding, complete with all necessary material. | pcs | 5 | 100 | 500 | 0 | 0 |  | 0 | 5 | 500 |  |  | 0 | [30 empty] | 0 | 100 | 0 | 5 | 100 | 500 | 5 | 500 |  | 5 | 100 | 500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.4 | Supply and laying of main drains LPS made of stainless steel wire Ø8mm on a section of the measurement compounds to the roof (of reception lines). The sentence included and standard stainless steel wall brackets. The length of the drain is an average of 5m. | pcs | 4 | 240 | 960 | 0 | 0 |  | 0 | 4 | 960 |  |  | 0 | [30 empty] | 4 | 240 | 960 |  |  |  | 4 | 960 |  | 4 | 240 | 960
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.5 | Laying the main drain LPS made of stainless steel strips P30x3,5mm the share of measuring compounds to the floor (ground fault). The sentence included and standard stainless steel wall brackets to the wall. Length of the line is Mean 3m. | pcs | 4 | 300 | 1200 | 0 | 0 |  | 0 | 4 | 1200 |  |  | 0 | [30 empty] | 4 | 300 | 1200 |  |  |  | 4 | 1200 |  | 4 | 300 | 1200
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.5 | Supply and installation of vertical type of protection the main drain LPS on the section of the floor to the measurement circuit. The sentence included mounting accessories for installation. | pcs | 4 | 300 | 1200 | 0 | 0 |  | 0 | 4 | 1200 |  |  | 0 | [30 empty] | 4 | 300 | 1200 |  |  |  | 4 | 1200 |  | 4 | 300 | 1200
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.6 | Supply and laying of roofing system clamps - Stainless steel wire Ø8mm on a standard stainless steel roof beams according to the type of roof covering. Compounds perform a standard stainless steel fittings. | m' | 1 | 300 | 300 | 0 | 0 |  | 0 | 1 | 300 |  |  | 0 | [30 empty] | 5.8 | 300 | 1740 |  |  |  | 5.8 | 1740 |  | 5.8 | 300 | 1740
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.7 | Supply of materials and performance measurement circuit by disconnection of cross stainless steel fittings "strip-wire ''. | pcs | 4 | 200 | 800 | 0 | 0 |  | 0 | 4 | 800 |  |  | 0 | [30 empty] | 4 | 200 | 800 |  |  |  | 4 | 800 |  | 4 | 200 | 800
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.8 | The supply of materials and circuit design of the vertical gutters on a copy of the grounding using standard stainless steel gutter. | pcs | 10 | 130 | 1300 | 0 | 0 |  | 0 | 10 | 1300 |  |  | 0 | [30 empty] | 1 | 130 | 130 |  |  |  | 1 | 130 |  | 1 | 130 | 130
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [30 empty] | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
G.5.9 | Supply of materials and execution of joint horizontal gutters on the main drainage system LPS using standard stainless steel fittings. | pcs | 10 | 130 | 1300 | 0 | 0 |  | 0 | 10 | 1300 |  |  | 0 | [30 empty] | 10 | 130 | 1300 |  |  |  | 10 | 1300 |  | 10 | 130 | 1300
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.5 | LPS of garage for compactor TOTAL |  |  |  | 11500 |  | 0 |  | 0 |  | 11500 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3280 |  |  | 7330 |  |  | 500 | 0 | 11110 |  | 0 | 0 | 11110
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6 | Electric installation of outdoor lighting | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.1 | Supply, laying and mutually connecting 1 kV power cables with flexible HERP insulation and PVC sheath, according to the lower specification. The cables are laid in PVC pipe in the ditch on a sandy bed. PVC pipe previously placed. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • FG70R 5×6 mm2 | m' | 35 | 40 | 1400 | 0 | 0 |  | 0 | 35 | 1400 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 40 | 0
| • FG70R 5×10 mm2 | m' | 180 | 58 | 10440 | 0 | 0 |  | 0 | 180 | 10440 |  |  | 0 | [24 empty] | 178 | 58 | 10324 |  | 0 | 0 |  | 180 | 0 |  |  |  | 178 | 10324 |  | 178 | 58 | 10324
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.2 | Supply and laying of double wall corrugated PVC / HDPE pipes in pre-prepared earthen trench to the lower specification. The pipes must be made of polyethylene, with ribbed outer wall and an inner smooth, suitable for direct burial in the ground and concrete. All pipe to perform a standard connectors. All segments laid pipes must be equipped with a trailer for broaching metal cable. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • 1 × PVC Ø50mm | m' | 180 | 26 | 4680 | 0 | 0 |  | 0 | 180 | 4680 |  |  | 0 | [24 empty] | 170 | 26 | 4420 |  | 0 | 0 |  | 180 | 0 |  |  |  | 170 | 4420 |  | 170 | 26 | 4420
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.3 | Supply, laying and connecting the internal wiring of lighting columns: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • NYY (PP00-Y) 3×1,5 mm | m' | 100 | 11 | 1100 | 0 | 0 |  | 0 | 100 | 1100 |  |  | 0 | [27 empty] | 100 | 11 | 1100 |  | 0 | 0 |  |  |  | 100 | 1100 |  | 100 | 11 | 1100
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.4 | Supply, installation and centering lighting columns height 10 (10.9) m, conical octagonal performance, hot galvanized, threaded, for the wind zone 3, scheduled for installation bracket and lamp outdoor lighting, as well as the type of KORS 2A-1000-3 ' DALEKOVOD '' or equivalent. Top column seal. Calculation per piece including materials and installation of the pre-prepared foundation. | pcs | 4 | 4900 | 19600 | 0 | 0 |  | 0 | 4 | 19600 |  |  | 0 | [27 empty] | 4 | 4900 | 19600 |  | 0 | 0 |  |  |  | 4 | 19600 |  | 4 | 4900 | 19600
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.5 | Supply and installation of dividing the column exterior lighting with built-D01 (E14) fuses. The divide must be able to accept min. 3 cable (input / output) number of wires and sections to 5x10mm2. For protection circuitry lights on a pole divide must be equipped with min. 3 D01 fuse rated current of 4A. The divide as type EKM 2050 " TYCO " or equivalent. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Offer |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | pcs | 4 | 270 | 1080 | 0 | 0 |  | 0 | 4 | 1080 |  |  | 0 | [27 empty] | 4 | 270 | 1080 |  | 0 | 0 |  |  |  | 4 | 1080 |  | 4 | 270 | 1080
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.6 | Supply of small installation materials (cable terminals, sleeves, etc.), Preparing the cable and connecting cable 5x6 (10) mm2 to divide the pillar or closet. Calculation per piece of cable, one-sided. | pcs | 10 | 370 | 3700 | 0 | 0 |  | 0 | 10 | 3700 |  |  | 0 | [27 empty] | 10 | 370 | 3700 |  | 0 | 0 |  |  |  | 10 | 3700 |  | 10 | 370 | 3700
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.7 | Supply and mounting brackets 2 reflectors on a pole height of 10m, with swivel plates made according to the type of tendered limelight because it enables rotation reflector per horizontal axis. Material iron access manned by hot dip galvanizing, all fixing and other accessories must be protected by anti-corrosion or stainless materials. | pcs | 4 | 270 | 1080 | 0 | 0 |  | 0 | 4 | 1080 |  |  | 0 | [27 empty] | 4 | 270 | 1080 |  | 0 | 0 |  |  |  | 4 | 1080 |  | 4 | 270 | 1080
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.8 | Supply, installation and connection of luminaires reflector, a source LED, aluminum housing, powder painted, silicone seal, tempered glass, IP66 protection, swivel bracket, lifespan L70 (70% of nominal light output) 130000h. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Characteristics of origin: |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Asymmetric optics |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Usable (real) luminous flux ≥ 23 770 lm |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Light-efficiency lamps ≥ 99lm / W |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Total power (LED module + gear) ≤ 238 W |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - Color light ≤ 4000K |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| - CRI (Ra) ≥ 70 |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| Flashlight with ENEC certification, the manufacturer must have a certificate of ISO9001, |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| all such type Guell 3 A / W ," SBP "" or equivalent. | pcs | 8 | 6750 | 54000 | 0 | 0 |  | 0 | 8 | 54000 |  |  | 0 | [27 empty] | 8 | 6750 | 54000 |  | 0 | 0 |  |  |  | 8 | 54000 |  | 8 | 6750 | 54000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.9 | The supply and laying of stainless steel strips P30x3,5mm RF cable with outdoor lighting, previously prepared in an earthen trench, complete with stainless steel fittings and accessories. | m' | 60 | 46 | 2760 | 0 | 0 |  | 0 | 60 | 2760 |  |  | 0 | [24 empty] | 60 | 46 | 2760 |  | 0 | 0 |  | 60 | 0 |  |  |  | 60 | 2760 |  | 60 | 46 | 2760
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.10 | The supply of stainless steel strips P30x3,5mm Rf and execution ground pillars of external lighting by connecting the grounding screw pillar and ground electrode in a trench. The sentence included stainless steel cross-coupling, "tape-strip", "tape l = 2m, and small installation supplies and accessories. | set | 4 | 160 | 640 | 0 | 0 |  | 0 | 4 | 640 |  |  | 0 | [27 empty] | 4 | 160 | 640 |  | 0 | 0 |  |  |  | 4 | 640 |  | 4 | 160 | 640
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6.11 | Setting the (routing) reflector in accordance with the project and the results of measurements of illumination on the ground. The sentence included the measurement of illumination before and after fine tuning lamps. | set | 1 | 2000 | 2000 | 0 | 0 |  | 0 | 1 | 2000 |  |  | 0 | [33 empty] | 1 | 2000 | 2000 | 1 | 2000 |  | 1 | 2000 | 2000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.6 | Electric installation of outdoor lighting TOTAL |  |  |  | 102480 |  | 0 |  | 0 |  | 102480 |  |  | 0 | [23 empty] | 0 |  |  | 17504 |  |  | 81200 |  |  | 0 |  |  | 2000 | 0 | 100704 |  | 0 | 0 | 100704
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7 | Integral grounding | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.1 | The supply and laying of stainless steel strips P30x3,5mm R in previously prepared soil trench along the ducts and energy for grounding available and foreign conductive parts (metal masses) in the building. All compounds perform a standard cross stainless steel fittings "strip-tape '' and coated bitumen coating. | m' | 200 | 46 | 9200 | 0 | 0 |  | 0 | 200 | 9200 |  |  | 0 | [24 empty] | 225 | 46 | 10350 |  | 0 | 0 |  | 200 | 0 |  |  |  | 225 | 10350 |  | 225 | 46 | 10350
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.2 | Development of lateral lines with grounding in the trenches, the average length l = 2.5m stainless steel strip P30x3,5mm Rf by cross-coupling (grounding conductive parts, introduced in wells, etc.). The compound coated with bitumen. | pcs | 35 | 155 | 5425 | 0 | 0 |  | 0 | 35 | 5425 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 155 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.3 | The implementation of ground available and foreign conductive mass connectivity to previously made copies of the tapes grounding. Compound perform screw, the type coupler or welding, complete with all necessary material. | pcs | 35 | 150 | 5250 | 0 | 0 |  | 0 | 35 | 5250 |  |  | 0 | [27 empty] | 10 | 150 | 1500 | 25 | 150 | 3750 |  |  |  | 35 | 5250 |  | 35 | 150 | 5250
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.4 | Supply of materials and execution ground (potential equalization) available and foreign conductive mass connecting green-yellow conductor type H07V-K 1x6mm2. Compound perform screw, the type coupler, complete with all necessary material. Cable length approx. 5m per joint. | pcs | 20 | 70 | 1400 | 0 | 0 |  | 0 | 20 | 1400 |  |  | 0 | [27 empty] | 11 | 70 | 770 | 9 | 70 | 630 |  |  |  | 20 | 1400 |  | 20 | 70 | 1400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.5 | Supply of materials and execution ground (potential equalization) available and foreign conductive mass connecting green-yellow conductor type H07V-K 1x6mm2. Compound perform screw, the type coupler, complete with all necessary material. Cable length approx. 5m per joint. | pcs | 15 | 70 | 1050 | 0 | 0 |  | 0 | 15 | 1050 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 70 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.6 | Supply of materials and execution grounded fence landfill at prescribed intervals in accordance with project documentation. The item is included below specified outfitting and material, with the installation, including nailing ground rod electrode (alt. Drilling), excavation pits and installation of the grounding wells and other work to full advantage. |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • grounding HDPE well 30x30x30cm - 1 pc |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • rod (stick) earthing Ø12mm, l = 2m - 1 pc |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Stainless steel strip P30x3,5mm Rf, l = 3m - 1 pc |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Stainless steel cross-coupling - 1 pc |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • Stainless steel joints (clip) for a fence - 1 pc |  |  |  |  | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| • small fittings and accessories - 1 set | set | 15 | 3000 | 45000 | 0 | 0 |  | 0 | 15 | 45000 |  |  | 0 | [27 empty] | 15 | 3000 | 45000 |  | 0 | 0 |  |  |  | 15 | 45000 |  | 15 | 3000 | 45000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7.7 | Delivery and installation assembly for dissipating static electricity and ground car tanks during refueling of diesel generators, as well as type SKX 15/41 ST "TEPEx" or equivalent. | pcs | 1 | 2400 | 2400 | 0 | 0 |  | 0 | 1 | 2400 |  |  | 0 | [27 empty] | 1 | 2400 | 2400 |  | 0 | 0 |  |  |  | 1 | 2400 |  | 1 | 2400 | 2400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.7 | Integral grounding TOTAL |  |  |  | 69725 |  | 0 |  | 0 |  | 69725 |  |  | 0 | [23 empty] | 0 |  |  | 10350 |  |  | 49670 |  |  | 4380 |  |  |  | 0 | 64400 |  | 0 | 0 | 64400
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8 | Grounding of reservoirs | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.1 | The supply and laying of stainless steel strips P30x3,5mm R in previously prepared soil trench wash area wheel and grounding available and foreign conductive parts (metal masses) in wash area. All compounds perform a standard cross stainless steel fittings "strip-tape '' and coated with bitumen coating . | m' | 50 | 47 | 2350 | 0 | 0 |  | 0 | 50 | 2350 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 47 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.2 | The supply and laying of stainless steel strips P30x3,5mm Rf in concrete foundations, walls and ceilings of the pool for leachate and storm water and based vehicular balances. All compounds perform a standard cross stainless steel fittings "strip-tape '' and coated with bitumen coating. | m' | 150 | 47 | 7050 | 0 | 0 |  | 0 | 150 | 7050 |  |  | 0 | [24 empty] | 55 | 47 | 2585 |  | 0 | 0 |  | 150 | 0 |  |  |  | 55 | 2585 |  | 55 | 47 | 2585
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.3 | Development of lateral lines with grounding in the trenches or concrete, the average length l = 2.5m stainless steel strip P30x3,5mm Rf by cross-coupling (grounding conductive parts, etc.). The compound coated with bitumen. | pcs | 42 | 155 | 6510 | 0 | 0 |  | 0 | 42 | 6510 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 155 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.4 | The implementation of ground available and foreign conductive mass connectivity to previously made copies of the tapes grounding. Compound perform screw, the type coupler or welding, complete with all necessary material. | pcs | 42 | 150 | 6300 | 0 | 0 |  | 0 | 42 | 6300 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 150 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.5 | Supply of materials and execution ground (potential equalization) available and foreign conductive mass connecting green-yellow conductor type H07V-K 1x6mm2. Compound perform screw, the type coupler, complete with all necessary material. Cable length approx. 5m per joint. | pcs | 30 | 70 | 2100 | 0 | 0 |  | 0 | 30 | 2100 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 70 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8.6 | Supply of materials and execution ground (potential equalization) available and foreign conductive mass connecting green-yellow conductor type H07V-K 1x6mm2. Compound perform screw, the type coupler, complete with all necessary material. Cable length approx. 5m per joint. | pcs | 30 | 70 | 2100 | 0 | 0 |  | 0 | 30 | 2100 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 70 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.8 | Grounding of reservoirs TOTAL |  |  |  | 26410 |  | 0 |  | 0 |  | 26410 |  |  | 0 | [23 empty] | 0 |  |  | 2585 |  |  | 0 |  |  | 0 |  |  |  | 0 | 2585 |  | 0 | 0 | 2585
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9 | Construction works | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.1 | Tracing the trench - marking the route of cable laying, cable wells and foundations of the pillars of external lighting. The course is conducted on the ground. | m' | 250 | 2 | 500 | 0 | 0 |  | 0 | 250 | 500 |  |  | 0 | [24 empty] | 240 | 2 | 480 |  | 0 | 0 |  | 250 | 0 |  |  |  | 240 | 480 |  | 240 | 2 | 480
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.2 | Excavation of trench for laying cables and pipes for electrical installations (OG, VR), regardless of the category of the terrain, with planning bottom of the trench, dimensions 60 x 100 cm (W x H) with the correct cuts the sides. Material from excavation disposed on the side min 1m from the edge trench. | m' | 15 | 70 | 1050 | 0 | 0 |  | 0 | 15 | 1050 |  |  | 0 | [24 empty] | 15 | 70 | 1050 |  | 0 | 0 |  | 15 | 0 |  |  |  | 15 | 1050 |  | 15 | 70 | 1050
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.3 | Excavation of trench for laying cables and pipes for electrical installations (OG, VR), regardless of the category of the terrain, with planning bottom of the channel dimensions 40-60 × 80 cm (W x H) with the correct cuts the sides. Material from excavation disposed on the side min 1m from the edge of the trench. | m' | 210 | 60 | 12600 | 0 | 0 |  | 0 | 210 | 12600 |  |  | 0 | [24 empty] | 225 | 60 | 13500 |  | 0 | 0 |  | 210 | 0 |  |  |  | 225 | 13500 |  | 225 | 60 | 13500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.4 | The supply and delivery of concrete C16 / 20 and creating a protective layer over the previously laid pipes and cables in a busy area. | m3 | 1 | 800 | 800 | 0 | 0 |  | 0 | 1 | 800 |  |  | 0 | [24 empty] | 1.92 | 800 | 1536 |  | 0 | 0 |  | 1 | 0 |  |  |  | 1.92 | 1536 |  | 1.92 | 800 | 1536
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.5 | The supply and laying of sand 0-4 mm in the cable channel in layers of 10 cm below and 20 cm above the pipe with a slight ramming. | m3 | 41 | 150 | 6150 | 0 | 0 |  | 0 | 41 | 6150 |  |  | 0 | [24 empty] | 36.62 | 150 | 5493 |  | 0 | 0 |  | 41 | 0 |  |  |  | 36.62 | 5493 |  | 36.62 | 150 | 5493
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.6 | Filling the rest of the cable channel dimensions 60 × 100 cm, with mechanical compaction and compaction testing. Filling is done in layers over the placement and grounding straps warning. The item also includes the removal of the remaining coarse material after backfilling. | m' | 15 | 20 | 300 | 0 | 0 |  | 0 | 15 | 300 |  |  | 0 | [24 empty] | 15 | 20 | 300 |  | 0 | 0 |  | 15 | 0 |  |  |  | 15 | 300 |  | 15 | 20 | 300
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.7 | Filling the rest of the cable channel dimensions 60 × 80 cm, with mechanical compaction and compaction testing. Filling is done in layers over the placement and grounding straps warning. The item also includes the removal of the remaining coarse material after backfilling. | m' | 210 | 20 | 4200 | 0 | 0 |  | 0 | 210 | 4200 |  |  | 0 | [24 empty] | 225 | 20 | 4500 |  | 0 | 0 |  | 210 | 0 |  |  |  | 225 | 4500 |  | 225 | 20 | 4500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.8 | The plastic warning tape, "CAUTION-POWER CABLE" "placed above the cables and pipes in the trenches in two layers. | m' | 450 | 2.8 | 1260 | 0 | 0 |  | 0 | 450 | 1260 |  |  | 0 | [30 empty] | 425 | 2.8 | 1190 |  |  |  | 425 | 1190 |  | 425 | 2.8 | 1190
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.9 | Supply and installation of prefabricated concrete orientation wells dim. 0.8 × 0.8 × 0.8 m (L x W x H) with cast-iron lid 125kN. The cover supplied with the appropriate inscription '' ELECTRIC ''. The item includes excavation pits the required size for the installation, removal of excess material, surface preparation (compaction, etc.), setting the well, retractable PVC tube set with sealing and backfilling of the pit. After feeding tube opening is required watertight seal. | pcs | 10 | 4250 | 42500 | 0 | 0 |  | 0 | 10 | 42500 |  |  | 0 | [24 empty] | 9 | 4250 | 38250 |  | 0 | 0 | 0.9 | 4250 | 3825 |  |  |  | 9.9 | 42075 |  | 9.9 | 4250 | 42075
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.10 | Making concrete foundation dimensions 100 x 100 x 120cm for stud public illumination column h = 10m, complete with tracing, a pit excavated for the foundation regardless of the category of land, concreting concrete C30 / 37, the installation of two PVC pipes Ø 50 mm / l = 4m and knees F125mm and installation reinforcement of concrete iron. | pcs | 4 | 1100 | 4400 | 0 | 0 |  | 0 | 4 | 4400 |  |  | 0 | [30 empty] | 4 | 1100 | 4400 |  |  |  | 4 | 4400 |  | 4 | 1100 | 4400
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9.11 | The supply and delivery of the underlying concrete C20 / 25 and the production of spacer plates 10 cm thick in the pits beneath the cable wells and foundations of the pillars of external lighting. | m3 | 1 | 1000 | 1000 | 0 | 0 |  | 0 | 1 | 1000 |  |  | 0 | [30 empty] | 1.3 | 1000 | 1300 |  |  |  | 1.3 | 1300 |  | 1.3 | 1000 | 1300
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.9 | Construction works TOTAL |  |  |  | 74760 |  | 0 |  | 0 |  | 74760 |  |  | 0 | [23 empty] | 0 |  |  | 65109 |  |  | 0 |  |  | 10715 |  |  |  | 0 | 75824 |  | 0 | 0 | 75824
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10 | Installation tests and technical documentation | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10.1 | Testing installations strong currents in accordance with HRN HD 60364-6 including testing of protection in case of a breakdown, insulation resistance and illumination, as well as publishing the minutes of questioning. | set | 1 | 4500 | 4500 | 0 | 0 |  | 0 | 1 | 4500 |  |  | 0 | [33 empty] | 1 | 4500 | 4500 | 1 | 4500 |  | 1 | 4500 | 4500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10.2 | Examination of mobility (calibration) standing pipes and issuing the minutes of questioning. | set | 1 | 2000 | 2000 | 0 | 0 |  | 0 | 1 | 2000 |  |  | 0 | [33 empty] | 1 | 2000 | 2000 | 1 | 2000 |  | 1 | 2000 | 2000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10.3 | Testing of grounding and lightning protection systems in accordance with the Technical Regulations for systems of protection from the effects of lightning on buildings (OG 87/08). | set | 1 | 2000 | 2000 | 0 | 0 |  | 0 | 1 | 2000 |  |  | 0 | [33 empty] | 1 | 2000 | 2000 | 1 | 2000 |  | 1 | 2000 | 2000
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10.4 | Built design (the project with all the marked changes and amendments in accordance with the actual state) made in three copies, and the development and delivery of software documentation in paper and electronic form (3 sets of copies). | set | 1 | 2500 | 2500 | 0 | 0 |  | 0 | 1 | 2500 |  |  | 0 | [33 empty] | 1 | 2500 | 2500 | 1 | 2500 |  | 1 | 2500 | 2500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10.5 | Geodetic survey of all derivative positions and installation of wells and columns. Creating geodetic report in 3 copies and in electronic format, all in the form to enable the entry of infrastructure in cadaster lines. | pcs | 1 | 3500 | 3500 | 0 | 0 |  | 0 | 1 | 3500 |  |  | 0 | [33 empty] | 1 | 3500 | 3500 | 1 | 3500 |  | 1 | 3500 | 3500
[6 empty] | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
G.10 | Installation tests and technical documentation TOTAL |  |  |  | 14500 |  | 0 |  | 0 |  | 14500 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 14500 | 0 | 14500 |  | 0 | 0 | 14500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G | ELECTROTECHNICAL WORKS | [12 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.1 | GENERATOR STATION |  |  |  | 153200 |  | 0 |  | 0 |  | 153200 |  |  | 0 | [23 empty] | 0 |  |  | 145000 |  |  | 0 |  |  | 3360 |  |  | 9040 | 0 | 157400 |  | 0 | 0 | 157400
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.2 | MAIN POWER DISTRIBUTTION |  |  |  | 114586 |  | 0 |  | 0 |  | 114586 |  |  | 0 | [23 empty] | 0 |  |  | 42045 |  |  | 28212 |  |  | 30791 |  |  | 3000 | 0 | 104048 |  | 0 | 0 | 104048
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.3 | ELECTRIC INSTALLATION OF BUILDING FOR PERSONNEL |  |  |  | 19305 |  | 0 |  | 0 |  | 19305 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3664 |  |  | 1740 |  |  | 1080 | 0 | 6484 |  | 0 | 0 | 6484
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.4 | ELECTRIC INSTALLATION OF GARAGE FOR COMPACTOR |  |  |  | 36211 |  | 0 |  | 0 |  | 36211 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 33525 |  |  | 0 | 0 | 33525 |  | 0 | 0 | 33525
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.5 | LPS OF GARAGE FOR COMPACTOR |  |  |  | 11500 |  | 0 |  | 0 |  | 11500 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 3280 |  |  | 7330 |  |  | 500 | 0 | 11110 |  | 0 | 0 | 11110
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.6 | ELECTRIC INSTALLATION OF OUTDOOR LIGHTING |  |  |  | 102480 |  | 0 |  | 0 |  | 102480 |  |  | 0 | [23 empty] | 0 |  |  | 17504 |  |  | 81200 |  |  | 0 |  |  | 2000 | 0 | 100704 |  | 0 | 0 | 100704
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.7 | INTEGRAL GROUNDING |  |  |  | 69725 |  | 0 |  | 0 |  | 69725 |  |  | 0 | [23 empty] | 0 |  |  | 10350 |  |  | 49670 |  |  | 4380 |  |  | 0 | 0 | 64400 |  | 0 | 0 | 64400
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.8 | GROUNDING OF RESERVOIRS |  |  |  | 26410 |  | 0 |  | 0 |  | 26410 |  |  | 0 | [23 empty] | 0 |  |  | 2585 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 2585 |  | 0 | 0 | 2585
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.9 | CONSTRUCTION WORKS |  |  |  | 74760 |  | 0 |  | 0 |  | 74760 |  |  | 0 | [23 empty] | 0 |  |  | 65109 |  |  | 0 |  |  | 10715 |  |  | 0 | 0 | 75824 |  | 0 | 0 | 75824
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G.10 | INSTALLATION TESTS AND TECHNICAL DOCUMENTATION |  |  |  | 14500 |  | 0 |  | 0 |  | 14500 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 14500 | 0 | 14500 |  | 0 | 0 | 14500
[14 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0
G | ELECTROTECHNICAL WORKS SUMMARY |  |  |  | 622677 |  | 0 |  | 0 |  | 622677 |  |  | 0 | [23 empty] | 0 |  |  | 282593 |  |  | 166026 |  |  | 91841 |  |  | 30120 | 0 | 570580 |  | 0 | 0 | 570580
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.1 | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
H.1 | Mechanical excavation of class "A" material, to the elevations specified in the design. The item includes excavation, transport and disposal at the place where backfilling shall be performed. The excavation includes also the fragmentation of large pieces into grains of maximum size of 40 cm. Calculation is conducted per m3 of actually excavated and transported material in natural condition, based on surveyed profiles and in the presence of the supervising engineer who shall also determine the class and percentage of excavated material. | m3 |  | 83.5 |  | 133272.63 | 11128264.605 |  | 0 | 133272.63 | 11128264.605 |  |  | 0 | 27789.78 | 83.5 | 2320446.63 | 12753.02 | 83.5 | 1064877.17 | 6656.8 | 83.5 | 555842.8 | 25322.35 | 83.5 | 2114416.225 | 34800 | 83.5 | 2905800 | 7200 | 83.5 | 601200 | 8739.05 | 83.5 | 729710.675 | [15 empty] | 123261 | 10292293.5 |  | 123261 | 83.5 | 10292293.5
[14 empty] | 0 |  |  | 0 | [33 empty] | 0 | 0 |  | 0 | 0 | 0
H.2. | Cost of mobilization and demobilization of machines | set |  | 378634.24 |  | 1 | 378634.24 |  | 0 | 1 | 378634.24 |  |  | 0 | 1 | 378634.24 | 378634.24 | [33 empty] | 1 | 378634.24 |  | 1 | 378634.24 | 378634.24
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.1 SUMMARY |  |  |  | 0 |  | 11506898.845 |  | 0 |  | 11506898.845 |  |  | 0 | [23 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 | 10670927.74 |  | 0 | 0 | 10670927.74
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.2 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
I. | VIK - ODVODNJA | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
I.1. | Zemljani radovi | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[9 empty] | 0 | [41 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.1. | Strojni iskop materijala u B kategoriji do dubine h[m] ovisno o građevini sa vertikalnim zasjecanjem. Radove izvesti ovisno o opremljenosti i tehnologiji rada izvođača za sve dubine prema grafičkim prilozima projekta. Širina rova je ovisna o normalnom profilu i veličini cjevovoda. Iskopano tlo odbacuje se u stranu unutar radnog pojasa, a ukoliko je potrebno na uskim mjestima se odvozi, međudeponira i kod zatrpavanja se ponovo dovozi na mjesto ugradbe. Način iskopa određuje izvoditelj, a obračun će biti proveden prema količinama po idealnom profilu iz glavnog projekta tako da višak iskopa treba biti ukalkuliran u cijenu i neće se naknadno priznavati. U stavku su uključeni svi potrebni radovi i oprema za razupiranje i osiguranje rova od urušavanja, prema tehnologiji izvođača radova, u skladu s propisanim uvjetima zaštite na radu, uključujući i potreban iskop za ugradnju zaštitne oplate (koji nije posebno specificiran). | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Iskop materijala (obračun u sraslom stanju) | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Objekti odvodnje | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Revizijska okna - 56 m3 | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Slivnici - 44 m3 | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 46,80 m3 | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| d) Upojni bunar - 21,15 m3 | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Zauljene oborinske vode | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi zauljene oborinske odvodnje, iskop dubine 1,50 m, - 19 m3 | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode | [7 empty] | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod sanitarne otpadne vode, iskop dubine 1 m, - 1,40 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod vode s perilišta kotača, iskop dubine 0,9 m, - 1,80 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 190.15 | 0 |  | 0 | 190.15 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.2. | Zatrpavanje prostora oko izvedenih građevina probranim materijalom iz iskopa granulacije 0-32 mm do projektom određenih kota. Stavka uključuje niveliranje i zbijanje materijala u slojevima od 30 cm. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Zatrpavanje materijalom iz iskopa | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Revizijska okna - 28 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Slivnici - 40 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 23 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| d) Upojni bunar - 10,20 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 101.2 | 0 |  | 0 | 101.2 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.3. | Izrada ispune prostora oko upojnih bunara kamenim materijalom granulacije 60/120 mm. Stavka uključuje niveliranje i zbijanje materijala u slojevima od 30 cm. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Izrada ispune (obračun prema idealnom profilu iz nacrta) | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ispuna upojnog bunara - 25 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 25 | 0 |  | 0 | 25 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.4. | Nabava i doprema pijeska granulacije 0 - 12 mm te izrada pješćane posteljice debljine 10 cm za polaganje cjevovoda. Stavka uključuje zbijanje ručnim nabijačima. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Izrada posteljice | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod potencijalno zauljene oborinske odvodnje - 3,37 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi sanitarne otpadne vode - 0,15 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod vode s perilišta kotača - 0,20 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 3.72 | 0 |  | 0 | 3.72 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.5. | Nabava i doprema pijeska/šljunka ili drobljenog kamena granulacije 0 - 32 mm te zatrpavanje cjevovoda s debljinom nadsloja iznad tjemena cijevi od 30 cm. Stavka uključuje zbijanje ručnim nabijačima. Posebnu pažnju obratiti na bočno zbijanje materijala između cijevi i stijenke rova visine 0,5 D kako bi se dobio čim veći kut nalijeganja. Pri zatrpavanju spoj mora ostati vidljiv do provođenja tlačne probe. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Zatrpavanje zamjenskim materijalom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi potencijalno zauljene oborinske odvodnje - 9 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi sanitarne otpadne vode - 0,60 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod vode s perilišta kotača - 0,60 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 10.2 | 0 |  | 0 | 10.2 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.6. | Zatrpavanje prostora zone ispune rova cjevovoda iznad zone zaštite cjevovoda materijalom iz iskopa (max. veličine zrna 63 mm). Stavka uključuje utovar, prijevoz, istovar, niveliranje i zbijanje materijala do projektiranog modula stišljivosti u slojevima debljine 30 cm. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Zatrpavanje materijalom iz iskopa | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi potencijalno zauljene oborinske odvodnje - 16,30 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi sanitarne otpadne vode - 0,60 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod vode s perilišta kotača - 1,00 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 17.9 | 0 |  | 0 | 17.9 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.7. | Prijevoz viška materijala iz iskopa nakon zatrpavanja prostora oko izvedenih građevina na deponiju unutar gradlilšta na udaljenosti do 500m. Stavka uključuje utovar, prijevoz i istovar te razastiranje materijala na deponiji. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Prijevoz materijala iz iskopa (obračun u sraslom stanju) | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Građevine: | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Revizijska okna - 8,3 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Slivnici - 4,90 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Separator - 24 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| e) Upojni bunar - 15,80 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi potencijalno zauljene oborinske odvodnje - 10,85 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovodi sanitarne otpadne vode - 0,75 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod vode s perilišta kotača - 0,80 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 65.4 | 0 |  | 0 | 65.4 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1.8. | Nabava, doprema i ugradnja pijeska granulacije 0 - 12 mm za izvedbu šljunčane podloge ispod separatora debljine 15 cm. Stavka uključuje zbijanje ručnim nabijačima. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Izrada podloge | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Separator - 0,90 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Separator kod perlišta kotača - 0,20 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 1.1 | 0 |  | 0 | 1.1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.1. | Zemljani radovi ukupno: |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.2. | Betonski radovi | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.2.1. | Nabava, doprema i ugradnja podložnog betona tlačne čvrstoće C16/20, debljine ovisno o građevini. Stavka uključuje svu eventualno potrebnu oplatu, njegu betona i atest tlačne čvrstoće. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Revizijska okna - (0,3 m3/kom) - 0,90 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Slivnici - (0,1 m3/kom) - 0,20 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| c) Kontrolno okno iza separatora - (0,3 m3/kom) - 0,30 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 1.4 | 0 |  | 0 | 1.4 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.2.2. | Nabava, doprema i ugradnja betona tlačne čvrstoće C25/30 u ploču i vijenac revizijskih okana i slivnika. Stavka uključuje obodnu oplatu, njegu betona i atest tlačne čvrstoće. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Revizijska okna (3 kom): | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) ploča - (0,3m3/kom) - 0,60 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) vijenac - (0,5m3/kom) - 1,00 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Slivnici (2 kom) | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) ploča - (0,1m3/kom) - 0,20 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) vijenac - (0,15m3/kom) - 0,30 m3 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  |  |  | 2.7 | 0 |  | 0 | 2.7 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.2. | Betonski radovi ukupno: |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.3. | Armirački radovi | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.3.1. | Nabava, doprema i ugradnja konstruktivne armature od čelika kvalitete B 500 B u ploču i vijenac revizijskih okana i slivnika. Stavka uključuje rezanje, oblikovanje, prijenos do mjesta ugradnje i ugradnju. Stavka također uključuje atest ugrađene armature. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Revizijska okna (3 kom): | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) ploča - (30 kg/kom) - 90 kg | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) vijenac- (40 kg/kom) - 120 kg | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Slivnici (2 kom) | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) ploča- (10 kg/kom) - 20 kg | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| b) vijenac- (15 kg/kom) - 30 kg | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kg |  |  |  | 260 | 0 |  | 0 | 260 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.3. | Armirački radovi ukupno: |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4. | Monterski radovi | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.1. | Nabava, doprema i ugradnja rebrastih PEHD i PVC kanalizacijskih cijevi za odvodnju potencijalno zauljenih oborinskih, sanitarnih otpadnih voda i voda s perilišta kotača. Stavka uključuje sav potreban rad i materijal za njihovu ugradnju. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode: | m' |  |  |  | 2.5 | 0 |  | 0 | 2.5 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| PEHD OD/ID 160/141 mm, SN 8 | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| PEHD OD/ID 200/171 mm, SN 8 | m' |  |  |  | 60.7 | 0 |  | 0 | 60.7 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Sanitarne otpadne vode: | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| PVC OD/ID 160/152 mm, SN 4 - 2,30 m' | m' |  |  |  | 2.3 | 0 |  | 0 | 2.3 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| PEHD OD/ID 110/99,4 mm, SN 8 - 3,85 m' | m' |  |  |  | 3.85 | 0 |  | 0 | 3.85 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.2. | Nabava, doprema i ugradnja rebrastih PEHD kanalizacijskih cijevi OD/ID 1000/851 mm, SN 8, za izvedbu tijela revizijskih okana. Stavka uključuje izradu okana sa svim elementima (ploča dna, priključci cijevi, kineta...) do pune gotovosti, uključujući izvedbu penjalica od PE pločevine debljine min 2 cm, širine 45 cm i izvedbu leđobrana. Stavka uključuje sav potreban rad i materijal za ugradnju do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Potencijalno zauljene oborinske vode: | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) revizijska okna - 3 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 3 | 0 |  | 0 | 3 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.3. | Nabava, doprema i ugradnja rebraste PEHD kanalizacijske cijevi OD/ID 1000/851 mm, SN 8, za izvedbu upojnog bunara uključujući izvedbu penjalica od PE pločevine debljine min 2 cm, širine 45 cm, izvedbu leđobrana i perforacija na dijelu bunara koji se nalazi ispod ulazne kote dovodnog cjevovoda. Stavka uključuje sav potreban rad i materijal za ugradnju do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) upojni bunar - 1 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.4. | Nabava, doprema i ugradnja kape okna od PEHD pločevine debljine min 2 cm. Stavka uključuje sav potreban rad i materijal za ugradnju do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ugrađene kape revizijskih okana - 3 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ugrađene kape kontrolnog okna - 1 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 4 | 0 |  | 0 | 4 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.5. | Nabava, doprema i ugradnja rebrastih PEHD kanalizacijskih cijevi OD/ID 500/431 mm, SN 8, za izvedbu slivnika. Stavka uključuje izradu slivnika sa svim elementima (ploča dna, priključci cijevi...) do pune gotovosti. Stavka uključuje sav potreban rad i materijal za ugradnju do pune funkcionalnosti. Obračun po komadu izvedenog slivnika. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Izvedeni slivnici - 2 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 2 | 0 |  | 0 | 2 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.6. | Nabava, doprema i ugradnja lijevano željeznih kanalskih rešetki na slivnike nosivosti D 400 kN prema HRN EN-124:2005, dimenzija 400 x 400 mm. Stavka uključuje sav potreban rad i materijal za njihovu ugradnju do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ugrađene rešetke - 2 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 2 | 0 |  | 0 | 2 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.7. | Nabava, doprema i ugradnja ljevano željeznih kanalskih poklopaca kvadratičnog oblika, dimenzija 600 x 600 mm. Stavka uključuje sav potreban rad i materijal za njihovu ugradnju. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Spremnik sanitarne otpadne vode: | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Ugradnja poklopca klase B 125 kN, prema HRN EN-124:2005 - 1kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.8. | Nabava, doprema i ugradnja tipskog separatora prema EN 858-1 zapremine 5000 l te protokom od 20 l/s. Dimenzije separatora su LxBxH -3,0 x 1,30 x 1,35 m. Stavka uključuje svu dodatnu opremu koja se nalazi u separatoru zajedno sa 2 lijevano željezna poklopca na otvorima za inspekcijski nadzor nosivosti B 125 kN. Stavka uključuje sav potreban rad i materijal za ugradnju separatora do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ugrađeni separator - 1 kom | kom |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.9. | Nabava, doprema i ugradnja tipskog separatora prema EN 858-1 zapremine 800 l te protokom od 1,6 l/s. Dimenzije separatora su LxBxH 1,5 x 0,75 x 0,80 m. Stavka uključuje svu dodatnu opremu koja se nalazi u separatoru zajedno sa 2 lijevano željezna poklopca na otvorima za inspekcijski nadzor nosivosti B 125 kN. Stavka uključuje sav potreban rad i materijal za ugradnju separatora do pune funkcionalnosti. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ugrađeni separator - 1 kom | kom |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.10. | Inicijalno punjenje separatora čistom vodom radi provjere vodonepropusnosti spojeva uključujući montažu i demontažu privremenog dovoda vode i ostale potrebne opreme. Prije punjenja, separator mora biti postavljen na uređenu podlogu i spojevi ne smiju biti zatrpani materijalom iz iskopa. Obračun po komadu ispitanog uređaja. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Inicijalno punjenje ugrađenog separatora - 2 kom | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  |  |  | 2 | 0 |  | 0 | 2 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4..11. | Ispitivanje cjelokupnog kanalizacijskog sustava (sustav oborinske odvodnje i sustav sanitarne odvodnje) na vodonepropusnost spojeva i protočnost (uključivo i revizijska okna zajedno sa slivnicima) pomoću vode na odgovarajući tlak. Stavka uključuje montažu i demontažu privremenog dovoda vode i ostale potrebne opreme. Prije punjenja, cjevovod mora biti zatrpan osim spojeva. Tlačnu probu izvesti prema propisima. Obračun po dužnom metru ispitane kanalizacije. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ispitivanje kanalizacijskog sustava zauljene vode - 32,50 m' | m' |  |  |  | 32.5 | 0 |  | 0 | 32.5 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Ispitivanje kanalizacijskog sustava vode s perlišta kotača - 57,10 m' | m' |  |  |  | 57.1 | 0 |  | 0 | 57.1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.12. | ˝Nulto˝ čišćenje novoizvedenog kanalizacijskog sustava (sustav oborinske odvodnje i sustav sanitarne odvodnje) nakon završetka svih prethodnih radova. Stavka uključuje sav potreban rad i materijal za izvršenje stavke. Obračun po dužnom metru očišćene kanalizacije. | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| ˝Nulto˝ čišćenje po m' kanalizacijskog sustava zauljene vode - 32,50 m' | m' |  |  |  | 60.7 | 0 |  | 0 | 60.7 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
I.4.13. | Kanal za linijsku odvodnju | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Kanala za linijsku odvodnju nosivosti C400 prema HR EN 1433.Kanal se zbog specifičnog V-presjeka odlikuje većom brzinom otjecanja vode i boljim efektom samočišćenja. Kanal je izrađen iz polimerbetona, građevinske visine 480 mm. Svjetla širina kanala je 400 mm, građevinska širina 450 mm, građevinska dužina 1000 mm. Rubovi kanala ojačani su kutnikom od pocinčanog čelika debljine 4 mm koji služi kao dosjed za polaganje pokrovne rešetke. Kanal se izvodi polaganjem na betonsku podlogu marke C25/30 debljine sloja 20 cm, bočno kanal založiti betonom. Gornji rub rešetke se izvodi u razini 2 - 5 mm ispod kote gotove završne okolne površine. Sve sa priborom za montažu do potpune funkcionalnosti. Proizvod kao ACO Multiline V400 ili jedankovrijedan: | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| 4.12.1. Proizvod kao Multiline V400 ili jedankovrijedan - građevinske visine 480 mm. Svjetla širina kanala je 400 mm, građevinska širina 450 mm, građevinska duljina 1000 mm | m' |  |  |  | 16.6 | 0 |  | 0 | 16.6 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| 4.12.2. Proizvod kao Multiline V400 ili jednakovrijedan, pokrovna rešetka ACO Multiline V400 za opterećenje C400 prema HR EN 1433 (srednje teški promet) iz lijevanog željeza. | m' |  |  |  | 16.6 | 0 |  | 0 | 16.6 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| 4.12.3. Sabirnik za proizvod kao ACO Multiline V400 ili jednakovrijedan iz polimerbetona, s Drainlock učvršćivanjem rešetke bez vijaka, s taložnom posudom od PVC. | kom |  |  |  | 3 | 0 |  | 0 | 3 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| - izrada betonskih temelja tlačne čvrstoće C 20/25 prema uputama proizvođača opreme, poprečnog profila i dimenzija prema preporuci proizvođača opreme ovisno o mjestu ugradnje | m3 |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Detaljna razrada prema uputama proizvođača | [5 empty] | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[7 empty] | 0 |  |  | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Kanal za linijsku odvodnju ukupno: |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
I.4. | Monterski radovi ukupno: |  |  |  | 0 | [45 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
I. | VIK - ODVODNJA UKUPNO |  |  |  | 0 |  | 0 |  | 0 |  | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II. | VIK - VODOOPSKRBA | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1. | Zemljani radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1.1. | Strojni iskop materijala u B kategoriji do dubine h[m] ovisno o građevini sa vertikalnim zasjecanjem. Radove izvesti ovisno o opremljenosti i tehnologiji rada izvođača za sve dubine prema grafičkim prilozima projekta. Širina rova je ovisna o normalnom profilu i veličini cjevovoda. Iskopano tlo odbacuje se u stranu unutar radnog pojasa, a ukoliko je potrebno na uskim mjestima se odvozi, međudeponira i kod zatrpavanja se ponovo dovozi na mjesto ugradbe. Način iskopa određuje izvoditelj, a obračun će biti proveden prema količinama po idealnom profilu iz glavnog projekta tako da višak iskopa treba biti ukalkuliran u cijenu i neće se naknadno priznavati. U stavku su uključeni svi potrebni radovi i oprema za razupiranje i osiguranje rova od urušavanja, prema tehnologiji izvođača radova, u skladu s propisanim uvjetima zaštite na radu, uključujući i potreban iskop za ugradnju zaštitne oplate (koji nije posebno specificiran). | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Iskop materijala (obračun u sraslom stanju) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Voda za perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod, iskop dubine 0,9 m, - 21 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| b) tipsko okno s priključkom za DN 32 - 2,0 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m³ |  | 90 | 0 | 23 | 2070 |  | 0 | 23 | 2070 | [33 empty] | 32 | 90 | 2880 |  |  |  | 32 | 2880 |  | 32 | 90 | 2880
| (kao stavka D.1.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
II.1.2. | Nabava i doprema pijeska granulacije 0 - 12 mm te izrada pješćane posteljice debljine 10 cm za polaganje cjevovoda. Stavka uključuje zbijanje ručnim nabijačima. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Izrada posteljice | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Voda za perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod - 2,3 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.2.1.4.) | m³ |  | 160 | 0 | 2.3 | 368 |  | 0 | 2.3 | 368 | [33 empty] | 3 | 160 | 480 |  |  |  | 3 | 480 |  | 3 | 160 | 480
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1.3. | Nabava i doprema pijeska/šljunka ili drobljenog kamena granulacije 0 - 32 mm te zatrpavanje cjevovoda s debljinom nadsloja iznad tjemena cijevi od 30 cm. Stavka uključuje zbijanje ručnim nabijačima. Posebnu pažnju obratiti na bočno zbijanje materijala između cijevi i stijenke rova visine 0,5 D kako bi se dobio čim veći kut nalijeganja. Pri zatrpavanju spoj mora ostati vidljiv do provođenja tlačne probe. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Zatrpavanje zamjenskim materijalom | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Voda za perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod - 6,90 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.2.1.5.) | m³ |  | 120 | 0 | 6.9 | 828 |  | 0 | 6.9 | 828 | [33 empty] | 9 | 120 | 1080 |  |  |  | 9 | 1080 |  | 9 | 120 | 1080
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1.4. | Zatrpavanje prostora zone ispune rova cjevovoda iznad zone zaštite cjevovoda materijalom iz iskopa (max. veličine zrna 63 mm). Stavka uključuje utovar, prijevoz, istovar, niveliranje i zbijanje materijala do projektiranog modula stišljivosti u slojevima debljine 30 cm. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Voda za perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod - 4,60 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Tipsko okno s priključkom za DN 32 - 1,00 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.2.1.6.) | m³ |  | 18 | 0 | 5.6 | 100.8 |  | 0 | 5.6 | 100.8 | [33 empty] | 19 | 18 | 342 |  |  |  | 19 | 342 |  | 19 | 18 | 342
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1.5. | Prijevoz viška materijala iz iskopa nakon zatrpavanja prostora oko izvedenih građevina na deponiju unutar gradlilšta na udaljenosti do 500m. Stavka uključuje utovar, prijevoz i istovar te razastiranje materijala na deponiji. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Prijevoz materijala iz iskopa (obračun u sraslom stanju) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Vode s perilišta kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) cjevovod - 16,40 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| b) Tipsko okno s priključkom za DN 32 - 1,00 m3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.2.1.7.) | m³ |  | 12 | 0 | 17.4 | 208.8 |  | 0 | 17.4 | 208.8 | [33 empty] | 13 | 12 | 156 |  |  |  | 13 | 156 |  | 13 | 12 | 156
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.1. | Zemljani radovi ukupno: |  |  |  | 0 |  | 3575.6 |  | 0 |  | 3575.6 | [35 empty] | 4938 |  |  |  | 0 | 4938 |  | 0 | 0 | 4938
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.2. | Monterski radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.2.1. | Nabava, doprema i ugradnja glatkih PEHD tlačnih cijevi za izvedbu cjevovoda za napajanje miniwasha perilišta kotača. Stavka uključuje sav potreban rad i materijal za njihovu ugradnju. Obračun po m' ugrađene cijevi. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Voda za perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| PEHD OD 32 mm, SDR 17, PE 100, PN 10 | m' |  | 50 | 0 | 60 | 3000 |  | 0 | 60 | 3000 | [33 empty] | 50 | 50 | 2500 |  |  |  | 50 | 2500 |  | 50 | 50 | 2500
| (kao stavka C.2.4.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
II.2.2. | Nabava, doprema i ugradnja tipskog AB okna tlocrtnih dimenzija minimalno 1 x 1 m. Okno mora biti opremljeno priključkom za DN 32 mm (vintil 1'' + brza spojka za spajanja miniwasha). Obračun prema komadu izvedenog okna. U stavku je uračunato sve potrebno za punu funkcionalnost. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 10000 | 0 | 1 | 10000 |  | 0 | 1 | 10000 | [33 empty] | 1 | 10000 | 10000 |  |  |  | 1 | 10000 |  | 1 | 10000 | 10000
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.2.3. | Nabava, doprema i ugradnja hvatača nečistoća (Y-filtra) promjera NO25 mm na tlačni cjevovod oborinske vode za napajanje perilišta kotača. Ugradnja hvatača nečistoća predviđena je unutar bazena za oborinske vode. | kom |  |  |  | 1 | 0 |  | 0 | 1 | 0 | [34 empty] | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II.2. | Monterski radovi ukupno: |  |  |  | 0 |  | 13000 |  | 0 |  | 13000 | [35 empty] | 12500 |  |  |  | 0 | 12500 |  | 0 | 0 | 12500
[51 empty] | 0 | 0 |  | 0 | 0 | 0
II. | VIK - VODOOPSKRBA UKUPNO |  |  |  | 0 |  | 16575.6 |  | 0 |  | 16575.6 | [35 empty] | 17438 |  |  |  | 0 | 17438 |  | 0 | 0 | 17438
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III. | KONSTRUKCIJE | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Perilište kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Okno perilišta kotača | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.1 | Zemljani radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.1.1. | Iskop zemlje s odlaganjem u neposrednoj blizini građevinske jame. Stavka uključuje i uređenje temeljnog tla mehaničkim zbijanjem do projektiranog modula stišljivosti. Obračun prema m3 zemlje u sraslom stanju. Količina određena prema idealnom profilu. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Perilište kotača | m³ |  | 90 | 0 | 2.6 | 234 |  | 0 | 2.6 | 234 | [33 empty] | 15.96 | 90 | 1436.4 |  |  |  | 15.96 | 1436.4 |  | 15.96 | 90 | 1436.4
| b) Okno perilišta kotača | m³ |  | 90 | 0 | 11 | 990 |  | 0 | 11 | 990 | [33 empty] | 1.57 | 90 | 141.3 |  |  |  | 1.57 | 141.3 |  | 1.57 | 90 | 141.3
| (kao stavka D.1.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.1.2. | Nabava, doprema i ugradnja tamponskog sloja do projektom određene kote. Stavka uključuje i uređenje tamposkog sloja mehaničkim zbijanjem do projektiranog modula stišljivosti od 40 MPa. Obračun prema m3 zemlje u sraslom stanju. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Perilište kotača | m³ |  | 120 | 0 | 9 | 1080 |  | 0 | 9 | 1080 | [33 empty] | 7.98 | 120 | 957.6 |  |  |  | 7.98 | 957.6 |  | 7.98 | 120 | 957.6
| b) Okno perilišta kotača | m³ |  | 120 | 0 | 2 | 240 |  | 0 | 2 | 240 | [33 empty] | 1.19 | 120 | 142.8 |  |  |  | 1.19 | 142.8 |  | 1.19 | 120 | 142.8
| (kao stavka C.2.1.5.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.1.3. | Prijevoz viška materijala iz iskopa nakon zatrpavanja građevinske jame na odlagalište udaljeno do 5 km. Stavka uključuje utovar, prijevoz i istovar te razastiranje materijala na odlagalištu. Obračun prema m3 zemlje u sraslom stanju. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka D.1.3.) | m³ |  | 12 | 0 | 80 | 960 |  | 0 | 80 | 960 | [33 empty] | 17.53 | 12 | 210.36 |  |  |  | 17.53 | 210.36 |  | 17.53 | 12 | 210.36
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.1 | Zemljani radovi ukupno: |  |  |  | 0 |  | 3504 |  | 0 |  | 3504 | [35 empty] | 2888.46 |  |  |  | 0 | 2888.46 |  | 0 | 0 | 2888.46
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.2. | Betonski radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.2.1. | Betoniranje podložnog betona razreda tlačne čvrstoće C12/15. Stavka uključuje proizvodnju, odnosno nabavu i dopremu betona, ugradnju i njegu svježeg betona. Obračun prema m3 ugrađenog betona. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Perilište kotača | m³ |  | 750 | 0 | 2.5 | 1875 |  | 0 | 2.5 | 1875 | [33 empty] | 2.66 | 750 | 1995 |  |  |  | 2.66 | 1995 |  | 2.66 | 750 | 1995
| b) Okno perilišta kotača | m³ |  | 750 | 0 | 0.5 | 375 |  | 0 | 0.5 | 375 | [33 empty] | 0.4 | 750 | 300 |  |  |  | 0.4 | 300 |  | 0.4 | 750 | 300
| (kao stavka D.2.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.2.2. | Betoniranje betonom razreda tlačne čvrstoće C30/37, XD3. Stavka uključuje proizvodnju, odnosno nabavu i dopremu betona, ugradnju i njegu svježeg betona. Stavka također uključuje svu potrebnu oplatu te materijale i radove vezane uz oplatu. Obračun prema m3 ugrađenog betona. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Perilište kotača | m³ |  | 1650 | 0 | 5.2 | 8580 |  | 0 | 5.2 | 8580 | [33 empty] | 4.49 | 1650 | 7408.5 |  |  |  | 4.49 | 7408.5 |  | 4.49 | 1650 | 7408.5
| (kao stavka D.2.2. + XD3) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.2.3. | Betoniranje betonom razreda tlačne čvrstoće C30/37, vodoneppropusni, XD2. Stavka uključuje proizvodnju, odnosno nabavu i dopremu betona, ugradnju i njegu svježeg betona. Stavka također uključuje svu potrebnu oplatu te materijale i radove vezane uz oplatu. Obračun prema m3 ugrađenog betona. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Okno perilišta kotača | m³ |  | 1650 | 0 | 5.1 | 8415 |  | 0 | 5.1 | 8415 | [33 empty] | 0.55 | 1650 | 907.5 |  |  |  | 0.55 | 907.5 |  | 0.55 | 1650 | 907.5
| (kao stavka D.2.2. + XD2) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.2. | Betonski radovi ukupno: |  |  |  | 0 |  | 19245 |  | 0 |  | 19245 | [35 empty] | 10611 |  |  |  | 0 | 10611 |  | 0 | 0 | 10611
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.3. | Armirački radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.3.1. | Nabava, doprema, rezanje, savijanje, prijenos do mjesta ugradnje i ugradnja armature. Stavka uključuje sav potreban materijal i radove. Obračun prema kg ugrađene armature. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| a) Perilište kotača | kg |  | 8 | 0 | 535 | 4280 |  | 0 | 535 | 4280 | [33 empty] | 535 | 8 | 4280 |  |  |  | 535 | 4280 |  | 535 | 8 | 4280
| b) Okno perilišta kotača | kg |  | 8 | 0 | 678 | 5424 |  | 0 | 678 | 5424 | [33 empty] | 678 | 8 | 5424 |  |  |  | 678 | 5424 |  | 678 | 8 | 5424
| (kao stavka C.1.3.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
III.3. | Armirački radovi ukupno: |  |  |  | 0 |  |  |  | 0 |  | 9704 | [35 empty] | 9704 |  |  |  | 0 | 9704 |  | 0 | 0 | 9704
[7 empty] | 9704 | [43 empty] | 0 | 0 |  | 0 | 0 | 0
III.4. | Monterski radovi | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.4.1. | Nabava, doprema i ugradnja lijevanoželjeznog poklopca nosivosti B125 (150 kN). Poklopac se ugrađuje na okno perlišta kotača. Poklopac je dimenzija 600 x 600 mm. Obračun prema komadu ugrađenog poklopca. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 900 | 0 | 1 | 900 |  | 0 | 1 | 900 | [33 empty] | 1 | 900 | 900 |  |  |  | 1 | 900 |  | 1 | 900 | 900
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.4.2. | Nabava, doprema i ugradnja lijevanoželjeznih rešetki dimenzija 400 x 400 mm. Rešetke se ugrađuju na perilištu kotača. Obračun prema komadu ugrađene rešetke. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 900 | 0 | 5 | 4500 |  | 0 | 5 | 4500 | [33 empty] | 5 | 900 | 4500 |  |  |  | 5 | 4500 |  | 5 | 900 | 4500
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III.4. | Monterski radovi ukupno: |  |  |  | 0 |  | 15104 |  | 0 |  | 5400 | [35 empty] | 5400 |  |  |  | 0 | 5400 |  | 0 | 0 | 5400
[51 empty] | 0 | 0 |  | 0 | 0 | 0
III. | KONSTRUKCIJE UKUPNO: |  |  |  | 0 |  | 37853 |  | 0 |  | 37853 | [35 empty] | 28603.46 |  |  |  | 0 | 28603.46 |  | 0 | 0 | 28603.46
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
IV. | ODLAGALIŠTE | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Sustav recirkulacije procjedne vode |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1. | Zemljani radovi |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.1. | Strojni iskop materijala u C kategoriji do dubine h[m] ovisno o građevini sa vertikalnim zasjecanjem. Radove izvesti ovisno o opremljenosti i tehnologiji rada izvođača za sve dubine prema grafičkim prilozima projekta. Širina rova je ovisna o normalnom profilu i veličini cjevovoda. Iskopano tlo odbacuje se u stranu unutar radnog pojasa, a ukoliko je potrebno na uskim mjestima se odvozi, međudeponira i kod zatrpavanja se ponovo dovozi na mjesto ugradbe. Način iskopa određuje izvoditelj, a obračun će biti proveden prema količinama po idealnom profilu iz glavnog projekta tako da višak iskopa treba biti ukalkuliran u cijenu i neće se naknadno priznavati. U stavku su uključeni svi potrebni radovi i oprema za razupiranje i osiguranje rova od urušavanja, prema tehnologiji izvođača radova, u skladu s propisanim uvjetima zaštite na radu, uključujući i potreban iskop za ugradnju zaštitne oplate (koji nije posebno specificiran). |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka D.1.1.) | m³ |  | 90 | 0 | 11.4 | 1026 |  | 0 | 11.4 | 1026 | [33 empty] | 12.6 | 90 | 1134 |  |  |  | 12.6 | 1134 |  | 12.6 | 90 | 1134
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| Strojni iskop materijala u C kategoriji (rekultivirajućem sloju odlagališta) do dubine 0,8 m. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.1.1.1.) | m³ |  | 35 | 0 | 104.5 | 3657.5 |  | 0 | 104.5 | 3657.5 | [33 empty] | 104.16 | 35 | 3645.6 |  |  |  | 104.16 | 3645.6 |  | 104.16 | 35 | 3645.6
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.2. | Nabava i doprema pijeska granulacije 0 - 12 mm te izrada pješćane posteljice debljine 10 cm za polaganje cjevovoda. Stavka uključuje zbijanje ručnim nabijačima. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.1.1.4.) | m³ |  | 160 | 0 | 9 | 1440 |  | 0 | 9 | 1440 | [33 empty] | 15 | 160 | 2400 |  |  |  | 15 | 2400 |  | 15 | 160 | 2400
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.3. | Nabava i doprema pijeska/šljunka ili drobljenog kamena granulacije 0 - 32 mm te zatrpavanje cjevovoda s debljinom nadsloja iznad tjemena cijevi od 30 cm. Stavka uključuje zbijanje ručnim nabijačima. Posebnu pažnju obratiti na bočno zbijanje materijala između cijevi i stijenke rova visine 0,5 D kako bi se dobio čim veći kut nalijeganja. Pri zatrpavanju spoj mora ostati vidljiv do provođenja tlačne probe. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.1.1.5.) | m³ |  | 120 | 0 | 26 | 3120 |  | 0 | 26 | 3120 | [33 empty] | 45 | 120 | 5400 |  |  |  | 45 | 5400 |  | 45 | 120 | 5400
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.4. | Nabava, doprema i ugradnja glatkih PEHD tlačnih PE 100, OD 90 mm, SDR 17 (PN 10) cijevi za izvedbu sustava recirkulacije procjedne vode. Stavka uključuje sav potreban rad i materijal za njihovu ugradnju, ispitivanje montiranog cjevovoda na vodonepropusnost pomoću vode na odgovarajući tlak, te nulto čišćenje sustava. Prije punjenja cjevovod mora biti zatrpan, osim spojeva. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m' |  | 120 | 0 | 250 | 30000 |  | 0 | 250 | 30000 | [33 empty] | 250 | 120 | 30000 |  |  |  | 250 | 30000 |  | 250 | 120 | 30000
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.5. | Zatrpavanje prostora zone iznad zone zaštite cjevovoda materijalom iz iskopa (rekultivirajući sloj odlagališta). Stavka uključuje utovar, prijevoz, istovar, niveliranje i zbijanje materijala do projektiranog modula stišljivosti u slojevima debljine 30 cm. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.1.1.6.) | m³ |  | 18 | 0 | 77 | 1386 |  | 0 | 77 | 1386 | [33 empty] | 60 | 18 | 1080 |  |  |  | 60 | 1080 |  | 60 | 18 | 1080
[5 empty] | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
IV.1.6. | Prijevoz viška materijala na deponiju unutar gradlilšta na udaljenosti do 500m. Stavka uključuje utovar, prijevoz i istovar te razastiranje materijala na deponiji. |  |  |  | 0 |  | 0 |  | 0 | 0 | 0 | [39 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka C.1.1.7.) | m³ |  | 12 | 0 | 11.4 | 136.8 |  | 0 | 11.4 | 136.8 | [33 empty] | 56.75 | 12 | 681 |  |  |  | 56.75 | 681 |  | 56.75 | 12 | 681
[51 empty] | 0 | 0 |  | 0 | 0 | 0
IV. | ODLAGALIŠTE - SUSTAV RECIRKULACIJE UKUPNO: |  |  |  | 0 |  | 40766.3 |  | 0 |  | 40766.3 | [35 empty] | 44340.6 |  |  |  | 0 | 44340.6 |  | 0 | 0 | 44340.6
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1. | ARHITEKTONSKI PROJEKT - NADSTREŠNICE | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.1. | Garaža za kompaktor | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.1.1. | Obloga krova i pročelja | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| Nabava, doprema i montaža fasadnog i krovnog sendvič panela po EN 14509 ili jednakovrijednoj normi. Sendvič panel se sastoji od obostrano pocinčanog čeličnog lima debljine 0,5/0,5 mm (kvalitete lima S 320 GD), trapeznog profila s gornje i standardnog profila s donje strane - Krovni panel mikroliniranog s vanjske strane i standardnog profila s unutarnje strane - Fasadni panel, s konstrukcijskom jezgrom od PIR-a gustoće 40±3kg/m3, ukupne debljine 100 mm, klase negorivosti B s1 d0 prema EN 13501 ili jednakovrijednoj normi. Paneli su obostrano antikorozivno zaštićeni PS bojom 35 ym (hairultra) te zaštitnim folijama koje se skidaju kod montaže, boja RAL 7011/9002, U faktor 0,214 W/m2K, Krovni sendvič paneli se postavljaju na prethodno montirane roženice, na rasponu 2,0 m. Nosivost krovnog panela mora biti sukladna proračunu iz glavnog projekta. Stavka uključuje kompletno riješenu odvodnju oborinskih voda, horizontalne i vertikalne oluke, okapnice i druge fazonske elemente istog proizvođača. U cijenu su uključeni svi potrebni preklopi i spojna sredstva kao i sve potrebno za punu funkcionalnost. Obračun po m2. Izvedba i montaža prema projektu i dogovoru s projektantom. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Žlijebovi se izvode od nehrđajučeg čelika debljine 0.55 mm, pravokutnog poprečnog presjeka 15 x 15 cm, pričvršćenog kukama od nehrđajućeg čelika dimenzija 30/3 mm na roženice. Vertikalne cijevi za odvodnju izvode se od nehrđajućeg čelika debljine 0,55 mm, kvadratičnog poprečnog presjeka 10 x 10 cm. Cijevi za odvodnju pričvršćene su za stupove nehrđajućim obujmicama od plosnatog čelika dimenzija 30/3 mm. Obujmice se montiraju na svakih 1,00 m međusobne udaljenosti. Fasadni sendvič paneli se postavljaju vertikalno na prethodno montiranu potkonstrukciju. U cijenu su uključeni svi potrebni preklopi, spojna sredstava, opšavi i sve potrebno za punu funkcionalnost. Nosivost fasadnog panela mora biti minimalno 1,00 kN/m² na rasponu od 3,0 m. Boja: RAL 7011/9002 Paneli moraju biti otporni na požar minimalno 30 min. KROVNI PANEL - REI 30 prema EN 13501-2 FASADNI PANEL - EI 30 prema EN 13501-2 U jedničnu cijenu ukalkulirati montažu i demontažu sve potrebne skele. Obračun prema m². | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| EN 14509 ili jednakovrijedna norma: ___________________________________________________ | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| EN 13501 ili jednakovrijedna norma: ___________________________________________________ | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| Krov - (krovni panel) | m² |  | 666 | 0 | 70 | 46620 |  | 0 | 70 | 46620 | [33 empty] | 70 | 666 | 46620 |  |  |  | 70 | 46620 |  | 70 | 666 | 46620
| Pročelje (fasadni lim) _ Jugozapad | m² |  | 720 | 0 | 15 | 10800 |  | 0 | 15 | 10800 | [33 empty] | 15 | 720 | 10800 |  |  |  | 15 | 10800 |  | 15 | 720 | 10800
| Pročelje (fasadni lim) _ Sjeveroistok | m² |  | 720 | 0 | 22 | 15840 |  | 0 | 22 | 15840 | [33 empty] | 22 | 720 | 15840 |  |  |  | 22 | 15840 |  | 22 | 720 | 15840
| Pročelje (fasadni lim) _ Sjeverozapad | m² |  | 720 | 0 | 33 | 23760 |  | 0 | 33 | 23760 | [33 empty] | 33 | 720 | 23760 |  |  |  | 33 | 23760 |  | 33 | 720 | 23760
| Pročelje (fasadni lim) _ Jugoistok | m² |  | 720 | 0 | 36 | 25920 |  | 0 | 36 | 25920 | [33 empty] | 36 | 720 | 25920 |  |  |  | 36 | 25920 |  | 36 | 720 | 25920
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.1. | Garaža za kompaktor ukupno: |  |  |  | 0 |  | 122940 |  | 0 |  | 122940 | [35 empty] | 122940 |  |  |  | 0 | 122940 |  | 0 | 0 | 122940
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.2. | Garaža za kompaltor - vrata i prozori | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.2.1. | Vrata | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| Sekcijska podizna vrata Stavka uključuje nabavu, dopremu i montažu. Sekcijska vrata, podizna segmentna vrata izrađena od čeličnog pocinčanog lima s poliuretanskom ispunom. Širine 400 i visine 500 m. Čelični lim je dvostruko plasticifiran (trajna zaštita od korozije i atmosferilija). Ugrađen je sigurnosni sistem kočnica (sistem pero - utor) kao osiguranje od nekontroliranog pada. Vratima se upravlja motornim pogonom, pomoću daljinskog upravljača i tipkalom (u samoj hali). Vanjska boja je elektrostatski zapečena na pripremljenom pocinčanom čeličnom limu. Spojni okovi i vodilice su toplo cinčani, debljine 2 i 1,5 mm. Bazni i gornji profil vrata su od aluminija. Pocinčane torzione opruge (za balansiranje i podizanje) se nalaze iznad vrata. Jedno polje vrata su prozirni prozorski elementi. Boja vrata RAL 7016. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 60000 | 0 | 1 | 60000 |  | 0 | 1 | 60000 | [33 empty] | 1 | 60000 | 60000 |  |  |  | 1 | 60000 |  | 1 | 60000 | 60000
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.2.2. | Prozori | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| Nabava, doprema i montaža Al prozora. Prozori su aluminijska stolarija s minimalnim zahtjevima i karakteristikama termoizolacijskih svojstava. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  |  | 0 | 0
|  | kom |  | 4800 | 0 | 8 | 38400 |  | 0 | 8 | 38400 | [33 empty] | 8 | 4800 | 38400 |  |  |  | 8 | 38400 |  | 8 | 4800 | 38400
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1.2. | Garaža za kompaltor - vrata i prozori ukupno: |  |  |  | 0 |  | 98400 |  | 0 |  | 98400 | [35 empty] | 98400 |  |  |  | 0 | 98400 |  | 0 | 0 | 98400
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
V.1. | NADSTREŠNICA UKUPNO: |  |  |  | 0 |  | 221340 |  | 0 |  | 221340 | [35 empty] | 221340 |  |  |  | 0 | 221340 |  | 0 | 0 | 221340
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI. | OSTALO | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI.1. | Dodatak crpke za oborinske vode | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 25272 |  | 1 | 25272 |  | 0 | 1 | 25272 | [33 empty] | 1 | 25272 | 25272 |  |  |  | 1 | 25272 |  | 1 | 25272 | 25272
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI.2. | Formiranje pokosa terena/nasipa iznad 4.odlagališne kazete | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | m² |  | 13.72 |  | 11300 | 155036 |  | 0 | 11300 | 155036 | [33 empty] | 11109.51 | 13.72 | 152422.4772 |  |  |  | 11109.51 | 152422.4772 |  | 11109.51 | 13.72 | 152422.4772
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI.3. | Ulazna vrata na istočnom dijelu odlagališta | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| (kao stavka A.2.2.) | kom |  | 19000 |  | 1 | 19000 |  | 0 | 1 | 19000 | [33 empty] | 1 | 19000 | 19000 |  |  |  | 1 | 19000 |  | 1 | 19000 | 19000
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI.4. | Izrada betonskog okna (sv.dim. 1x1x1,8) za smještaj crpki za sanitarnu vodu | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 9945 |  | 1 | 9945 |  | 0 | 1 | 9945 | [33 empty] | 1 | 9945 | 9945 |  |  |  | 1 | 9945 |  | 1 | 9945 | 9945
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI.5. | Troškovi zastoja u periodu od 24.01.18. do 13.04.19. | [49 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom | [48 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VI. | OSTALO UKUPNO: |  |  |  | 0 |  | 209253 |  | 0 |  | 209253 | [35 empty] | 206639.4772 |  |  |  | 0 | 206639.4772 |  | 0 | 0 | 206639.4772
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
VII. | Naknadna izvedba | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.1. | Rezanje betona u armiranobetonskoj gornjoj ploči bazena za procjedne vode (okno za ulaz). Rezanje se izvodi pomoću dijamantne pile. Dubina reza iznosi 25 cm, a dimenzije reza su 600 x 600 mm. Stavka uključuje sav potreban rad, opremu i transport opreme za rezanje, te eventualni dodatni materijal kako bi se izveo potrebni rez armiranog betona. | m |  | 6375 | 0 | 2.4 | 15300 |  | 0 | 2.4 | 15300 | [33 empty] | 2.4 | 6375 | 15300 |  |  |  | 2.4 | 15300 |  | 2.4 | 6375 | 15300
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.2. | Rezanje betona u armiranobetonskoj gornjoj ploči bazena za oborinske vode (okno za crpke). Rezanje se izvodi pomoću dijamantne pile. Dubina reza iznosi 25 cm, a dimenzije reza su 1200 x 1500 mm. Stavka uključuje sav potreban rad, opremu i transport opreme za rezanje, te eventualni dodatni materijal kako bi se izveo potrebni rez armiranog betona. | m |  | 4500 |  | 5.4 | 24300 |  | 0 | 5.4 | 24300 | [33 empty] | 5.4 | 4500 | 24300 |  |  |  | 5.4 | 24300 |  | 5.4 | 4500 | 24300
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.3. | Bušenje rupe u zidovima bazena za oborinske vode i okna za priključak vatrogasnog crijeva za prolazak cijevi DN50. | kom |  | 8150 | 0 | 1 | 8150 |  | 0 | 1 | 8150 | [33 empty] | 1 | 8150 | 8150 |  |  |  | 1 | 8150 |  | 1 | 8150 | 8150
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.4. | Bušenje rupe u gornjoj ploči bazena za procjedne vode prolazak cijevi oduška promjera 3''. | kom |  | 8150 | 0 | 1 | 8150 |  | 0 | 1 | 8150 | [33 empty] | 1 | 8150 | 8150 |  |  |  | 1 | 8150 |  | 1 | 8150 | 8150
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.5. | Nabava, doprema i ugradnja betona tlačne čvrstoće C25/30 za izvedbu grla okana i okna za priključenje vatrogasnog crijeva za pranje površina kod bazena za oborinske vode. Stavka uključuje obodnu oplatu, njegu betona i atest tlačne čvrstoće. | m³ |  | 1300 | 0 | 2 | 2600 |  | 0 | 2 | 2600 | [33 empty] | 2 | 1300 | 2600 |  |  |  | 2 | 2600 |  | 2 | 1300 | 2600
| (stavka D.2.3.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
1.6. | Nabava, doprema i ugradnja konstruktivne armature od čelika kvalitete B 500 B u svrhu izvedbe grla okana i okna za priključenje crijeva za pranje površina kod bazena za oborinske vode. Stavka uključuje nabavu, dopremu, rezanje, oblikovanje, prijenos do mjesta ugradnje i ugradnju. Stavka također uključuje atest ugrađene armature. | kg |  | 7.5 | 0 | 160 | 1200 |  | 0 | 160 | 1200 | [33 empty] | 160 | 7.5 | 1200 |  |  |  | 160 | 1200 |  | 160 | 7.5 | 1200
| (stavka D.3.1.) | [49 empty] | 0 | 0 |  | 0 | 0 | 0
1.7. | Nabava, doprema i ugradnja čeličnih ljestvi duljine 232 cm, odvojene od dna bazena 29 cm. Antikorozivna zaštita je vruće cinčanje za razred korozivnosti C5. Penjalice izvesti od okruglog profila promjera 16 mm. Penjalice su široke 45 cm te su na osnom razmaku od 30 cm. Ljestve se montiraju na zid okna sa 4 ankera M8. Ljestve se izvode u jednom komadu, tako da su prečke zavarene na dva flaha debljine minimalno 8 mm. Stavka uključuje i izvedbu pripadajućeg leđobrana prema važećem Zakon o zaštiti na radu i spoj na uzemljenje. | kom |  | 11258.7 | 0 | 1 | 11258.7 |  | 0 | 1 | 11258.7 | [33 empty] | 0 | 11258.7 | 0 | 1 | 11258.7 | 11258.7 | 1 | 11258.7 |  | 1 | 11258.7 | 11258.7
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.8. | Nabava, doprema i ugradnja čeličnih ljestvi duljine 303 cm, odvojene od dna taložnice prema 30 cm. Antikorozivna zaštita je vruće cinčanje za razred korozivnosti C5. Penjalice izvesti od okruglog profila promjera 16 mm. Penjalice su široke 45 cm te su na osnom razmaku od 30 cm. Ljestve se montiraju na zid okna sa 4 ankera M8. Ljestve se izvode u jednom komadu, tako da su prečke zavarene na dva flaha debljine minimalno 8 mm. Stavka uključuje i izvedbu pripadajućeg leđobrana prema važećem Zakon o zaštiti na radu i spoj na uzemljenje. | kom |  | 12170 | 0 | 1 | 12170 |  | 0 | 1 | 12170 | [33 empty] | 0 | 12170 | 0 | 1 | 12170 | 12170 | 1 | 12170 |  | 1 | 12170 | 12170
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.9. | Nabava, doprema i ugradnja čeličnih ljestvi duljine 440 cm, odvodjene od dna bazena 29 cm. Antikorozivna zaštita je vruće cinčanje za razred korozivnosti C5. Penjalice izvesti od okruglog profila promjera 16 mm. Penjalice su široke 45 cm te su na osnom razmaku od 30 cm. Ljestve se montiraju na zid okna sa 4 ankera M8. Ljestve se izvode u jednom komadu, tako da su prečke zavarene na dva flaha debljine minimalno 8 mm. Stavka uključuje i izvedbu pripadajućeg leđobrana prema važećem Zakon o zaštiti na radu i spoj na uzemljenje. | kom |  | 12756.5 | 0 | 2 | 25513 |  | 0 | 2 | 25513 | [33 empty] | 0 | 12756.5 | 0 | 2 | 12756.5 | 25513 | 2 | 25513 |  | 2 | 12756.5 | 25513
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.10. | Nabava, doprema i ugradnja kanalskog poklopca pravokutnog oblika dimenzija 600 x 600 mm prema normi HRN EN-124:2015. Stavka uključuje sav potreban rad i materijal za ugradnju. Poklopac klase B 125 (nosivost 125 kN) | kom |  | 4875 | 0 | 2 | 9750 |  | 0 | 2 | 9750 | [33 empty] | 2 | 4875 | 9750 |  |  |  | 2 | 9750 |  | 2 | 4875 | 9750
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.11. | Nabava, doprema i ugradnja kanalskog poklopca pravokutnog oblika dimenzija 1200 x 1200 mm prema normi HRN EN-124:2015. Stavka uključuje sav potreban rad i materijal za ugradnju. Poklopac klase B 125 (nosivost 125 kN) | kom |  | 25525 | 0 | 1 | 25525 |  | 0 | 1 | 25525 | [33 empty] | 1 | 25525 | 25525 |  |  |  | 1 | 25525 |  | 1 | 25525 | 25525
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.12. | Nabava, doprema i ugradnja elemenata cjevovoda unutar okna za priključenje vatrogasnog crijeva za pranje površina kod bazena za oborinske vode: | [49 empty] | 0 | 0 |  | 0 | 0 | 0
| - prirubnica s navojem DN50 | kom |  | 515.61 | 0 | 1 | 515.61 |  | 0 | 1 | 515.61 | [33 empty] | 1 | 515.61 | 515.61 |  |  |  | 1 | 515.61 |  | 1 | 515.61 | 515.61
| - nipl DN50 | kom |  | 154.67 | 0 | 3 | 464.01 |  | 0 | 3 | 464.01 | [33 empty] | 3 | 154.67 | 464.01 |  |  |  | 3 | 464.01 |  | 3 | 154.67 | 464.01
| - Y-filtar DN50 | kom |  | 574.5 | 0 | 1 | 574.5 |  | 0 | 1 | 574.5 | [33 empty] | 1 | 574.5 | 574.5 |  |  |  | 1 | 574.5 |  | 1 | 574.5 | 574.5
| - razdjelni komad DN50 | kom |  | 447.1 | 0 | 1 | 447.1 |  | 0 | 1 | 447.1 | [33 empty] | 1 | 447.1 | 447.1 |  |  |  | 1 | 447.1 |  | 1 | 447.1 | 447.1
| - ventil DN50 | kom |  | 769.5 | 0 | 1 | 769.5 |  | 0 | 1 | 769.5 | [33 empty] | 1 | 769.5 | 769.5 |  |  |  | 1 | 769.5 |  | 1 | 769.5 | 769.5
| - spojnica za vatrogasno crijevo DN50 | kom |  | 444.89 | 0 | 1 | 444.89 |  | 0 | 1 | 444.89 | [33 empty] | 1 | 444.89 | 444.89 |  |  |  | 1 | 444.89 |  | 1 | 444.89 | 444.89
| - redukcija DN50/25 | kom |  | 287.3 | 0 | 1 | 287.3 |  | 0 | 1 | 287.3 | [33 empty] | 1 | 287.3 | 287.3 |  |  |  | 1 | 287.3 |  | 1 | 287.3 | 287.3
| - nipl DN25 | kom |  | 140.4 | 0 | 2 | 280.8 |  | 0 | 2 | 280.8 | [33 empty] | 2 | 140.4 | 280.8 |  |  |  | 2 | 280.8 |  | 2 | 140.4 | 280.8
| - ventil DN25 | kom |  | 487.4 | 0 | 1 | 487.4 |  | 0 | 1 | 487.4 | [33 empty] | 1 | 487.4 | 487.4 |  |  |  | 1 | 487.4 |  | 1 | 487.4 | 487.4
| - spojni komad sa slobodnom maticom (PEHD-č) OD32/DN25 | kom |  | 401.6 | 0 | 1 | 401.6 |  | 0 | 1 | 401.6 | [33 empty] | 1 | 401.6 | 401.6 |  |  |  | 1 | 401.6 |  | 1 | 401.6 | 401.6
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1.13. | Nabava dobprema i ugradnja oduška bazena za procjedne vode. Odušak se izvodi od čeličnih cijevi promjera 3'' te tzv. lule koja se izvodi od dva luka 90° promjera 3''. Visina oduška od kote uređenog terena iznosi 5 m. Stavka uključuje izvedbu antikorozivne zaštite (temeljni i finalni premaz) i spoj na uzemljenje. | komplet |  | 20550 | 0 | 1 | 20550 |  | 0 | 1 | 20550 | [33 empty] | 1 | 20550 | 20550 |  |  |  | 1 | 20550 |  | 1 | 20550 | 20550
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| UKUPNO |  |  |  | 0 |  | 169139.41 |  | 0 |  | 169139.41 | [35 empty] | 120197.71 |  |  | 48941.7 | 0 | 169139.41 |  | 0 | 0 | 169139.41
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.2 SUMMARY |  |  |  | 0 |  | 694927.31 |  | 0 |  | 694927.31 | [35 empty] | 638559.2472 |  |  | 48941.7 | 0 | 687500.9472 |  | 0 | 0 | 687500.9472
[51 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.3 | [49 empty] | 0 | 0 |  | 0 | 0 | 0
[51 empty] | 0 | 0 |  | 0 | 0 | 0
1. | Nabavu, dopremu i ugradnju kompaktnog prekidača snage s mogućnosti daljinskog isklopa signalom 230V uz dodatne preinake prema zahtjevu strojarskog i elektro nadzora koji su izvedeni na terenu dana 03.12.2019. | kom |  | 16635 | [5 empty] | 1 | 16635 | [36 empty] | 1 | 16635 | 16635 | 1 | 16635 |  | 1 | 16635 | 16635
[51 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
2. | Troškovi zastoja u periodu od 24.01.18. do 13.04.19. | [12 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
|  | kom |  | 453032.73 | [5 empty] | 1 | 453032.73 |  |  | 0 | [33 empty] | 1 | 453032.73 | 453032.73 | 1 | 453032.73 |  | 1 | 453032.73 | 453032.73
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
| ADENDA no.3 SUMMARY | [9 empty] | 469667.73 |  |  | 0 | [35 empty] | 469667.73 | 0 | 469667.73 |  | 0 | 0 | 469667.73
[14 empty] | 0 | [36 empty] | 0 | 0 |  | 0 | 0 | 0
[14 empty] | 0 | [36 empty] | 0
| TOTAL SUMMARY | [12 empty] | 0
0
A | ARCHITECTURAL WORKS |  |  |  | 428000 |  | 0 |  | 0 |  | 428000 |  |  | 0 | [23 empty] | 249000 |  |  | 111000 |  |  | 0 |  |  | 0 |  |  | 0 |  | 360000 |  |  |  | 360000
0
B | CIVIL WORKS - TRAFFIC AND MANIPULATIVE AREA |  |  |  | 217020 |  | 0 |  | 0 |  | 217020 |  |  | 0 | [23 empty] | 5000 |  |  | 0 |  |  | 196030 |  |  | 0 |  |  | 0 |  | 201030 |  |  |  | 201030
0
C | CIVIL WORKS - WATER SUPPLY AND DRAINAGE |  |  |  | 203803.05 |  | 0 |  | 0 |  | 203803.05 |  |  | 0 | [23 empty] | 51863.5 |  |  | 168724.32 |  |  | 41558.8 |  |  | 0 |  |  | 0 |  | 262146.62 |  |  |  | 262146.62
0
D | CIVIL WORKS - CONSTRUCTION |  |  |  | 404721.5 |  | 0 |  | 0 |  | 404721.5 |  |  | 0 | [23 empty] | 214102.075 |  |  | 106997.3 |  |  | 35926.56 |  |  | 0 |  |  | 0 |  | 357025.935 |  |  |  | 357025.935
0
E | CIVIL WORKS - LANDFILL (STAGE II, PHASE 1) |  |  |  | 19314104 |  | 456952.99 |  | 3238039.2 |  | 16533017.79 |  |  | 320292.662 |  |  | 76894.34 |  |  | 2084103.745 |  |  | 2870506.44 |  |  | 2636119.1 |  |  | 3784470.6 |  |  | 831464.78 |  |  | 2414044.34 |  |  | 1612208.02 |  |  | 144152 |  |  | 20281.25 |  |  | 0 |  |  | 0 |  | 16794537.277 |  |  |  | 16794537.277
0
F | MECHANICAL WORKS |  |  |  | 765000 |  | 0 |  | 0 |  | 765000 |  |  | 0 | [23 empty] | 35000 |  |  | 46000 |  |  | 0 |  |  | 0 |  |  | 0 |  | 265000 |  |  |  | 265000
[14 empty] | 0 | [20 empty] | 184000
G | ELECTROTEHNICAL WORKS |  |  |  | 622677 |  | 0 |  | 0 |  | 622677 |  |  | 0 | [23 empty] | 0 |  |  | 282593 |  |  | 166026 |  |  | 91841 |  |  | 30120 |  | 570580 |  |  |  | 570580
0
| ADENDA no.1 | [5 empty] | 11506898.845 |  | 0 |  | 11506898.845 |  |  | 0 |  |  | 2699080.87 |  |  | 1064877.17 |  |  | 555842.8 |  |  | 2114416.225 |  |  | 2905800 |  |  | 601200 |  |  | 729710.675 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 10670927.74 |  |  |  | 10670927.74
| ADENDA no.2 | [45 empty] | 638559.2472 |  |  | 48941.7 |  | 687500.9472 |  |  |  | 687500.9472
| ADENDA no.3 | [48 empty] | 469667.73 |  | 469667.73 |  |  |  | 469667.73
0
| TOTAL SUMMARY |  |  |  | 21955325.55 |  | 11963851.835 |  | 3238039.2 |  | 30681138.185 |  |  | 320292.662 |  |  | 2775975.21 |  |  | 3148980.915 |  |  | 3426349.24 |  |  | 4750535.325 |  |  | 6690270.6 |  |  | 1432664.78 |  |  | 3327755.015 |  |  | 2167173.595 |  |  | 859466.62 |  |  | 459822.61 |  |  | 730400.2472 |  |  | 548729.43 |  | 30638416.2492 |  |  |  | 30638416.2492
[14 empty] | 0 | [36 empty] | 0
| RAZLIKA: |  |  |  | 8725812.635 | [8 empty] | 0 | [36 empty] | 0 |  |  | 0 | 0 | 0